## Slats
Issue | Desc. | Phase | Ref | ECD
1 | FILLET SEALS ON FITTINGS WRONG SPEC | 3 | N/A | N/A
2 | ON RIB #1 FOULING CONDITION BETWEEN DOUBLER AND SKIN | 2 | N/A | N/A
3 | EXCESSIVE GAPPING BTW SKIN, OUTER AND FITTING ASSY | 3 | N/A | N/A
4 | LOW THICKNESS ON SLAT SKINS | 3 | N/A | N/A

## TC5-6
Issue | Desc. | Phase | Ref | ECD
1 | STEP CONDITION BETWEEN APU DOORS AND TAILCONE ASSEMBLY | 3 | N/A | N/A
2 | HOLE WITH LOW ED IN SKIN ASSY, RH, FWD TAILCONE | 3 | N/A | N/A
3 | TWO FASTENERS B0207005M5-02 ARE INSTALLED ON THE INLET GA452-0057-1 FASTENERS ARE NOT ACCEPTED AS PER BAPS 151-010 | 3 | N/A | N/A
4 | THERE IS A DISCREPANCY BETWEEN DWG 2D AND 3D (CATIA V5) ON INSTALLATION OF FRAMES: FRAME RH UPR FS1081.2 R/F (GD238-6834-5) AND FRAME LH FS 1081.2 R/FUSE (GD238-6817-11) | 3 | N/A | N/A
5 | TC7500 INSTALLED QTY 6 RIVETS FAR SIDE, DUE TO THE ACCESS COMMON PARTS: PANEL CLOSE OUT (GD239_`9095_`9) | 3 | N/A | N/A

## TC7-8
Issue | Desc. | Phase | Ref | ECD
1 | FOULING CONDITION BETWEEN G05393108-101 AND G05393109-101 | 3 | N/A | N/A
2 | EXIST QTY (3) LATCH OUT OF TOLERANCE OF STEP AS PER DRAWING G00606301 TOLERANCE S/B +0.010"/-0.015" | 4 | N/A | N/A
3 | STEP CONDITION BETWEEN APU DOORS AND TAILCONE ASSEMBLY | 3 | N/A | N/A
4 | SKINS SKIN, RH FWD, SUB ASSY G05394080-005 AND SKIN, LH FWD, SUB ASSY G05394001-007 IT IS NOT POSSIBLE TO MEET THE REQUIREMENTS OF THE DWG | 3 | N/A | N/A
5 | DOUBLE HOLE | 3 | N/A | N/A
6 | EXIST QTY (14) HOLE OVER SIZE IN SKIN, TOP, FWD (G05394064-101) | 3 | N/A | N/A
7 | HOLE WITH LOW ED IN SKIN ASSY, RH, FWD TAILCONE | 3 | N/A | N/A
8 | EXISTS GAP WITH THE PART G05394010-101 BETWEEN G05394020-101(SIDE 1 UPPER) AND G05394014-101 (SIDE 2 LOWER) | 3 | N/A | N/A
9 | AFFECTED PARTS BUSHING 399-67-113 BOLT NAS6705DU16 IN DOOR ACTUATOR G04900012-007. FOUND JAMMED BOLT AND BUSHING , THE BUSHING SEATS ON THE RADIUS CAUSING SEIZURE OF ALL ASSEMBLY. | 3 | N/A | N/A
10 | DEPRESIONES | 3 | N/A | N/A
11 | THERE IS A TAPER GAP BETWEEN ANGLE (G05394098-101) AND STIFFENER (GD238-8124-1) | 3 | N/A | N/A
12 | FOULING CONDITION (Intercostakl)BTWN SURROUND ANGLE GD238-6991-2 AND GD238-6991-1 | 3 | N/A | N/A
13 | TC7500 INSTALLED QTY 6 RIVETS FAR SIDE, DUE TO THE ACCESS COMMON PARTS: PANEL CLOSE OUT (GD239_`9095_`9) | 3 | N/A | N/A

## Z1
Issue | Desc. | Phase | Ref | ECD
1 | AT REAR SPAR A DEVIATION IS NOTED AT LOCAL AXIS CENTER LINE OF HINGES | 3 | N/A | N/A
2 | OVERGAP BETWEEN BUSHING AND GUARD PIN | 4 | N/A | N/A
3 | WAS INSTALLED AT WRONG SIDE CONDUIT ASSY, SATCOM AND CONDUIT ASSY, SATCOM COAX | 4 | N/A | N/A

## Z2
Issue | Desc. | Phase | Ref | ECD
1 | FOULING CONDITION BTWN WEB, FRONT SPAR AND ANGLE, SHEAR, VERTICAL STABILIZER | 2 | N/A | N/A
2 | TAPERED GAP NOTED ON FRAME ASSY FS 987 WITH SPAR, FRONT, INTERFACE FITTING & SPAR, FRONT, INTERFACE FITTING | 2 | N/A | N/A
3 | TAPPERED GAP BETWEEN VERTICAL STIFFENER AND SHEAR PLATE | 3 | N/A | N/A
4 | N/A | N/A | N/A | N/A

## Z3
Issue | Desc. | Phase | Ref | ECD
1 | ISSUE 85 | 2 | N/A | N/A
2 | ISSUE 84 | 2 | N/A | N/A
3 | STEP CONDITION BETWEEN APU DOORS AND TAILCONE ASSEMBLY | 3 | N/A | N/A
4 | TAPPER GAP BTW INTERCOSTAL, STGR #6 AND FRAME PANEL | 3 | N/A | N/A
5 | RESINTANCE TOO HIGH AT SHELF ASSY, HF #1 | 3 | N/A | N/A
6 | RESINTANCE TOO HIGH AT SHELF ASSY, HF #2 | 3 | N/A | N/A
7 | WAS INSTALLED HI-LITE B0206001AG5 IN BONDED PANEL ASSY, RH AND LH IN LIEU OF B/P MS90354U0503W | 4 | N/A | N/A
8 | EXIST QTY (18) HOLE WITH LOW E.D. ON DRAG ANGLE, UPPER PYLON, RH (GD617-4051-3). | 4 | N/A | N/A
9 | CONNECTOR HARNESS M145 L/H DON'T COMPLY WITH DWG REQUIREMENTS | 4 | N/A | N/A
10 | AT TEE GD421-7810-1 EXISTS LOW E.D | 3 | N/A | N/A
11 | LOCATION BL 0.000 & FS 844.75 UNABLE TO INSTALL GD42-7800-3 VELCRO (PLY) ON GD421-7874-47 PANEL ASSY | 4 | N/A | N/A