## Old Data
Zone | BADGE | NCR # | NCR Type | Disc. Create Date | Work Centre | Norm. Line Position | Tail # | Part # | Part Desc | Action | ¿Repetitivo? | COS | Number | Phase | PSS # | ECD_or_AC | Comments | Query
Zone 4 | Methods | Q321006285-1 | SNC | 2021-04-05 | AGX955 | AGX955 | 70099 | G09171071-005 | CABLE, PWR FDR, ACEPC 1 APU TB RAP | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD
Zone 4 | Methods | Q321006285-2 | SNC | 2021-04-05 | AGX955 | AGX955 | 70099 | G09171057-007 | CABLE, PWR FDDR, VFG LHS ACEPC 1 PH A RL | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD
Zone 5 | Methods | Q321006304-1 | STANDARD | 2021-04-05 | AGX290 | AGX290 | 70107 | G05310750-001-01 | COCKPIT NOSE ASSY | NO | NO | N/A | N/A | 1 Problema detectado | PSS WIP for analisys from disc 001 from Dimensional Capsule Nose | TBD
Zone 5 | Methods | Q321006304-2 | STANDARD | 2021-04-05 | AGX290 | AGX290 | 70107 | G05310750-001-01 | COCKPIT NOSE ASSY | NO | NO | N/A | N/A | 1 Problema detectado | PSS WIP for analisys from disc 001 from Dimensional Capsule Nose | TBD
Zone 5 | Methods | Q321006304-3 | STANDARD | 2021-04-05 | AGX290 | AGX290 | 70107 | G05310750-001-01 | COCKPIT NOSE ASSY | NO | NO | N/A | N/A | 1 Problema detectado | PSS WIP for analisys from disc 001 from Dimensional Capsule Nose | TBD
Zone 3.2 | Methods | Q321006315-1 | STANDARD | 2021-04-05 | AGX830 | AGX830 | 70102 | G05364510-001 | CELL INSTL, FLEXIBLE, AFT FUEL TANK | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.4 | Methods | Q321006320-1 | STANDARD | 2021-04-05 | AGX952 | AGX952 | 70101 | G05450057-014 | TE ASSY, REMOVABLE, PYLON | YES | YES | COS | G05450508-108-02 & G05450509-108-03 | 4 Solución en espera de ser aprobada |  | 70113-X & 70130-X | CSK DEPTH. QUERY 3274
Zone 4 | Methods | Q321006322-1 | STANDARD | 2021-04-05 | AGX985 | AGX985 | 70098 | G05530140-003 | PANEL INSTL, ACCESS PANEL, VSTAB | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.2 | Methods | Q321006333-1 | SNC | 2021-04-05 | AGX830 | AGX830 | 70104 | G05372104-001 | ECS INSTL, PACK PROVISION, REAR FUSE | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.1 | Methods | Q321006347-1 | STANDARD | 2021-04-06 | AGX802 | AGX802 | 70106 | G05372102-003 | ECS INSTL TRIM AIR PROVISIONS | NO | yes | N/A | N/A | 1 Problema detectado |  | 2021-08-27
Zone 3.1 | Methods | Q321006351-1 | EXTENSION | 2021-04-06 | AGX810 |  | 70104 | G05362084-101 | CLEAT, AFT FUSE | NO | YES | N/A | N/A | 1 Problema detectado |  | 70132
Zone 3.1 | Methods | Q321006352-1 | EXTENSION | 2021-04-06 | AGX810 |  | 70105 | G05362084-101 | CLEAT, AFT FUSE | NO | YES | N/A | N/A | 1 Problema detectado |  | 70132
Zone 3.1 | Methods | Q321006353-1 | EXTENSION | 2021-04-06 | AGX810 | AGX810 | 70106 | G05362084-101 | CLEAT, AFT FUSE | NO | YES | N/A | N/A | 1 Problema detectado |  | 70132
Zone 3.1 | Methods | Q321006354-1 | EXTENSION | 2021-04-06 | AGX810 |  | 70107 | G05362084-101 | CLEAT, AFT FUSE | NO | YES | N/A | N/A | 1 Problema detectado |  | 70132
Zone 3.1 | Methods | Q321006355-1 | EXTENSION | 2021-04-06 | AGX810 |  | 70108 | G05362084-101 | CLEAT, AFT FUSE | NO | YES | N/A | N/A | 1 Problema detectado |  | 70132
Zone 3.1 | Methods | Q321006356-1 | EXTENSION | 2021-04-06 | AGX810 |  | 70109 | G05362084-101 | CLEAT, AFT FUSE | NO | YES | N/A | N/A | 1 Problema detectado |  | 70132
Zone 3.1 | Methods | Q321006357-1 | EXTENSION | 2021-04-06 | AGX810 |  | 70110 | G05362084-101 | CLEAT, AFT FUSE | NO | YES | N/A | N/A | 1 Problema detectado |  | 70132
Zone 3.1 | Methods | Q321006358-1 | EXTENSION | 2021-04-06 | AGX810 |  | 70111 | G05362084-101 | CLEAT, AFT FUSE | NO | YES | N/A | N/A | 1 Problema detectado |  | 70132
Zone 3.1 | Methods | Q321006359-1 | EXTENSION | 2021-04-06 | AGX810 |  | 70112 | G05362084-101 | CLEAT, AFT FUSE | NO | YES | N/A | N/A | 1 Problema detectado |  | 70132
Zone 3.1 | Methods | Q321006360-1 | EXTENSION | 2021-04-06 | AGX810 |  | 70113 | G05362084-101 | CLEAT, AFT FUSE | NO | YES | N/A | N/A | 1 Problema detectado |  | 70132
Zone 4 | Methods | Q321006361-1 | SNC | 2021-04-06 | AGX955 | AGX955 | 70100 | G09171071-005 | CABLE, PWR FDR, ACEPC 1 APU TB RAP | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD
Zone 4 | Methods | Q321006361-2 | SNC | 2021-04-06 | AGX955 | AGX955 | 70100 | G09171057-007 | CABLE, PWR FDDR, VFG LHS ACEPC 1 PH A RL | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.3 | Methods | Q321006379-1 | STANDARD | 2021-04-06 | AGX950 | AGX950 | 70101 | G05363640-003 | DOOR ASSY, GROUND AIR, AFT BARREL | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.2 | Methods | Q321006383-1 | STANDARD | 2021-04-06 | AGX830 | AGX830 | 70103 | G05364666-107-01 | PLATE, FLOOR, FUEL TANK | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD |  | 3508
MTS | Methods | Q321006384-1 | STANDARD | 2021-04-06 | SGX965 | SGX965 |  | G02490961-103 | SUPPORT, PANEL SERVICE LIGHTS, AFT FUSE | YES | YES | RFC | 61563 | 4 Solución en espera de ser aprobada |  | TBD |  | 2560
Zone 3.2 | Methods | Q321006421-1 | STANDARD | 2021-04-06 | AGX830 | AGX830 | 70102 | G02895000-001 | FUEL INSTL, VENT, REAR FUSE | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD |  | 2560
Zone 2 | Methods | Q321006422-1 | STANDARD | 2021-04-06 | AGX880 | AGX880 | 70105 | G05530119-003 | SKIN INSTL, VSTAB, LH | YES | Yes | RFC | 3000168585 | 4 Solución en espera de ser aprobada |  | TBD | QUERY 4126/ Waiting RFC 26 May | 2756
Zone 3.3 | Methods | Q321006426-3 | STANDARD | 2021-04-06 | AGX950 | AGX952 | 70103 | G05363926-102 | INTERCOSTAL, MOORING, FTG AFT BARREL | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD |  | 2560
Zone 3.3 | Methods | Q321006426-4 | STANDARD | 2021-04-06 | AGX950 | AGX952 | 70103 | G05363926-101 | INTERCOSTAL, MOORING, FTG, AFT BARREL | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD |  | 2560
Zone 3.3 | Methods | Q321006426-1 | STANDARD | 2021-04-06 | AGX950 | AGX952 | 70103 | G05363921-001 | JOINT INSTL, STA 1016, REAR FUSE | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.3 | Methods | Q321006426-2 | STANDARD | 2021-04-06 | AGX950 | AGX952 | 70103 | G05363921-001 | JOINT INSTL, STA 1016, REAR FUSE | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
MTS | Methods | Q321006440-1 | STANDARD | 2021-04-06 | SGX965 | SGX965 |  | G02490961-103 | SUPPORT, PANEL SERVICE LIGHTS, AFT FUSE | YES | YES | RFC | 61563 | 4 Solución en espera de ser aprobada |  | TBD
MTS | Methods | Q321006445-1 | STANDARD | 2021-04-06 | SGX900 | SGX900 |  | G05211418-101 | PLATE, HINGE STEP, PASS ACS DR | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Q 4320
MTS | Methods | Q321006482-1 | STANDARD | 2021-04-07 | SGX948 | SGX948 |  | G05450432-002-04 | BRACKET ASSY, CTR BOX, PYLON | YES | YES | RFC | 3000165719 | 4 Solución en espera de ser aprobada |  | 70110 ?
MTS | Methods | Q321006531-1 | STANDARD | 2021-04-07 | SGX730 | SGX730 |  | G05293053-101 | RETAINER, BEARING | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Q 4502
MTS | Methods | Q321006567-1 | STANDARD | 2021-04-07 | SGX975 | SGX975 |  | G02197162-012-01 | INLET ASSY, MECH, PRECOOLER, PYLON | YES | YES | RFC | 3000163508 | 4 Solución en espera de ser aprobada |  | 70100
Zone 3.1 | Methods | Q321006516-1 | STANDARD | 2021-04-07 | AGX810 | AGX810 | 70106 | G05360040-001 | FLOOR INSTLALLATION, REAR FUSE | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.3 | Methods | Q321006523-1 | STANDARD | 2021-04-07 | AGX950 | AGX950 | 70102 | G05530170-001 | FAIRING INSTL, DORSAL | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Query 4475
Zone 3.3 | Methods | Q321006562-1 | STANDARD | 2021-04-07 | AGX950 | AGX950 | 70104 | G05363447-105 | SPLICE, REAR SPAR, AFT BARREL | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.3 | Methods | Q321006562-2 | STANDARD | 2021-04-07 | AGX950 | AGX950 | 70104 | G05363637-103 | STRAP, LOWER PANEL, AFT BARREL | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.4 | Methods | Q321006534-1 | STANDARD | 2021-04-07 | AGX952 | AGX952 | 70103 | G05450378-103 | FITTING, TENSION, FIXED TE, PYLON | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD | GAP TENSION FITTING TE FIXED ASSY
Zone 4 | Methods | Q321006514-1 | STANDARD | 2021-04-07 | AGX985 | AGX985 | 70098 | G05530150-001-90 | FAIRING INSTL, BULLET | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 4 | Methods | Q321006572-1 | STANDARD | 2021-04-07 | AGX964 | AGX965 | 70099 | 627700-1002 | PTU - MOTOR/PUMP PACKAGE INTERFACE DEF | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | QUERY 3387
Zone 3.4 | Methods | Q321006418-1 | sTANDARD | 2021-04-07 | AGX952 | AGX952 | 70103 | G05450363-104 | RIB, FIXED TE, PYLON | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD | FOULING RIB VS BUCKET DUE TO ISSUE LOCATING PYLON 70103
Zone 4 | Methods | Q321006453-1 | EXTENSION | 2021-04-07 | AGX955 |  | 70101 | G09172051-019 | HARNESS, AFT FUSE, REAR RHS RBB | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Query 4534 26-JUN
Zone 4 | Methods | Q321006454-1 | EXTENSION | 2021-04-07 | AGX955 |  | 70102 | G09172051-019 | HARNESS, AFT FUSE, REAR RHS RBB | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Query 4534 26-JUN
Zone 4 | Methods | Q321006455-1 | EXTENSION | 2021-04-07 | AGX955 |  | 70103 | G09172051-019 | HARNESS, AFT FUSE, REAR RHS RBB | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Query 4534 26-JUN
Zone 4 | Methods | Q321006458-1 | EXTENSION | 2021-04-07 | AGX955 |  | 70101 | G09171051-019 | HARNESS, AFT FUSE, REAR LHS RAB | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Query 4173 28/MAYO
Zone 4 | Methods | Q321006459-1 | EXTENSION | 2021-04-07 | AGX955 |  | 70102 | G09171051-019 | HARNESS, AFT FUSE, REAR LHS RAB | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Query 4173 28/MAYO
Zone 4 | Methods | Q321006460-1 | EXTENSION | 2021-04-07 | AGX955 |  | 70103 | G09171051-019 | HARNESS, AFT FUSE, REAR LHS RAB | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Query 4173 28/MAYO
Zone 4 | Methods | Q321006461-1 | EXTENSION | 2021-04-07 | AGX955 |  | 70101 | G09172051-019 | HARNESS, AFT FUSE, REAR RHS RBB | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Query 4451 Clamps* / 26/JUN
Zone 4 | Methods | Q321006462-1 | EXTENSION | 2021-04-07 | AGX955 |  | 70102 | G09172051-019 | HARNESS, AFT FUSE, REAR RHS RBB | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Query 4451 Clamps* / 26/JUN
Zone 4 | Methods | Q321006463-1 | EXTENSION | 2021-04-07 | AGX955 |  | 70103 | G09172051-019 | HARNESS, AFT FUSE, REAR RHS RBB | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Query 4451 Clamps* / 26/JUN
Zone 4 | Methods | Q321006464-1 | EXTENSION | 2021-04-07 | AGX955 |  | 70101 | G09171051-019 | HARNESS, AFT FUSE, REAR LHS RAB | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Query 3942 11/JUN
Zone 4 | Methods | Q321006465-1 | EXTENSION | 2021-04-07 | AGX955 |  | 70102 | G09171051-019 | HARNESS, AFT FUSE, REAR LHS RAB | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Query 3942 11/JUN
Zone 4 | Methods | Q321006466-1 | EXTENSION | 2021-04-07 | AGX955 |  | 70103 | G09171051-019 | HARNESS, AFT FUSE, REAR LHS RAB | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Query 3942 11/JUN
Zone 3.3 | Methods | Q321006577-1 | STANDARD | 2021-04-08 | AGX950 | AGX950 | 70101 | G05363963-105 | FITTING, STRG 4, OUTBD | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.3 | Methods | Q321006577-2 | STANDARD | 2021-04-08 | AGX950 | AGX950 | 70101 | G05363963-106 | FITTING, STRG 4, OUTBD | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.4 | Methods | Q321006610-1 | STANDARD | 2021-04-08 | AGX952 | AGX952 | 70102 | G05370026-001-01 | FIDEX INSTL, PROVISIONS, REAR FUSE | YES | YES | COS | G05363284-101-02 | 4 Solución en espera de ser aprobada | TBD | TBD | New COS G05363284-101-02. DDA 11138A
Zone 4 | Methods | Q321006595-1 | STANDARD | 2021-04-08 | AGX965 | AGX965 | 70098 | G02123249-003 | DUCT ASSY, RIGID | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Query 4431
Zone 4 | Methods | Q321006604-1 | STANDARD | 2021-04-08 | AGX965 | AGX965 | 70099 | G02123249-003 | DUCT ASSY, RIGID | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Query 4431
Zone 4 | Methods | Q321006626-1 | STANDARD | 2021-04-08 | AGX965 | AGX965 | 70099 | G02691253-003 | TUBE ASSY, FIDEX, ENG LH | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD | Revisar
Zone 4 | Methods | Q321006637-1 | STANDARD | 2021-04-08 | AGX985 | AGX985 |  | G05530608-002 | SKIN ASSY, LWR HSTA ACCESS, BLT FAIR, RH | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 5 | Methods | Q321006589-1 | STANDARD | 2021-04-08 | AGX276 | AGX276 | 70107 | G05311192-101/01 | ANGLE, MLG, DOOR | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Query 2934, 70110-x
Zone 5 | Methods | Q321006608-5 | STANDARD | 2021-04-08 | AGX290 | AGX290 | 70105 | G05310750-001-01 | COCKPIT NOSE ASSY | NO | NO | N/A | N/A | 1 Problema detectado | PSS WIP for analisys from disc 001 from Dimensional Capsule Nose | TBD
Zone 5 | Methods | Q321006608-3 | STANDARD | 2021-04-08 | AGX290 | AGX290 | 70105 | G05310750-001-01 | COCKPIT NOSE ASSY | NO | NO | N/A | N/A | 1 Problema detectado | PSS WIP for analisys from disc 001 from Dimensional Capsule Nose | TBD
Zone 5 | Methods | Q321006608-4 | STANDARD | 2021-04-08 | AGX290 | AGX290 | 70105 | G05310750-001-01 | COCKPIT NOSE ASSY | NO | NO | N/A | N/A | 1 Problema detectado | PSS WIP for analisys from disc 001 from Dimensional Capsule Nose | TBD
Zone 3.1 | Methods | Q321006655-1 | STANDARD | 2021-04-09 | AGX802 | AGX802 | 70107 | G05372102-003 | ECS INSTL TRIM AIR PROVISIONS | NO | yes | N/A | N/A | 1 Problema detectado |  | 2021-08-27
Zone 5 | Methods | Q321006659-1 | STANDARD | 2021-04-09 | AGX276 | AGX276 | 70108 | G05311192-101/01 | ANGLE, MLG, DOOR | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Query 2934, 70110-x
Zone 3.4 | Methods | Q321006660-2 | STANDARD | 2021-04-09 | AGX952 | AGX952 | 70103 | G05450606-101 | ANGLE, DRAG, CTR BOX, PYLON | YES | YES | COS | G005450606-101-04 | 4 Solución en espera de ser aprobada |  | 70108-X | Query 2560
Zone 3.4 | Methods | Q321006660-1 | STANDARD | 2021-04-09 | AGX952 | AGX952 | 70103 | G05450606-101 | ANGLE, DRAG, CTR BOX, PYLON | YES | YES | COS | G05450606-101-05 | 4 Solución en espera de ser aprobada |  | 70128-X | Query 3116
Zone 1 | Methods | Q321006681-1 | STANDARD | 2021-04-09 | AGX744 | AGX744 | 70108 | G05372390-001 | ECS INSTL CPCS PROVISION REAR FUSE | YES | Yes | PCR | 61582 | 4 Solución en espera de ser aprobada |  | TBD | David Lencz da seguimiento al PCR
Zone 5 | Methods | Q321006686-1 | STANDARD | 2021-04-09 | AGX274 | AGX274 | 70110 | G05311032-101/01 | STRIKER, AVIONIC DOOR SEAL, FWD | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD | One off S/B tooling since drill .128" lote was changed
Zone 5 | Methods | Q321006686-2 | STANDARD | 2021-04-09 | AGX274 | AGX274 | 70110 | G05311032-102/01 | STRIKER, AVIONIC DOOR SEAL, FWD | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD | One off S/B tooling since drill .128" lote was changed
Zone 3.2 | Methods | Q321006693-1 | STANDARD | 2021-04-09 | AGX830 | AGX830 | 70102 | G05372201-001 | ECS INSTL, LP PROVISIONS, ABOVE FLOOR | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
MTS | Methods | Q321006696-1 | STANDARD | 2021-04-09 | SGX975 | SGX975 |  | G02197168-105-01 | PANEL, DOOR, PRECOOLER INLET, PYLON | YES | YES | RFC | 3000163508 | 4 Solución en espera de ser aprobada |  | 70100
Zone 3.4 | Methods | Q321006697-1 | STANDARD | 2021-04-09 | AGX952 | AGX952 | 70103 | G05363449-101 | DOUBLER SIDE PANEL AFT BARREL | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Low ED Doubler G05363449. Possible RFC in progress
Zone 3.4 | Methods | Q321006698-3 | STANDARD | 2021-04-09 | AGX952 | AGX952 | 70103 | G05450490-102 | ANGLE, CTR BOX, PYLON | YES | YES | COS | G05450490-102-03 | 4 Solución en espera de ser aprobada |  | 2021-05-28 | Query 4472
Zone 3.4 | Methods | Q321006698-7 | STANDARD | 2021-04-09 | AGX952 | AGX952 | 70103 | G05450476-104 | ANGLE, CTR BOX, PYLON | YES | YES | COS | G05450476-104-03 | 4 Solución en espera de ser aprobada |  | 2021-05-28 | Query 4470
Zone 3.4 | Methods | Q321006698-8 | STANDARD | 2021-04-09 | AGX952 | AGX952 | 70103 | G05450485-102 | ANGLE, CTR BOX, PYLON | YES | YES | COS | G05450485-102-03 | 4 Solución en espera de ser aprobada |  | TBD | Query 4503
Zone 3.4 | Methods | Q321006698-4 | STANDARD | 2021-04-09 | AGX952 | AGX952 | 70103 | G05450427-101 | RIB, CTR BOX, PYLON | YES | YES | COS | G05450427-102-03 | 4 Solución en espera de ser aprobada |  | 70105-X | Query 2756
Zone 3.4 | Methods | Q321006698-11 | STANDARD | 2021-04-09 | AGX952 | AGX952 | 70103 | G05363449-102 | DOUBLER, SIDE PANEL AFT BARREL | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Low ED Doubler G05363449. Possible RFC in progress
Zone 3.4 | Methods | Q321006698-9 | STANDARD | 2021-04-09 | AGX952 | AGX952 | 70103 | G05450075-002 | BOX INSTL, CENTER, PYLON | YES | YES | COS | G05450062-010-02 | 4 Solución en espera de ser aprobada |  | 70110-X | Query 2560
Zone 3.4 | Methods | Q321006698-10 | STANDARD | 2021-04-09 | AGX952 | AGX952 | 70103 | G05450502-104 | SKIN, UPPER, CTR BOX, PYLON | YES | YES | COS | G05450061-004-04 | 4 Solución en espera de ser aprobada |  | 70105-X | Query 2560
Zone 3.4 | Methods | Q321006698-5 | STANDARD | 2021-04-09 | AGX952 | AGX952 | 70103 | G05450503-104 | SKIN , LWR, CTR BOX, PYLON | YES | YES | COS | G05450605-102-06 | 4 Solución en espera de ser aprobada |  | 70142-X | Query 4402
Zone 3.1 | Methods | Q321006718-1 | STANDARD | 2021-04-10 | AGX810 | AGX810 | 70106 | G05366015-101 | FITTING, FWD ENGINE FRAME | NO | yes | N/A | N/A | 1 Problema detectado | STL PANEL ISSUES | TBD
Zone 3.1 | Methods | Q321006718-2 | STANDARD | 2021-04-10 | AGX810 | AGX810 | 70106 | G05366015-102 | FITTING, FWD ENGINE FRAME | NO | NO | N/A | N/A | 1 Problema detectado | STL PANEL ISSUES | TBD
Zone 1 | Methods | Q321006724-1 | STANDARD | 2021-04-12 | AGX738 | AGX738 | 70101 | G05291600-001 | ELECTRICAL INSTL,CARGO ACS DR | NO | Yes | N/A | N/A | 1 Problema detectado |  | 25/06/2021 | Query # 4450 Method config Queue
Zone 4 | Methods | Q321006751-1 | STANDARD | 2021-04-12 | AGX985 | AGX985 | 70099 | G02894000-001 | FUEL INSTL, FEED, ENGINE, REAR FUSE | NO | NO | N/A | N/A | 1 Problema detectado | Leak fitting Fuel | TBD | Query # 3627
Zone 4 | Methods | Q321006756-1 | SR | 2021-04-12 | AGX955 | AGX955 | 70100 | G05363136-009-01 | FRAME ASSY, AFT ENG MOUNT | YES | YES | RFC | 61756 | 4 Solución en espera de ser aprobada |  | 70110
Zone 3.2 | Methods | Q321006761-1 | STANDARD | 2021-04-12 | AGX830 | AGX830 | 70103 | G05364500-001-01 | STRUCTURE ASSY, FUEL TANK, REAR FUSE | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.2 | Methods | Q321006763-1 | STANDARD | 2021-04-12 | AGX830 | AGX830 | 70103 | G05364510-001 | CELL INSTL, FLEXIBLE, AFT FUEL TANK | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.1 | Methods | Q321006764-1 | STANDARD | 2021-04-12 | AGX806 | AGX806 | 70107 | G05373185-101 | BRACKET, AVIONICS, AFT FUSE | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
MTS | Methods | Q321006790-1 | STANDARD | 2021-04-12 | SGX900 | SGX900 |  | G05211000-001-16 | HINGE SUB-ASSY, PAX DOOR | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Q 4320
Zone 4 | Methods | Q321006844-1 | STANDARD | 2021-04-13 | AGX955 | AGX965 | 70101 | G02691253-003 | TUBE ASSY, FIDEX, ENG LH | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Low clearance Fidex pipe VS clamp, investigación - reclamo cliente
Zone 3.4 | Methods | Q321006852-1 | STANDARD | 2021-04-13 | AGX945 | AGX945 | 70105 | G05450051-007 | LE ASSY, FIXED, PYLON | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.4 | Methods | Q321006867-1 | STANDARD | 2021-04-13 | AGX952 | AGX952 | 70103 | G05370031-001-01 | BATT RACK PREFIT, OPEN FINAL & DEBURR | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | QUEY 4223 IMPLEMENT. A/C 70105
Zone 3.4 | Methods | Q321006872-1 | STANDARD | 2021-04-13 | AGX950 | AGX952 | 70102 | G05363921-003 | JOINT INSTL, STA 1016, REAR FUSE | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | QUERY 4365, gap intercostal vs frame
Zone 3.2 | Methods | Q321006874-1 | STANDARD | 2021-04-13 | AGX830 | AGX830 | 70103 | G02895000-001 | FUEL INSTL, VENT, REAR FUSE | YES | YES | COS | G02895104-009-01 | 4 Solución en espera de ser aprobada |  | TBD | Query 3924, modif posición etiqueta
Zone 3.2 | Methods | Q321006862-1 | STANDARD | 2021-04-13 | AGX820 | AGX820 | 70105 | G05364510-001 | CELL INSTL, FLEXIBLE, AFT FUEL TANK | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.3 | Methods | Q321006882-2 | STANDARD | 2021-04-14 | AGX950 | AGX950 | 70102 | G05363921-003 | JOINT INSTL, STA 1016, REAR FUSE | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD | BY JOINING, double hole
Zone 3.4 | Methods | Q321006887-1 | STANDARD | 2021-04-14 | AGX952 | AGX952 | 70103 | G05450072-001 | TE INSTL, PYLON | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.4 | Methods | Q321006900-2 | STANDARD | 2021-04-14 | AGX947 | AGX947 | 70105 | G05450053-019-01 | BOX ASSY, CENTER, PYLON | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.1 | Methods | Q321006914-1 | STANDARD | 2021-04-14 | AGX810 | AGX810 | 70107 | G05360040-001 | FLOOR INSTL | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Supplier
Zone 3.1 | Methods | Q321006914-2 | STANDARD | 2021-04-14 | AGX810 | AGX810 | 70107 | G05360040-001 | FLOOR INSTL | NO | YES | N/A | N/A | 1 Problema detectado | 34 | TBD | PSS WIP
Zone 3.4 | Methods | Q321006921-1 | STANDARD | 2021-04-14 | AGX952 | AGX952 | 70103 | G05450075-002-01 | BOX INSTL, CENTER, PYLON | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.4 | Methods | Q321006928-1 | STANDARD | 2021-04-14 | AGX948 | AGX948 | 70105 | G05450073-002-01 | TE INSTL, PYLON | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.2 | Methods | Q321006934-1 | EXTENSION | 2021-04-14 | AGX830 |  | 70104 | G02895000-001 | FUEL INSTL, VENT, REAR FUSE | YES | YES | COS | G02895104-009-01 | 4 Solución en espera de ser aprobada |  | TBD | Q3924
Zone 3.2 | Methods | Q321006935-1 | EXTENSION | 2021-04-14 | AGX830 |  | 70105 | G02895000-001 | FUEL INSTL, VENT, REAR FUSE | YES | YES | COS | G02895104-009-02 | 4 Solución en espera de ser aprobada |  | TBD | Q3924
Zone 3.2 | Methods | Q321006936-1 | EXTENSION | 2021-04-14 | AGX830 |  | 70106 | G02895000-001 | FUEL INSTL, VENT, REAR FUSE | YES | YES | COS | G02895104-009-03 | 4 Solución en espera de ser aprobada |  | TBD | Q3924
Zone 3.2 | Methods | Q321006937-1 | EXTENSION | 2021-04-14 | AGX830 |  | 70107 | G02895000-001 | FUEL INSTL, VENT, REAR FUSE | YES | YES | COS | G02895104-009-04 | 4 Solución en espera de ser aprobada |  | TBD | Q3924
Zone 3.2 | Methods | Q321006938-1 | EXTENSION | 2021-04-14 | AGX830 |  | 70108 | G02895000-001 | FUEL INSTL, VENT, REAR FUSE | YES | YES | COS | G02895104-009-05 | 4 Solución en espera de ser aprobada |  | TBD | Q3924
Zone 3.2 | Methods | Q321006939-1 | EXTENSION | 2021-04-14 | AGX830 |  | 70109 | G02895000-001 | FUEL INSTL, VENT, REAR FUSE | YES | YES | COS | G02895104-009-06 | 4 Solución en espera de ser aprobada |  | TBD | Q3924
Zone 3.2 | Methods | Q321006940-1 | EXTENSION | 2021-04-14 | AGX830 |  | 70110 | G02895000-001 | FUEL INSTL, VENT, REAR FUSE | YES | YES | COS | G02895104-009-07 | 4 Solución en espera de ser aprobada |  | TBD | Q3924
Zone 3.2 | Methods | Q321006941-1 | EXTENSION | 2021-04-14 | AGX830 |  | 70111 | G02895000-001 | FUEL INSTL, VENT, REAR FUSE | YES | YES | COS | G02895104-009-08 | 4 Solución en espera de ser aprobada |  | TBD | Q3924
Zone 3.2 | Methods | Q321006942-1 | EXTENSION | 2021-04-14 | AGX830 |  | 70112 | G02895000-001 | FUEL INSTL, VENT, REAR FUSE | YES | YES | COS | G02895104-009-09 | 4 Solución en espera de ser aprobada |  | TBD | Q3924
Zone 3.2 | Methods | Q321006943-1 | EXTENSION | 2021-04-14 | AGX830 |  | 70113 | G02895000-001 | FUEL INSTL, VENT, REAR FUSE | YES | YES | COS | G02895104-009-10 | 4 Solución en espera de ser aprobada |  | TBD | Q3924
Zone 3.2 | Methods | Q321006944-1 | EXTENSION | 2021-04-14 | AGX830 |  | 70114 | G02895000-001 | FUEL INSTL, VENT, REAR FUSE | YES | YES | COS | G02895104-009-11 | 4 Solución en espera de ser aprobada |  | TBD | Q3924
Zone 3.2 | Methods | Q321006945-1 | EXTENSION | 2021-04-14 | AGX830 |  | 70115 | G02895000-001 | FUEL INSTL, VENT, REAR FUSE | YES | YES | COS | G02895104-009-12 | 4 Solución en espera de ser aprobada |  | TBD | Q3924
Zone 3.4 | Methods | Q321006946-1 | STANDARD | 2021-04-14 | AGX952 | AGX952 | 70103 | G05450073-002-01 | TE INSTL, PYLON | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.2 | Methods | Q321006963-1 | STANDARD | 2021-04-14 | AGX830 | AGX830 | 70100 | G05372719-101-01 | BRACKET, FUEL SYSTEM | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD | Should be workmanship, bracket mal posicionado
Zone 3.4 | Methods | Q321006965-1 | STANDARD | 2021-04-14 | AGX952 | AGX952 | 70102 | G05360001-003 | STRUCTURE ASSY REAR FUSELAGE | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Shooting PCPR
Zone 3.4 | Methods | Q321006966-1 | STANDARD | 2021-04-14 | AGX952 | AGX952 | 70102 | G05360001-003 | STRUCTURE ASSY REAR FUSELAGE | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Shooting PCPR
Zone 3.4 | Methods | Q321006966-2 | STANDARD | 2021-04-14 | AGX952 | AGX952 | 70102 | G05360001-003 | STRUCTURE ASSY REAR FUSELAGE | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Shooting PCPR
Zone 3.4 | Methods | Q321006966-3 | STANDARD | 2021-04-14 | AGX952 | AGX952 | 70102 | G05360001-003 | STRUCTURE ASSY REAR FUSELAGE | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Shooting PCPR
Zone 3.4 | Methods | Q321006966-4 | STANDARD | 2021-04-14 | AGX952 | AGX952 | 70102 | G05360001-003 | STRUCTURE ASSY REAR FUSELAGE | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Shooting PCPR
Zone 3.4 | Methods | Q321006966-5 | STANDARD | 2021-04-14 | AGX952 | AGX952 | 70102 | G05360001-003 | STRUCTURE ASSY REAR FUSELAGE | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Shooting PCPR
MTS | Methods | Q321006883-2 | STANDARD | 2021-04-14 | SGX900 | SGX900 |  | G05211418-101 | PLATE, HINGE STEP, PASS ACS DR | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Q 4320
Zone 2 | Methods | Q321006901-1 | STANDARD | 2021-04-14 | AGX880 | AGX880 | 70107 | G05530256-007-01 | RIB 9 ASSY, AFT, VSTAB | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 5 | Methods | Q321006952-2 | STANDARD | 2021-04-14 | AGX280 | AGX280 | 70108 | G05311301-101/01 | STRINGER 3, COCKPIT NOSE | NO | NO | N/A | N/A | 3 Causa Raiz detectada | N/A | TBD | There are 3 common parts with external parts came with same pilot holes that not make match, NCR raised since double hole condition. Query raised with investigation to avoid double hole condition.
Zone 5 | Methods | Q321006952-1 | STANDARD | 2021-04-14 | AGX280 | AGX280 | 70108 | G05311296-103-01 | INTERCOSTAL, FLOOR, AVIONIC BAY | NO | NO | N/A | N/A | 4 Solución en espera de ser aprobada | N/A | TBD | There are 3 common parts with external parts came with same pilot holes that not make match, NCR raised since double hole condition. Query raised with investigation to avoid double hole condition.
Zone 3.4 | Methods | Q321006966-8 | STANDARD | 2021-04-14 | AGX952 | AGX952 | 70102 | G00653060-003 | STRINGER EOP | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.3 | Methods | Q321006982-1 | STANDARD | 2021-04-15 | AGX950 | AGX950 | 70104 | G05363921-001 | JOINT INSTL, STA 1016, REAR FUSE | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.3 | Methods | Q321006982-2 | STANDARD | 2021-04-15 | AGX950 | AGX950 | 70104 | G05363921-001 | JOINT INSTL, STA 1016, REAR FUSE | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.4 | Methods | Q321006989-1 | STANDARD | 2021-04-15 | AGX952 | AGX950 | 70102 | G05530300-101 | FAIRING, DORSAL, V/STAB | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 1 | Methods | Q321007060-1 | STANDARD | 2021-04-15 | AGX744 | AGX744 | 70109 | G05372390-001 | ECS INSTL CPCS PROVISION REAR FUSE | YES | Yes | PCR | 61582 | 4 Solución en espera de ser aprobada |  | TBD | David Lencz da seguimiento al PCR
Zone 4 | Methods | Q321007081-1 | STANDARD | 2021-04-15 | AGX985 | AGX985 | 70099 | G05530150-001-90 | FAIRING INSTL, BULLET | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD
Zone 4 | Methods | Q321006968-1 | STANDARD | 2021-04-15 | AGX965 | AGX965 | 70100 | G02691253-003 | TUBE ASSY, FIDEX, ENG LH | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 4 | Methods | Q321006973-1 | STANDARD | 2021-04-15 | AGX985 | AGX985 | 70099 | G05530140-003 | PANEL INSTL, ACCESS PANEL, VSTAB | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
MTS | Methods | Q321007187-1 | STANDARD | 2021-04-16 | SGX949 | SGX949 |  | G05450432-001-05 | BRACKET ASSY, CTR BOX, PYLON | YES | YES | RFC | 3000165719 | 4 Solución en espera de ser aprobada |  | 70110 ?
Zone 3.1 | Methods | Q321007094-2 | STANDARD | 2021-04-16 | AGX810 | AGX810 | 70107 | G05363534-113 | FRAME, FRONT SPAR, REAR FUSE | NO | NO | N/A | N/A | 1 Problema detectado | STL PANEL ISSUES | TBD
Zone 3.1 | Methods | Q321007094-3 | STANDARD | 2021-04-16 | AGX810 | AGX810 | 70107 | G05366015-102. | FITTING, FWD ENGINE FRAME | NO | NO | N/A | N/A | 1 Problema detectado | STL PANEL ISSUES | TBD
Zone 3.3 | Methods | Q321007098-1 | STANDARD | 2021-04-16 | AGX950 | AGX950 | 70102 | G05363963-105 | FITTING, STRG 4, OUTBD | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.3 | Methods | Q321007098-2 | STANDARD | 2021-04-16 | AGX950 | AGX950 | 70102 | G05363963-106 | FITTING, STRG 4, OUTBD | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.3 | Methods | Q321007099-1 | STANDARD | 2021-04-16 | AGX950 | AGX950 | 70103 | G05530170-001 | FAIRING INSTL, DORSAL | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.4 | Methods | Q321007090-1 | STANDARD | 2021-04-16 | AGX945 | AGX945 | 70106 | G05450207-101-03 | STIFFENER, FIXED LE, PYLON | YES | YES | COS | G05450212-101-04 | 4 Solución en espera de ser aprobada |  | TBD | DDA 12219A
Zone 3.4 | Methods | Q321007101-4 | STANDARD | 2021-04-16 | AGX952 | AGX952 | 70104 | G05363449-102 | DOUBLER, SIDE PANEL, AFT BARREL | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.4 | Methods | Q321007101-5 | STANDARD | 2021-04-16 | AGX952 | AGX952 | 70104 | G05450503-104 | SKIN, LWR, CTR BOX, PYLON | YES | YES | COS | G05450062-010-03 | 4 Solución en espera de ser aprobada |  | TBD | Query 4470 Meth Config ECD = 30 APR
Zone 3.4 | Methods | Q321007101-6 | STANDARD | 2021-04-16 | AGX952 | AGX952 | 70104 | G05450502-104 | SKIN, UPPER, CTR BOX, PYLON | YES | YES | COS | G05450061-004-05 | 4 Solución en espera de ser aprobada |  | TBD | Query 4470 Meth Config ECD = 30 APR
Zone 3.4 | Methods | Q321007101-8 | STANDARD | 2021-04-16 | AGX952 | AGX952 | 70104 | G05450502-104 | SKIN, UPPER, CTR BOX, PYLON | YES | YES | COS | G05450061-004-04 | 4 Solución en espera de ser aprobada |  | 70105-X
Zone 3.4 | Methods | Q321007101-9 | STANDARD | 2021-04-16 | AGX952 | AGX952 | 70104 | G05450522-102-02 | ANGLE, CTR BOX, PYLON | YES | YES | COS | G05450426-103-03 | 4 Solución en espera de ser aprobada |  | 70105-X
Zone 3.4 | Methods | Q321007101-10 | STANDARD | 2021-04-16 | AGX952 | AGX952 | 70104 | G05450485-102-02 | ANGLE, CTR BOX, PYLON | YES | YES | COS | G05450485-102-03 | 4 Solución en espera de ser aprobada |  | TBD | Query 4503 Meth Config ECD = 7 May
Zone 3.4 | Methods | Q321007118-1 | STANDARD | 2021-04-16 | AGX952 | AGX952 | 70104 | G05450628-001 | FITTING, CTR BOX, PYLON | YES | YES | COS | G05450628-101-04 | 4 Solución en espera de ser aprobada |  | TBD | Query 4503 Meth Config ECD = 7 May
Zone 3.4 | Methods | Q321007118-2 | STANDARD | 2021-04-16 | AGX952 | AGX952 | 70104 | G05450606-101 | ANGLE, DRAG, CTR BOX, PYLON | YES | YES | COS | G05450606-101-04 | 4 Solución en espera de ser aprobada |  | 70108-X
Zone 4 | Methods | Q321007081-1 | STANDARD | 2021-04-16 | AGX985 | AGX985 | 70099 | G05530150-001-90 | FAIRING INSTL, BULLET | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 4 | Methods | Q321007092-1 | STANDARD | 2021-04-16 | AGX955 | AGX955 | 70101 | G09172051-019 | HARNESS, AFT FUSE, REAR RHS RBB | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Query 4447 26-JUN
Zone 4 | Methods | Q321007171-1 | STANDARD | 2021-04-16 | AGX985 | AGX952 | 70100 | GD425-1005-5 | FITTING, BULKHEAD, ENGINE FEED (LH) | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 5 | Methods | Q321007125-1 | STANDARD | 2021-04-16 | AGX290 | AGX290 | 70108 | G05310750-001-01 | COCKPIT NOSE ASSY | NO | NO | N/A | N/A | 1 Problema detectado | PSS WIP for analisys from disc 001 from Dimensional Capsule Nose | TBD
Zone 5 | Methods | Q321007125-2 | STANDARD | 2021-04-16 | AGX290 | AGX290 | 70108 | G05310750-001-01 | COCKPIT NOSE ASSY | NO | NO | N/A | N/A | 1 Problema detectado | PSS WIP for analisys from disc 002 from Dimensional Capsule Nose new Jig from Uplock fitting | TBD
Zone 5 | Methods | Q321007125-3 | STANDARD | 2021-04-16 | AGX290 | AGX290 | 70108 | G05310750-001-01 | COCKPIT NOSE ASSY | NO | NO | N/A | N/A | 1 Problema detectado | PSS WIP for analisys from disc 003 from Dimensional Capsule Nose some details parts seems to be out of tol contour analisys WIP. | TBD
Zone 3.4 | Methods | Q321007101-7 | STANDARD | 2021-04-16 | AGX952 | AGX952 | 70104 | G05450503-104 | SKIN , LWR, CTR BOX, PYLON | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 2 | Methods | Q321007198-1 | STANDARD | 2021-04-17 | AGX880 | AGX880 | 70107 | G05530119-003 | SKIN INSTL, VSTAB, LH | YES | Yes | RFC | 3000168585 | 4 Solución en espera de ser aprobada |  | TBD | QUERY 4126/ Waiting RFC 26 May
Zone 3.3 | Methods | Q321007199-1 | STANDARD | 2021-04-17 | AGX950 | AGX950 | 70105 | G05530213-106-01 | FITTING, INTERFACE, FRONT SPAR, VS | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.1 | Methods | Q321003490-7 | STANDARD | 2021-04-19 | AGX810 | AGX810 | 70101 | G05360055-003 | BULKHEAD INSTL,PRESSURE | NO | NO | N/A | N/A | 1 Problema detectado | PSS-034 | TBD
Zone 3.1 | Methods | Q321007208-1 | STANDARD | 2021-04-19 | AGX802 | AGX802 | 70108 | G05372102-003 | ECS INSTL TRIM AIR PROVISIONS | NO | YES | N/A | N/A | 1 Problema detectado | WAITING FINAL DISPOSITION FOR NCRS | TBD
Zone 4 | Methods | Q321007211-1 | SR | 2021-04-19 | AGX955 | AGX955 | 70101 | G05363514-101 | FRAME, AFT ENG MOUNT, REAR FUSE | YES | YES | RFC | 61756 | 4 Solución en espera de ser aprobada |  | 70110
Zone 3.3 | Methods | Q321007215-1 | STANDARD | 2021-04-19 | AGX950 | AGX950 | 70105 | G05363921-003 | JOINT INSTL, STA 1016, REAR FUSE | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Investigación en conjunto con Z2, falta PSS
Zone 3.3 | Methods | Q321007215-2 | STANDARD | 2021-04-19 | AGX950 | AGX950 | 70105 | G05530215-101 | ANGLE, FRONT SPAR, VSTAB | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Query ??
Zone 3.3 | Methods | Q321007215-3 | STANDARD | 2021-04-19 | AGX950 | AGX950 | 70105 | G05363921-003 | JOINT INSTL, STA 1016, REAR FUSE | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Investigación en conjunto con Z2, falta PSS
Zone 2 | Methods | Q321007218-1 | STANDARD | 2021-04-19 | AGX890 | AGX880 | 70106 | G05530119-003 | SKIN INSTL, VSTAB, LH | YES | Yes | RFC | 3000168585 | 4 Solución en espera de ser aprobada |  | TBD | QUERY 4126/ Waiting RFC 26 May
Zone 4 | Methods | Q321007219-1 | STANDARD | 2021-04-19 | AGX955 | AGX874 | 70101 | G02691203-005 | TUBE ASSY, FIDEX, APU | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Query 4354, modificar secuencia/uso JIG
Zone 3.2 | Methods | Q321007242-1 | STANDARD | 2021-04-19 | AGX830 | AGX830 | 70105 | G05372201-001 | ECS INSTL, LP PROVISIONS, ABOVE FLOOR | YES | YES | COS | CIN CSD-G05362500-003-0036 | 4 Solución en espera de ser aprobada |  | 70117-x | Query 3232
Zone 5 | Methods | Q321007250-1 | STANDARD | 2021-04-19 | AGX276 | AGX276 | 70109 | G05311192-101/01 | ANGLE, MLG, DOOR | YES | YES | RFC | 3000167102 | 4 Solución en espera de ser aprobada | WAITTING FOR IMPLEMENTATION | 70110 | RFC 3000167102 incorporation on AC 70110.
Zone 1 | Methods | Q321007254-1 | STANDARD | 2021-04-19 | AGX738 | AGX738 | 70102 | G05291600-001 | ELECTRICAL INSTL, CARGO ACCESS DR | NO | Yes | N/A | N/A | 1 Problema detectado |  | 25/06/2021 | Query # 4450 Method config Queue
Zone 3.4 | Methods | Q321007267-1 | STANDARD | 2021-04-19 | AGX952 | AGX952 | 70103 | G05370026-001-01 | FIDEX INSTL, PROVISIONS, REAR FUSE | YES | YES | COS | G05363284-101-01 | 4 Solución en espera de ser aprobada |  | TBD | Query 4145 DDA 11138 A
Zone 3.3 | Methods | Q321007268-1 | STANDARD | 2021-04-19 | AGX950 | AGX950 | 70105 | G05530314-002 | FAIRING ASSY, DORSAL, AFT | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Investigación / Mismatch packer LE Z2
Zone 2 | Methods | Q321007274-1 | STOCK PURGE | 2021-04-20 | AGX880 | AGX880 |  | G02996302-001 | TUBE ASSY, HYDR SYS 3 RTN, VS | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.4 | Methods | Q321007282-1 | STANDARD | 2021-04-20 | AGX952 | AGX952 | 70104 | G05450606-101-01 | ANGLE, DRAG, CTR BOX, PYLON | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | QUERIES 3116 & 2560
Zone 4 | Methods | Q321007302-1 | STANDARD | 2021-04-20 | AGX955 | AGX955 | 70102 | G09172051-019-01 | HARNESS, AFT FUSE, REAR RHS RBB | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Query 4451 Clamps*
Zone 3.3 | Methods | Q321007310-1 | STANDARD | 2021-04-20 | AGX950 | AGX950 | 70105 | G05363921-003 | JOINT INSTL, STA 1016, REAR FUSE | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | TBD | Q1473, esperando actualización dwg
Zone 3.3 | Methods | Q321007310-2 | STANDARD | 2021-04-20 | AGX950 | AGX950 | 70105 | G05363921-003 | JOINT INSTL, STA 1016, REAR FUSE | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | TBD | Q1473, esperando actualización dwg
Zone 3.3 | Methods | Q321007312-1 | STANDARD | 2021-04-20 | AGX950 | AGX950 | 70103 | G05363963-105 | FITTING, STRG 4, OUTBD | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Should be workmanship, secuencia barrenado
Zone 3.3 | Methods | Q321007312-2 | STANDARD | 2021-04-20 | AGX950 | AGX950 | 70103 | G05363963-106 | FITTING, STRG 4, OUTBD | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | Should be workmanship, secuencia barrenado
Zone 3.2 | Methods | Q321007319-1 | STANDARD | 2021-04-20 | AGX830 | AGX830 | 70106 | G05372201-001 | ECS INSTL, LP PROVISIONS, ABOVE FLOOR | YES | YES | COS | CIN CSD-G05362500-003-0036 | 4 Solución en espera de ser aprobada |  | 70117-x | Query 3232
Zone 3.3 | Methods | Q321007326-1 | STANDARD | 2021-04-20 | AGX950 | AGX950 | 70105 | G05363637-103 | STRAP, LOWER PANEL, AFT BARREL | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | PSS en conjunto con Z1
Zone 4 | Methods | Q321007335-1 | STANDARD | 2021-04-20 | AGX964 | AGX965 | 70101 | 627700-1002 | PTU - MOTOR/PUMP PACKAGE INTERFACE DEF | YES | YES | RFC | 3000166121 | 4 Solución en espera de ser aprobada |  | TBD
Zone 4 | Methods | Q321007341-1 | STANDARD | 2021-04-20 | AGX985 | AGX965 | 70100 | 627700-1002 | PTU - MOTOR/PUMP PACKAGE INTERFACE DEF | YES | YES | RFC | 3000166121 | 4 Solución en espera de ser aprobada |  | TBD
Zone 3.3 | Methods | Q321007301-1 | STANDARD | 2021-04-20 | AGX950 | AGX950 | 70105 | G05363602-109 | PANEL , LWR, BARREL, REAR | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.1 | Methods | Q421007364-1 | STANDARD | 2021-04-21 | AGX810 | METHOD | 70105 | NCRQ321005670-001-01 | FITTING, STGR 22 | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD | NO METHODS
Zone 3.1 | Methods | Q321007365-1 | STANDARD | 2021-04-21 | AGX806 | AGX806 | 70101 | G05360055-003 | BULKHEAD INSTL,PRESSURE,REAR FULEJAGE | NO | NO | N/A | N/A | 3 Causa Raiz detectada | pss-034 | TBD
Zone 3.1 | Methods | Q321007369-1 | STANDARD | 2021-04-21 | AGX808 | AGX808 | 70109 | G05362360-108 | FRAME, FS 981.45, AFT FUSE | NO | NO | N/A | N/A | 3 Causa Raiz detectada | SEQUENCE INSTALLATION CHANGED | TBD
Zone 5 | Methods | Q321007381-1 | STANDARD | 2021-04-21 | AGX274 | AGX274 | 70111 | G05311033-101/03 | STRIKER, AFT AVIONIC DOOR SEAL, LH | NO | NO | N/A | N/A | 3 Causa Raiz detectada |  | 70112 | Se mando fabricar nuevo Snap especial para squeezer de acuerdo a las medias del ensamble.
Zone 4 | Methods | Q321007395-1 | EXTENSION | 2021-04-21 | AGX955 |  | 70103 | G09172051-019-01 | HARNESS, AFT FUSE, REAR RHS RBB | NO | YES | N/A | N/A | 3 Causa Raiz detectada | Query 4451/4447 | TBD
Zone 4 | Methods | Q321007396-1 | EXTENSION | 2021-04-21 | AGX955 |  | 70104 | G09172051-019-01 | HARNESS, AFT FUSE, REAR RHS RBB | NO | YES | N/A | N/A | 3 Causa Raiz detectada | Query 4451/4447 | TBD
Zone 3.3 | Methods | Q321007398-1 | STANDARD | 2021-04-21 | AGX952 | AGX952 | 70104 | G05363449-101 | DOUBLER SIDE PANEL AFT BARREL | NO | YES | N/A | N/A | 1 Problema detectado |  | TBD | LOW ED
Zone 3.3 | Methods | Q321007416-1 | STANDARD | 2021-04-21 | AGX950 | AGX950 | 70104 | G05363963-105-02 | FITTING, STGR 4, OUTBD | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD | Mismatch holes
Zone 3.4 | Methods | Q321007481-1 | SR | 2021-04-21 | AGX952 | AGX952 | 70103 | G05450056-009-01 | TE ASSY, FIXED, PYLON | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD | TOOLCRIP SCRATCH AT TOOLING HOLE
Zone 4 | Methods | Q321007407-1 | STANDARD | 2021-04-21 | AGX965 | AGX965 |  | G02490961-103 | SUPPORT, PANEL SERVICE LIGHTS, AFT FUSE | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
MTS | Methods | Q321007408-1 | STANDARD | 2021-04-21 | SGX965 | SGX965 |  | G02490961-103 | SUPPORT, PANEL SERVICE LIGHTS, AFT FUSE | YES | YES | RFC | 61563 | 4 Solución en espera de ser aprobada |  | TBD
Zone 3.4 | Methods | Q321007389-2 | STANDARD | 2021-04-22 | AGX952 | AGX952 | 70104 | G05362370-106-01 | FRAME, FS999.00, AFT FUSE | YES | YES | COS | G05450606-102-06 | 4 Solución en espera de ser aprobada |  | TBD | Query 3968. dda 12219A
Zone 3.4 | Methods | Q321007492-1 | STANDARD | 2021-04-22 | AGX952 | AGX952 | 70104 | G05450614-101-02 | PLATE, AFT ENG FTG, CTR BOX | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD
Zone 4 | Methods | Q321007517-1 | STANDARD | 2021-04-22 | AGX955 | AGX874 | 70102 | G02691203-005 | TUBE ASSY, FIDEX, APU | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.2 | Methods | Q321007533-1 | STANDARD | 2021-04-22 | AGX830 | AGX830 | 70104 | G05364510-001 | CELL INSTL, FLEXIBLE, AFT FUEL TANK | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.4 | Methods | Q321007537-1 | STANDARD | 2021-04-22 | AGX946 | AGX946 | 70107 | G05450061-004-04 | SKIN ASSY, UPR, CTR BOX, PYLON | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD | No firmado por Arturo.
Zone 3.2 | Methods | Q321007541-1 | STANDARD | 2021-04-22 | AGX830 | AGX830 | 70104 | G05364500-001-01 | STRUCTURE ASSY, FUEL TANK, REAR FUSE | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.2 | Methods | Q321007551-1 | STANDARD | 2021-04-22 | AGX830 | AGX830 | 70105 | G05364670-102-01 | WEB, SHEAR, UPPER, FUEL TANK FLOOR | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.4 | Methods | Q321007552-1 | STANDARD | 2021-04-22 | AGX952 | AGX952 | 70103 | G05450073-002-01 | TE INSTL, PYLON | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD | Low ED due to deviation in WL / accumulation of tolerances
Zone 4 | Methods | Q321007553-1 | SR | 2021-04-22 | AGX955 | AGX955 | 70102 | G05363514-101 | FRAME, AFT ENG MOUNT, REAR FUSE | YES | YES | RFC | 61756 | 4 Solución en espera de ser aprobada |  | 70110
Zone 4 | Methods | Q321007559-1 | STANDARD | 2021-04-22 | AGX985 | AGX985 | 70100 | G05530140-003 | PANEL INSTL, ACCESS PANEL, VSTAB | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.1 | Methods | Q321007486-1 | STANDARD | 2021-04-22 | AGX810 | AGX810 | 70108 | G05361500-003 | PANEL ASSY, LOWER, AFT FUSE | NO | NO | N/A | N/A | 1 Problema detectado | STL PANEL ISSUES | TBD
Zone 3.1 | Methods | Q321007509-1 | STANDARD | 2021-04-22 | AGX806 | AGX806 | 70101 | G05365560-104-01 | ANGLE, SPLICE, UPR, AFT PRESS BHD | NO | NO | N/A | N/A | 3 Causa Raiz detectada | PSS-034 | TBD
Zone 3.1 | Methods | Q321007509-2 | STANDARD | 2021-04-22 | AGX806 | AGX806 | 70101 | G05365560-103-01 | ANGLE, SPLICE, UPR, AFT PRESS BHD | NO | NO | N/A | N/A | 3 Causa Raiz detectada | PSS-034 | TBD
Zone 3.1 | Methods | Q321007661-1 | STANDARD | 2021-04-23 | AGX810 | AGX810 | 70108 | G05360010-003 | BARREL ASSY, FWD, AFT FUSE | NO | NO | N/A | N/A | 3 Causa Raiz detectada | STL PANEL ISSUES | TBD
Zone 4 | Methods | Q321007582-1 | STANDARD | 2021-04-23 | AGX955 | AGX955 | 70102 | G09172051-019-01 | HARNESS, AFT FUSE, REAR RHS RBB | YES | YES | PCR | 60265 | 4 Solución en espera de ser aprobada |  | TBD | pcr stop due programa
Zone 3.3 | Methods | Q321007585-2 | STANDARD | 2021-04-23 | AGX950 | AGX950 | 70105 | G05363966-105-02 | FITTING, STGR 4, INBD | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.3 | Methods | Q321007585-1 | STANDARD | 2021-04-23 | AGX950 | AGX950 | 70105 | G05363966-106-02 | FITTING, STGR 4, INBD | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.1 | Methods | Q321007589-2 | STANDARD | 2021-04-23 | AGX810 | AGX810 | 70108 | G05360040-001 | FLOOR INSTL | NO | YES | N/A | N/A | 3 Causa Raiz detectada | PSS-034 | TBD
Zone 3.4 | Methods | Q321007606-1 | STANDARD | 2021-04-23 | AGX952 | AGX952 | 70103 | G05450057-N0014 | TE ASSY, REMOVABLE, PYLON | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 4 | Methods | Q321007656-1 | STANDARD | 2021-04-23 | AGX985 | AGX985 | 70100 | G05530150-001-90 | FAIRING INSTL, BULLET | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.1 | Methods | Q321007661-2 | STANDARD | 2021-04-23 | AGX810 | AGX810 | 70108 | G05366015-101 | FITTING, FWD ENGINE FRAME | NO | NO | N/A | N/A | 1 Problema detectado | STL PANEL ISSUES | TBD
Zone 5 | Methods | Q321007688-1 | STANDARD | 2021-04-26 | AGX290 | AGX290 | 70109 | G05310750-001-01 | COCKPIT NOSE ASSY | NO | NO | N/A | N/A | 2 Análisis en Proceso | PSS WIP for analisys from disc 001 from Dimensional Capsule Nose | TBD
Zone 5 | Methods | Q321007688-4 | STANDARD | 2021-04-26 | AGX290 | AGX290 | 70109 | G05310750-001-01 | COCKPIT NOSE ASSY | NO | NO | N/A | N/A | 2 Análisis en Proceso | PSS WIP for analisys from disc 001 from Dimensional Capsule Nose | TBD
Zone 5 | Methods | Q321007688-3 | STANDARD | 2021-04-26 | AGX290 | AGX290 | 70109 | G05310750-001-01 | COCKPIT NOSE ASSY | NO | NO | N/A | N/A | 2 Análisis en Proceso | PSS WIP for analisys from disc 001 from Dimensional Capsule Nose | TBD
Zone 5 | Methods | Q321007688-2 | STANDARD | 2021-04-26 | AGX290 | AGX290 | 70109 | G05310750-001-01 | COCKPIT NOSE ASSY | NO | NO | N/A | N/A | 2 Análisis en Proceso | PSS WIP for analisys from disc 001 from Dimensional Capsule Nose | TBD
Zone 1 | Methods | Q321007690-1 | STANDARD | 2021-04-26 | AGX738 | AGX738 | 70103 | G05291600-001 | ELECTRICAL INSTL, CARGO ACCESS DR | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | 25/06/2021 | Query # 4450 Method config Queue
Zone 3.4 | Methods | Q321007712-9 | STANDARD | 2021-04-26 | AGX952 | AGX952 | 70103 | G00653060-003 | STRINGER EOP | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD
Zone 3.4 | Methods | Q321007712-3 | STANDARD | 2021-04-26 | AGX952 | AGX952 | 70103 | G00653060-003 | SKIN EOP | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD
Zone 3.4 | Methods | Q321007712-2 | STANDARD | 2021-04-26 | AGX952 | AGX952 | 70103 | G00653060-003 | BUTT STRAP OML | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD
Zone 3.4 | Methods | Q321007712-1 | STANDARD | 2021-04-26 | AGX952 | AGX952 | 70103 | G00653060-003 | FLOOR BEAM EOP/WL/BL | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD
Zone 3.4 | Methods | Q321007712-4 | STANDARD | 2021-04-26 | AGX952 | AGX952 | 70103 | G00606104-001 | SYM POINTS | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD
Zone 3.4 | Methods | Q321007712-5 | STANDARD | 2021-04-26 | AGX952 | AGX952 | 70103 | G00606104-001 | HSTAB PIVOT FITTINGS | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD
Zone 3.4 | Methods | Q321007725-1 | STANDARD | 2021-04-26 | AGX952 | AGX952 | 70103 | G05360001-003 | STRINGER RADIAL | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.4 | Methods | Q321007738-1 | STANDARD | 2021-04-26 | AGX945 | AGX945 | 70107 | G05450500-103-03 | SKIN, FIXED LE, PYLON | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 4 | Methods | Q321007740-1 | STANDARD | 2021-04-26 | AGX975 | AGX955 | 70101 | GD425-1005-5 | FITTING, BULKHEAD, ENGINE FEED (LH) | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
MTS | Methods | Q321007741-1 | STANDARD | 2021-04-26 | SGX900 | SGX900 |  | G05211418-101 | PLATE, HINGE STEP, PASS ACS DR | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | TBD | Q 4320
MTS | Methods | Q321007749-1 | STANDARD | 2021-04-26 | SGX949 | SGX949 |  | G05450432-001-05 | BRACKET ASSY, CTR BOX, PYLON | YES | YES | RFC | 3000165719 | 4 Solución en espera de ser aprobada |  | 70110 ?
MTS | Methods | Q321007753-1 | STANDARD | 2021-04-26 | SGX948 | SGX948 |  | G05450432-002-04 | BRACKET ASSY, CTR BOX, PYLON | YES | YES | RFC | 3000165719 | 4 Solución en espera de ser aprobada |  | 70110 ?
Zone 4 | Methods | Q321007756-1 | STANDARD | 2021-04-26 | AGX964 | AGX965 | 70102 | 627700-1002 | PTU - MOTOR/PUMP PACKAGE INTERFACE DEF | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.2 | Methods | Q321007763-1 | STANDARD | 2021-04-26 | AGX830 | AGX830 | 70107 | G05372201-001 | ECS INSTL, LP PROVISIONS, ABOVE FLOOR | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.3 | Methods | Q321007773-1 | STANDARD | 2021-04-26 | AGX950 | AGX950 | 70104 | G05363963-105 | FITTING, STRG 4, OUTBD | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.3 | Methods | Q321007773-2 | STANDARD | 2021-04-26 | AGX950 | AGX950 | 70104 | G05363921-003 | JOINT INSTL, STA 1016, REAR FUSE | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.4 | Methods | Q321007776-1 | STANDARD | 2021-04-26 | AGX952 | AGX952 | 70105 | G05450379-101-02 | FITTING, TENSION, FIXED LE, PYLON | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.3 | Methods | Q321007814-1 | STANDARD | 2021-04-27 | AGX950 | AGX950 | 70104 | G05530170-001 | FAIRING INSTL, DORSAL | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.3 | Methods | Q321007829-2 | STANDARD | 2021-04-27 | AGX950 | AGX950 | 70106 | G05363921-003 | JOINT INSTL, STA 1016, REAR FUSE | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.3 | Methods | Q321007829-3 | STANDARD | 2021-04-27 | AGX950 | AGX950 | 70106 | G05530215-101 | ANGLE, FRONT SPAR, VSTAB | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.3 | Methods | Q321007829-1 | STANDARD | 2021-04-27 | AGX950 | AGX950 | 70106 | G05363921-003 | JOINT INSTL, STA 1016, REAR FUSE | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.3 | Methods | Q321007829-4 | STANDARD | 2021-04-27 | AGX950 | AGX950 | 70106 | G05530213-106 | FITTING, INTERFACE, FRONT SPAR, VS | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 2 | Methods | Q321007830-1 | STANDARD | 2021-04-27 | AGX880 | AGX880 | 70107 | B0305102-004 | FAIRLEAD, TWO HOLES | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD
Zone 2 | Methods | Q321007832-1 | STANDARD | 2021-04-27 | AGX874 | AGX874 | 70108 | G05372103-003-01 | FITTING ASSY, BLEED AIR, REAR FUSE | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD
Zone 3.4 | Methods | Q321007848-1 | STANDARD | 2021-04-27 | AGX952 | AGX952 | 70105 | G05450379-101-02 | FITTING, TENSION, FIXED LE, PYLON | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.3 | Methods | Q321007857-1 | STANDARD | 2021-04-27 | AGX950 | AGX950 | 70106 | G05394000-001 | TAILCONE, FWD | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.4 | Methods | Q321007910-8 | STANDARD | 2021-04-28 | AGX952 | AGX952 | 70105 | G05450503-104 | SKIN, LWR, CTR BOX, PYLON | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.4 | Methods | Q321007910-6 | STANDARD | 2021-04-28 | AGX952 | AGX952 | 70105 | G05450484-102 | FITTING, CTR BOX, PYLON | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.4 | Methods | Q321007910-7 | STANDARD | 2021-04-28 | AGX952 | AGX952 | 70105 | G05450680-102 | FITTING, CTR BOX, PYLON | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.3 | Methods | Q321007913-1 | STANDARD | 2021-04-28 | AGX950 | AGX950 | 70105 | G05397266-101 | FITTING, HOIST BEAM, REAR FUSE TAILCONE | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.4 | Methods | Q321007927-5 | STANDARD | 2021-04-28 | AGX952 | AGX952 | 70104 | G00606104-001 | HSTAB PIVOT FITTINGS | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD
Zone 3.4 | Methods | Q321007927-2 | STANDARD | 2021-04-28 | AGX952 | AGX952 | 70104 | G00653060-003 | BUTT STRAP OML | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD
Zone 3.4 | Methods | Q321007927-3 | STANDARD | 2021-04-28 | AGX952 | AGX952 | 70104 | G00653060-003 | SKIN EOP | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD
Zone 3.4 | Methods | Q321007927-1 | STANDARD | 2021-04-28 | AGX952 | AGX952 | 70104 | G00653060-003 | FLOOR BEAM EOP/WL/BL | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD
Zone 3.4 | Methods | Q321007927-4 | STANDARD | 2021-04-28 | AGX952 | AGX952 | 70104 | G00606104-001 | SYM POINTS | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD
Zone 3.4 | Methods | Q321007940-1 | STANDARD | 2021-04-28 | AGX952 | AGX952 | 70104 | G05450057-N0014 | TE ASSY, REMOVABLE, PYLON | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
MTS | Methods | Q321007945-1 | STANDARD | 2021-04-28 | SGX949 | SGX949 |  | G05450432-001-05 | BRACKET ASSY, CTR BOX, PYLON | YES | YES | RFC | 3000165719 | 4 Solución en espera de ser aprobada |  | 70110 ?
Zone 3.1 | Methods | Q321007947-1 | STANDARD | 2021-04-28 | AGX802 | AGX802 | 70109 | G05372102-003 | ECS INSTL TRIM AIR PROVISIONS | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | 2021-08-27
Zone 2 | Methods | Q321007948-1 | STANDARD | 2021-04-28 | AGX872 | AGX872 | 70109 | G05363430-109-01 | SKIN, SIDE PANEL, AFT BARREL, LH | YES | Yes | RFC | 3000168585 | 4 Solución en espera de ser aprobada |  | TBD | QUERY 4126/ Waiting RFC 26 May
Zone 3.2 | Methods | Q321007953-1 | STANDARD | 2021-04-28 | AGX820 | AGX820 | 70109 | G05364500-001-01 | STRUCTURE ASSY, FUEL TANK, REAR FUSE | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.3 | Methods | Q321007956-1 | STANDARD | 2021-04-28 | AGX950 | AGX950 | 70104 | G05363926-101 | INTERCOSTAL, MOORING, FTG, AFT BARREL | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 2 | Methods | Q321007961-1 | STANDARD | 2021-04-28 | AGX890 | AGX890 | 70108 | G05530214-105-02 | ANGLE, DRAG, VSTAB | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD
Zone 3.4 | Methods | Q321007981-1 | STANDARD | 2021-04-29 | AGX952 | AGX810 | 70105 | G05366015-102 | FITTING, FWD ENGINE FRAME | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.4 | Methods | Q321007982-1 | STANDARD | 2021-04-29 | AGX952 | AGX952 | 70104 | G05450052-006 | LE ASSY, REMOVABLE, PYLON | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.1 | Methods | Q321007985-1 | STANDARD | 2021-04-29 | AGX810 | AGX810 | 70106 | G05370907-001 | FITTING ASSY, WASTE SYSTEM | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | TBD
Zone 3.1 | Methods | Q321007985-2 | STANDARD | 2021-04-29 | AGX810 | AGX810 | 70106 | G05370907-001 | FITTING ASSY, WASTE SYSTEM | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | TBD
Zone 3.1 | Methods | Q321008004-1 | STANDARD | 2021-04-29 | AGX810 | AGX810 | 70108 | G05362013-101-09 | SPLICE, ORBITAL JOINT, AFT FUSE | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | TBD
Zone 4 | Methods | Q321008005-1 | STANDARD | 2021-04-29 | AGX955 | AGX226 | 70103 | G05390000-001 | TAILCONE, GA | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 4 | Methods | Q321008008-1 | STANDARD | 2021-04-29 | AGX955 | AGX955 | 70103 | G09172051-019-01 | HARNESS, AFT FUSE, REAR RHS RBB | YES | YES | PCR | 60265 | 4 Solución en espera de ser aprobada |  | TBD
Zone 2 | Methods | Q321008051-1 | STANDARD | 2021-04-30 | AGX890 | AGX880 | 70108 | G05530119-003 | SKIN INSTL, VSTAB, LH | YES | Yes | RFC | 3000168585 | 4 Solución en espera de ser aprobada |  | TBD | QUERY 4126/ Waiting RFC 26 May
Zone 3.1 | Methods | Q321008072-1 | STANDARD | 2021-04-30 | AGX810 | AGX810 | 70109 | G05365628-101 | FITTING, STGR 9 EXT, AFT FUSE | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | 2021-06-11
Zone 1 | Methods | Q321008076-1 | STANDARD | 2021-04-30 | AGX744 | AGX744 | 70110 | G05372390-001 | ECS INSTL CPCS PROVISION REAR FUSE | YES | Yes | PCR | 61582 | 4 Solución en espera de ser aprobada |  | TBD | David Lencz da seguimiento al PCR
Zone 3.2 | Methods | Q321008092-1 | STANDARD | 2021-04-30 | AGX818 | AGX818 | 70111 | G05364667-103-01 | PAN, WATER DRAIN | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 2 | Methods | Q321008097-1 | STANDARD | 2021-04-30 | AGX872 | AGX872 | 70110 | G05363100-003 | BARREL ASSY, REAR FUSELAGE | YES | Yes | COS | G05363136-009-01 | 4 Solución en espera de ser aprobada |  | 70120

## Sheet1
UNDEFINED
RFC 3000163508
RFC 3000165719
RFC 3000165719
RFC 3000165719
RFC 61563
RFC 3000163508
UNDEFINED
UNDEFINED
RFC 3000163508
UNDEFINED
RFC 3000163508
UNDEFINED
RFC 3000165719
RFC 61563
RFC 61563
UNDEFINED
UNDEFINED
RFC PCR 61582
RFC PCR 61582
UNDEFINED
RFC PCR 61582
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
RFC PCR 61582
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
COS G05363136-009-01
UNDEFINED
COS G05363136-009-01
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED no
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED N/A
UNDEFINED
UNDEFINED -
UNDEFINED -
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
COS 4470
UNDEFINED
COS 4470
COS 2560
UNDEFINED
COS 2560
COS 4402
COS 2756
COS 2560
COS 2560
COS 2560
COS 2560
COS 4183
COS 3274
COS 3274
COS 3274
COS 3274
COS 3274
COS
UNDEFINED
UNDEFINED
COS 2560
COS 4470
COS 4470
UNDEFINED
UNDEFINED
COS 4470
COS 2560
COS 2560
COS 4145
COS 2560
COS 2756
COS 4203
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
COS 4183
COS FAI snag
COS 2560 4470
COS 4470
COS 2560
COS 4503
COS 2560
COS 4470
UNDEFINED
COS 2560
COS 4183
UNDEFINED
COS 4503
UNDEFINED
COS 4183
COS 2756
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
COS 3116
UNDEFINED
UNDEFINED
RFC 61498
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
RFC 61498
UNDEFINED
UNDEFINED
UNDEFINED
RFC 61498
RFC 61498
RFC 61498
RFC 61498
RFC 61498
RFC 61498
RFC 61498
RFC 61498
RFC 61498
RFC 61498
RFC 61498
RFC 61498
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
RFC 3000166121
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
RFC 3000166121
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
RFC 3000167102
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
COS 2560
UNDEFINED
COS 3274
CN 2329335
CN 2329335
CN 2329335
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
CN 2329335
CN 2329335
CN 2329335
CN 2329335
UNDEFINED
UNDEFINED
RFC 3000165719
UNDEFINED
UNDEFINED
COS 4470
RFC 3000163508
COS 4470
UNDEFINED
UNDEFINED
UNDEFINED
COS 4470
UNDEFINED
COS 3274
COS 3274
UNDEFINED
COS 3274
UNDEFINED
UNDEFINED
COS 3274
COS 3274
UNDEFINED
UNDEFINED
RFC 3000167102
UNDEFINED 3274
UNDEFINED 3274
UNDEFINED 3274
UNDEFINED 3274
UNDEFINED 3274
UNDEFINED 3274
UNDEFINED 3274
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
RFC 3000167678
UNDEFINED
RFC 3000165719
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
RFC PCR 61582
UNDEFINED 4183
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
RFC 3000165719
UNDEFINED
UNDEFINED
UNDEFINED
RFC 61563
UNDEFINED
UNDEFINED
UNDEFINED
RFC 3000165719
RFC 3000165719
RFC
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED

## Today
ZONE | BADGE | NCR # | NCR Type | Disc. Create Date | Work Centre | Norm. Line Position | Tail # | Part # | Part Desc | Action | RFC/Query | ECD or A/C | Comments
3.3 |  | Q321005663-1 | STANDARD | 2021-03-23 | AGX950 | AGX950 | 70102 | G05363921-003 | JOINT INSTL, STA 1016, REAR FUSE | N/A | N/A | N/A | N/A
3.3 |  | Q321005707-1 | STANDARD | 2021-03-23 | AGX950 | AGX950 | 70102 | G02100001-001 | DUCT, RAM AIR | YES | CIN | 70106-70116 | OMIT INSTALL IN 1001 PLANT
4 |  | Q321005676-1 | STANDARD | 2021-03-23 | AGX985A | AGX975AA | 70097 | G02197162-012-01 | INLET ASSY, MECH, PRECOOLER, PYLON
MTS |  | Q321005654-1 | STANDARD | 2021-03-23 | SGX965A | SGX965A |  | G02490961-103 | SUPPORT, PANEL SERVICE LIGHTS, AFT FUSE
MTS |  | Q321005710-1 | STANDARD | 2021-03-23 | SGX900A | SGX900A |  | G05211418-101 | PLATE, HINGE STEP, PASS ACS DR

## Today Chart
2021-05-20
Row Labels | Count of RFC/Query
MTS
(blank)
ZONE 2 | 3
r | 3
ZONE 3.1
(blank)
ZONE 3.2
(blank)
ZONE 3.4 | 7
g | 3
v | 4
(blank)
ZONE 3.4B | 1
v | 1
ZONE 4
(blank)
ZONE 5 | 3
v | 3
(blank)
(blank)
(blank)
Grand Total | 14

## Full chart
Disc. Create Date | (All)
Row Labels | Count of RFC/Query | Count of NCR #
0 |  | 10
2 |  | 1
3 |  | 16
3.1 |  | 2
3.4 | 5 | 25
4 |  | 2
1502 |  | 1
4
AGX226AA |  | 1
AGX277 |  | 1
AGX290 |  | 5
AGX710 |  | 1
AGX740 |  | 1
AGX740AA |  | 1
AGX742AA |  | 2
AGX744 |  | 3
AGX744AA |  | 1
AGX760AA |  | 2
AGX770 |  | 1
AGX770AA |  | 1
AGX784 |  | 3
AGX802 |  | 1
AGX802AA |  | 1
AGX806 |  | 1
AGX806AA |  | 2
AGX807 |  | 1
AGX810 |  | 6
AGX810AA |  | 18
AGX818 |  | 1
AGX830 |  | 1
AGX830AA |  | 14
AGX872AA |  | 2
AGX874AA |  | 1
AGX879 |  | 1
AGX880AA |  | 8
AGX882AA |  | 3
AGX888AA |  | 1
AGX890AA |  | 2
AGX942AA |  | 1
AGX944 |  | 1
AGX944AA |  | 1
AGX945 |  | 1
AGX946 |  | 1
AGX949 |  | 1
AGX950AA |  | 27
AGX952 |  | 4
AGX952AA |  | 96
AGX955AA |  | 15
AGX964AA |  | 4
AGX965AA |  | 2
AGX985AA |  | 9
AGX999AA |  | 4
C1 |  | 1
EXTENSION |  | 10
Fase 5 |  | 3
MTS |  | 6
SNC |  | 3
STANDARD |  | 17
ZONE 1 |  | 12
ZONE 2 | 6 | 10
ZONE 3 | 52 | 121
Zone 3.1 |  | 9
Zone 3.2 | 1 | 2
Zone 3.3 |  | 5
Zone 3.4 | 14 | 23
ZONE 4 | 2 | 60
ZONE 5 |  | 8
(blank)
Grand Total | 80 | 605