## Old Data
ZONE | BADGE | NCR # | NCR Type | Disc. Create Date | Work Centre | Norm. Line Position | Tail # | Part # | Part Desc | Action | ¿Repetitivo? | COS | Number | Phase | PSS # | ECD_or_AC | Comments
Zone 3.1 | METHODS | Q321008162-1 | STANDARD | 2021-05-03 | AGX810AA | AGX810AA | 70106 | G05362013-101-09 | SPLICE, ORBITAL JOINT, AFT FUSE | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Orbital splice, CAB ITEM; new COs is not working for RHS
Zone 1 | METHODS | Q321008166-1 | STANDARD | 2021-05-03 | AGX738 | AGX738 | 70104 | G05291600-001 | ELECTRICAL INSTL, CARGO ACCESS DR | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | TBD | Query 4450 solicitando RFC EDC: 25 Junio para levantar RFC
Zone 3.1 | METHODS | Q321008203-2 | STANDARD | 2021-05-03 | AGX810AA | AGX810AA | 70109 | G05360040-001 | FLOOR INSTL | NO | YES | N/A | N/A | 3 Causa Raiz detectada | 34 | TBD | Gaps localización piso/PSS 034
Zone 4 | METHODS | Q321008204-1 | STANDARD | 2021-05-03 | AGX985AA | AGX985AA | 70101 | G05530140-003 | PANEL INSTL, ACCESS PANEL, VSTAB | YES | YES | RFC | 3000168061 | 4 Solución en espera de ser aprobada |  | 70125-X | Query 4421 / CSK Deep VSTAB / 70107-x paneles sin CSK
Zone 5 | METHODS | Q321008207-3 | STANDARD | 2021-05-03 | AGX290 | AGX290 | 70110 | G05310750-001-01 | COCKPIT NOSE ASSY | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | KCCP CN 70110
Zone 5 | METHODS | Q321008207-4 | STANDARD | 2021-05-03 | AGX290 | AGX290 | 70110 | G05310750-001-01 | COCKPIT NOSE ASSY | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | KCCP CN 70110
Zone 5 | METHODS | Q321008207-1 | STANDARD | 2021-05-03 | AGX290 | AGX290 | 70110 | G05310750-001-01 | COCKPIT NOSE ASSY | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | KCCP CN 70110
Zone 5 | METHODS | Q321008207-2 | STANDARD | 2021-05-03 | AGX290 | AGX290 | 70110 | G05310750-001-01 | COCKPIT NOSE ASSY | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | KCCP CN 70110
Zone 1 | METHODS | Q321008260-1 | SNC | 2021-05-04 | AGX975A | AGX738A | 70102 | G05291000-001 | DOOR ASSY, CARGO ACCESS DR | YES | YES | CN | 2603390 | 5 Monitoreo y mejora |  | 2091-12-10 | Undertorque CARGO
Zone 2 | METHODS | Q321008267-1 | STANDARD | 2021-05-04 | AGX955AA | AGX879AA | 70103 | G05530112-105-01 | HINGE 2, REAR SPAR, VSTAB | YES | YES | RFC | 3000168703 | 4 Solución en espera de ser aprobada | N/A | 70115-X | OMISSION OF TOPCOAT ON QUERY 3917
Zone 3.1 | METHODS | Q321008273-1 | STANDARD | 2021-05-04 | AGX985 | AGX802AA | 70101 | G05373026-101-01 | BRACKET, GROUND | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | 2021-08-27
Zone 1 | METHODS | Q321008277-1 | SNC | 2021-05-04 | AGX985A | AGX738A | 70101 | G05291000-001 | DOOR ASSY, CARGO ACCESS DR | YES | YES | CN | 2603390 | 5 Monitoreo y mejora |  | 2091-12-10 | Undertorque CARGO
Zone 3.4 | METHODS | Q321008278-1 | STANDARD | 2021-05-04 | AGX952 | AGX952 | 70106 | G05450053-018-01 | BOX ASSY, CENTER, PYLON | YES | YES | COS | G05450061-004-05 | 4 Solución en espera de ser aprobada |  | 2021-05-28 | No COS creado. No effy. Query 4470 reemplaza 3500
Zone 1 | METHODS | Q321008279-1 | SNC | 2021-05-04 | AGX955A | AGX738A | 70103 | G05291000-001 | DOOR ASSY, CARGO ACCESS DR | YES | YES | CN | 2603390 | 5 Monitoreo y mejora |  | 2091-12-10 | Undertorque CARGO
Zone 2 | METHODS | Q321008281-1 | EXTENSION | 2021-05-04 | AGX952AA | AGX879AA | 70104 | G05530112-105-01 | HINGE 2, REAR SPAR, VSTAB | YES | YES | RFC | 3000168703 | 4 Solución en espera de ser aprobada | N/A | 70115-X | OMISSION OF TOPCOAT ON QUERY 3917
Zone 2 | METHODS | Q321008282-1 | EXTENSION | 2021-05-04 | AGX952AA | AGX879AA | 70105 | G05530112-105-01 | HINGE 2, REAR SPAR, VSTAB | YES | YES | RFC | 3000168703 | 4 Solución en espera de ser aprobada | N/A | 70115-X | OMISSION OF TOPCOAT ON QUERY 3917
Zone 2 | METHODS | Q321008283-1 | EXTENSION | 2021-05-04 | AGX952AA | AGX879AA | 70106 | G05530112-105-01 | HINGE 2, REAR SPAR, VSTAB | YES | YES | RFC | 3000168703 | 4 Solución en espera de ser aprobada | N/A | 70115-X | OMISSION OF TOPCOAT ON QUERY 3917
Zone 2 | METHODS | Q321008285-1 | EXTENSION | 2021-05-04 | AGX890AA | AGX879AA | 70108 | G05530112-105-01 | HINGE 2, REAR SPAR, VSTAB | YES | YES | RFC | 3000168703 | 4 Solución en espera de ser aprobada | N/A | 70115-X | OMISSION OF TOPCOAT ON QUERY 3917
Zone 3.4 | METHODS | Q321008296-1 | STANDARD | 2021-05-04 | AGX952 | AGX952 | 70106 | G05450606-102 | ANGLE, DRAG, CTR BOX, PYLON | YES | YES | COS | G05450606-102-06 | 4 Solución en espera de ser aprobada |  | 70122-X | Query 3968. DDA 12219
Zone 3.4 | METHODS | Q321008296-2 | STANDARD | 2021-05-04 | AGX952 | AGX952 | 70106 | G05450605-102 | ANGLE, DRAG, CTR BOX, PYLON | YES | YES | COS | G05450605-102-05 | 4 Solución en espera de ser aprobada |  | 70109-X | Query 2560
Zone 4 | METHODS | Q321008299-1 | STANDARD | 2021-05-04 | AGX985A | AGX985AA | 70101 | G05530150-001-90 | FAIRING INSTL, BULLET | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | TBD | Bullet Fairing csk deep, RFC en aprobación con ENG
Zone 4 | METHODS | Q321008306-1 | SR | 2021-05-04 | AGX955AA | AGX955AA | 70103 | G05363514-101 | FRAME, AFT ENG MOUNT, REAR FUSE | YES | YES | RFC | 61756 | 4 Solución en espera de ser aprobada |  | TBD | Low clearance ENG Mount y arnés
Zone 3.4 | METHODS | Q321008348-1 | STANDARD | 2021-05-05 12:17 | AGX952 | AGX952 | 70105 | G05450605-102 | ANGLE, DRAG, CTR BOX, PYLON | YES | YES | COS | G05450605-102-05 | 4 Solución en espera de ser aprobada |  | 70109-X | Query 2560
Zone 3.4 | METHODS | Q321008362-1 | STANDARD | 2021-05-05 13:48 | AGX952 | AGX952 | 70105 | G05450606-101-02 | ANGLE, DRAG, CTR BOX, PYLON | YES | YES | COS | G05450606-101- | 4 Solución en espera de ser aprobada |  | 70108-X
Zone 1 | METHODS | Q321008366-1 | STANDARD | 2021-05-05 14:02 | AGX744AA | AGX744AA | 70111 | G05372390-001 | ECS INSTL CPCS PROVISION REAR FUSE | YES | YES | PCR | 61582 | 4 Solución en espera de ser aprobada |  | TBD | David Lencz da seguimiento al PCR
Zone 3.4 | METHODS | Q321008367-1 | STANDARD | 2021-05-05 14:10 | AGX952 | AGX952 | 70105 | G05450472-103 | CLIP, CTR BOX, PYLON | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Low ED Doubler G05363449-101. Posible RFC pendiente
Zone 4 | METHODS | Q321008388-1 | STANDARD | 2021-05-05 16:32 | AGX955AA | AGX955AA | 70104 | G09171051-019 | HARNESS, AFT FUSE, REAR LHS RAB | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | TBD | Conector angularidad EWIS
Zone 4 | METHODS | Q321008389-1 | STANDARD | 2021-05-05 16:45 | AGX955AA | AGX955AA | 70104 | G09171051-019 | HARNESS, AFT FUSE, REAR LHS RAB | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | TBD | Cambio tamaño clamps EWIS ECD 26 Jun
Zone 4 | METHODS | Q321008390-1 | STANDARD | 2021-05-05 16:53 | AGX955AA | AGX955AA | 70104 | G09172051-019 | HARNESS, AFT FUSE, REAR RHS RBB | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | TBD | Cambio tamaño clamps EWIS
Zone 4 | METHODS | Q321008391-1 | STANDARD | 2021-05-05 17:16 | AGX955AA | AGX955AA | 70104 | G09172051-019 | HARNESS, AFT FUSE, REAR RHS RBB | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | TBD | Cambio tamaño clamps EWIS
Zone 3.3 | METHODS | Q321008393-1 | STANDARD | 2021-05-05 18:03 | AGX950AA | AGX950AA | 70107 | G05394060-105 | SKIN, LATERAL, RH | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | FOLLOW UP PSS / Barrenos cercanos joggle TAILCONE
Zone 4 | METHODS | Q321008395-1 | STANDARD | 2021-05-05 18:35 | AGX955AA | AGX955AA | 70104 | G09172051-019-01 | HARNESS, AFT FUSE, REAR RHS RBB | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | PCR 60265 esperando aprobacion / Clocking conector
Zone 3.4 | METHODS | Q321008398-1 | STANDARD | 2021-05-05 21:01 | AGX952 | AGX952 | 70105 | G05450490-102 | ANGLE, CTR BOX, PYLON | YES | YES | COS | G05450490-102-03 | 4 Solución en espera de ser aprobada |  | 2021-05-28 | Query 4472
Zone 2 | METHODS | Q321008409-1 | STANDARD | 2021-05-05 22:50 | AGX880 | AGX880AA | 70109 | G05530119-003 | SKIN INSTL, VSTAB, LH | YES | YES | RFC | 3000169938 | 4 Solución en espera de ser aprobada |  | 70123-70125 | QUERY: 4218
Zone 1 | METHODS | Q321008410-1 | STANDARD | 2021-05-06 06:43 | AGX720AA | AGX720AA | 70111 | G05363134-005 | PANEL ASSY LWR BARREL REAR FUSE | YES | YES | CN | 2498025 | 5 Monitoreo y mejora | LEAD ZONE 3 | 2091-12-19 | Acciones terminadas e implementadas Contenido con Visual help y soporte en lo que se incorporo el cambio
Zone 2 | METHODS | Q321008419-1 | STANDARD | 2021-05-06 07:41 | AGX882AA | AGX882AA | 70109 | G02490920-005 | HARNESS INSTLL, VS | YES | YES | RFC | 61470 | 4 Solución en espera de ser aprobada |  | 2091-12-13
Zone 3.4 | DESIGN | Q321008423-4 | STANDARD | 2021-05-06 22:46 | AGX952A | AGX952B | 70105 | G09172001-017-01 | HARNESS, AFT FUSE, BAGGAGE RHS RBA | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 4 | METHODS | Q321008457-1 | STANDARD | 2021-05-06 09:28 | AGX964A | AGX965A | 70103 | 627700-1002 | PTU - MOTOR/PUMP PACKAGE INTERFACE DEF | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD
Zone 2 | METHODS | Q321008461-1 | STANDARD | 2021-05-06 10:18 | AGX890AA | AGX890AA | 70108 | G05363100-003 | BARREL ASSY, REAR FUSELAGE | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD | GAP STRAP UPPER PANEL
Zone 3.3 | METHODS | Q321008468-1 | STANDARD | 2021-05-06 11:20 | AGX950AA | AGX950AA | 70107 | G05363921-003 | JOINT INSTL, STA 1016, REAR FUSE | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | BY JOINING (SHIM CRUCI)
Zone 3.3 | METHODS | Q321008468-2 | STANDARD | 2021-05-06 11:46 | AGX950AA | AGX950AA | 70107 | G05530215-101-03 | ANGLE, FRONT SPAR, VSTAB | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | BY JOINING (SHIM CRUCI)
Zone 4 | METHODS | Q321008477-1 | EXTENSION | 2021-05-06 12:55 | AGX955AA |  | 70105 | G09171051-019 | HARNESS, AFT FUSE, REAR LHS RAB | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | TBD | disposition use as is.. find out
Zone 4 | METHODS | Q321008478-1 | EXTENSION | 2021-05-06 12:55 | AGX955AA |  | 70106 | G09171051-019 | HARNESS, AFT FUSE, REAR LHS RAB | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | TBD | disposition use as is.. find out
Zone 4 | METHODS | Q321008479-1 | EXTENSION | 2021-05-06 12:55 | AGX955AA |  | 70107 | G09171051-019 | HARNESS, AFT FUSE, REAR LHS RAB | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | TBD | disposition use as is.. find out
Zone 4 | METHODS | Q321008480-1 | EXTENSION | 2021-05-06 12:55 | AGX955AA |  | 70108 | G09171051-019 | HARNESS, AFT FUSE, REAR LHS RAB | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | TBD | disposition use as is.. find out
Zone 4 | METHODS | Q321008481-1 | EXTENSION | 2021-05-06 12:55 | AGX955AA |  | 70109 | G09171051-019 | HARNESS, AFT FUSE, REAR LHS RAB | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | TBD | disposition use as is.. find out
Zone 4 | METHODS | Q321008482-1 | EXTENSION | 2021-05-06 12:57 | AGX955AA |  | 70105 | G09172051-019 | HARNESS, AFT FUSE, REAR RHS RBB | YES | YES | RFC | PCR 60265 | 4 Solución en espera de ser aprobada |  | TBD | Query #4534 / 10 - Jun
Zone 4 | METHODS | Q321008483-1 | EXTENSION | 2021-05-06 12:57 | AGX955AA |  | 70106 | G09172051-019 | HARNESS, AFT FUSE, REAR RHS RBB | YES | YES | RFC | PCR 60265 | 4 Solución en espera de ser aprobada |  | TBD | Query #4534 / 10 - Jun
Zone 4 | METHODS | Q321008484-1 | EXTENSION | 2021-05-06 12:57 | AGX955AA |  | 70107 | G09172051-019 | HARNESS, AFT FUSE, REAR RHS RBB | YES | YES | RFC | PCR 60265 | 4 Solución en espera de ser aprobada |  | TBD | Query #4534 / 10 - Jun
Zone 4 | METHODS | Q321008485-1 | EXTENSION | 2021-05-06 12:57 | AGX955AA |  | 70108 | G09172051-019 | HARNESS, AFT FUSE, REAR RHS RBB | YES | YES | RFC | PCR 60265 | 4 Solución en espera de ser aprobada |  | TBD | Query #4534 / 10 - Jun
Zone 4 | METHODS | Q321008486-1 | EXTENSION | 2021-05-06 12:57 | AGX955AA |  | 70109 | G09172051-019 | HARNESS, AFT FUSE, REAR RHS RBB | YES | YES | RFC | PCR 60265 | 4 Solución en espera de ser aprobada |  | TBD | Query #4534 / 10 - Jun
Zone 4 | METHODS | Q321008487-1 | EXTENSION | 2021-05-06 12:58 | AGX955AA |  | 70105 | G09172051-019 | HARNESS, AFT FUSE, REAR RHS RBB | YES | YES | RFC | PCR 60265 | 4 Solución en espera de ser aprobada |  | TBD | Query #4451 / 10 - Jun
Zone 4 | METHODS | Q321008488-1 | EXTENSION | 2021-05-06 12:58 | AGX955AA |  | 70106 | G09172051-019 | HARNESS, AFT FUSE, REAR RHS RBB | YES | YES | RFC | PCR 60265 | 4 Solución en espera de ser aprobada |  | TBD | Query #4451 / 10 - Jun
Zone 4 | METHODS | Q321008489-1 | EXTENSION | 2021-05-06 12:58 | AGX955AA |  | 70107 | G09172051-019 | HARNESS, AFT FUSE, REAR RHS RBB | YES | YES | RFC | PCR 60265 | 4 Solución en espera de ser aprobada |  | TBD | Query #4451 / 10 - Jun
Zone 4 | METHODS | Q321008490-1 | EXTENSION | 2021-05-06 12:58 | AGX955AA |  | 70108 | G09172051-019 | HARNESS, AFT FUSE, REAR RHS RBB | YES | YES | RFC | PCR 60265 | 4 Solución en espera de ser aprobada |  | TBD | Query #4451 / 10 - Jun
Zone 4 | METHODS | Q321008491-1 | EXTENSION | 2021-05-06 12:58 | AGX955AA |  | 70109 | G09172051-019 | HARNESS, AFT FUSE, REAR RHS RBB | YES | YES | RFC | PCR 60265 | 4 Solución en espera de ser aprobada |  | TBD | Query #4451 / 10 - Jun
Zone 4 | METHODS | Q321008492-1 | EXTENSION | 2021-05-06 12:59 | AGX955AA |  | 70105 | G09171051-019 | HARNESS, AFT FUSE, REAR LHS RAB | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | TBD | QUERY #3942
Zone 4 | METHODS | Q321008493-1 | EXTENSION | 2021-05-06 12:59 | AGX955AA |  | 70106 | G09171051-019 | HARNESS, AFT FUSE, REAR LHS RAB | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | TBD | QUERY #3942
Zone 4 | METHODS | Q321008494-1 | EXTENSION | 2021-05-06 12:59 | AGX955AA |  | 70107 | G09171051-019 | HARNESS, AFT FUSE, REAR LHS RAB | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | TBD | QUERY #3942
Zone 4 | METHODS | Q321008495-1 | EXTENSION | 2021-05-06 12:59 | AGX955AA |  | 70108 | G09171051-019 | HARNESS, AFT FUSE, REAR LHS RAB | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | TBD | QUERY #3942
Zone 4 | METHODS | Q321008496-1 | EXTENSION | 2021-05-06 12:59 | AGX955AA |  | 70109 | G09171051-019 | HARNESS, AFT FUSE, REAR LHS RAB | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | TBD | QUERY #3942
Zone 4 | METHODS | Q321008497-1 | EXTENSION | 2021-05-06 13:01 | AGX955AA |  | 70105 | G09172051-019-01 | HARNESS, AFT FUSE, REAR RHS RBB | YES | YES | RFC | PCR 60265 | 4 Solución en espera de ser aprobada | N/A | TBD
Zone 4 | METHODS | Q321008498-1 | EXTENSION | 2021-05-06 13:01 | AGX955AA |  | 70106 | G09172051-019-01 | HARNESS, AFT FUSE, REAR RHS RBB | YES | YES | RFC | PCR 60265 | 4 Solución en espera de ser aprobada | N/A | TBD
Zone 4 | METHODS | Q321008499-1 | EXTENSION | 2021-05-06 13:01 | AGX955AA |  | 70107 | G09172051-019-01 | HARNESS, AFT FUSE, REAR RHS RBB | YES | YES | RFC | PCR 60265 | 4 Solución en espera de ser aprobada | N/A | TBD
Zone 4 | METHODS | Q321008500-1 | EXTENSION | 2021-05-06 13:01 | AGX955AA |  | 70108 | G09172051-019-01 | HARNESS, AFT FUSE, REAR RHS RBB | YES | YES | RFC | PCR 60265 | 4 Solución en espera de ser aprobada | N/A | TBD
Zone 4 | METHODS | Q321008501-1 | EXTENSION | 2021-05-06 13:01 | AGX955AA |  | 70109 | G09172051-019-01 | HARNESS, AFT FUSE, REAR RHS RBB | YES | YES | RFC | PCR 60265 | 4 Solución en espera de ser aprobada | N/A | TBD
Zone 4 | METHODS | Q321008513-1 | STANDARD | 2021-05-06 15:25 | AGX955 | AGX226AA | 70104 | G05390000-001 | TAILCONE, GA | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.4 | METHODS | Q321008517-1 | STANDARD | 2021-05-06 17:45 | AGX952AA | AGX952B | 70105 | G00653060-003 | FLOOR BEAM EOP/WL/BL | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | SHOOTING REAR FUSE 70105
Zone 3.4 | METHODS | Q321008517-2 | STANDARD | 2021-05-06 17:45 | AGX952AA | AGX952B | 70105 | G00653060-003 | BUTT STRAP OML | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | SHOOTING REAR FUSE 70105
Zone 3.4 | METHODS | Q321008517-3 | STANDARD | 2021-05-06 17:45 | AGX952AA | AGX952B | 70105 | G00653060-003 | SKIN EOP | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | SHOOTING REAR FUSE 70105
Zone 3.4 | METHODS | Q321008517-4 | STANDARD | 2021-05-06 17:45 | AGX952AA | AGX952B | 70105 | G00606104-001 | SYM POINTS | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | SHOOTING REAR FUSE 70105
Zone 3.4 | METHODS | Q321008517-5 | STANDARD | 2021-05-06 17:45 | AGX952AA | AGX952B | 70105 | G00606104-001 | HSTAB PIVOT FITTINGS | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | SHOOTING REAR FUSE 70105
Zone 3.4 | METHODS | Q321008517-6 | STANDARD | 2021-05-06 17:45 | AGX952AA | AGX952B | 70105 | G00653060-003 | STRAP EOP | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | SHOOTING REAR FUSE 70105
Zone 3.4 | METHODS | Q321008517-7 | STANDARD | 2021-05-06 17:45 | AGX952AA | AGX952B | 70105 | G00653060-003 | KEEL BEAM | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | SHOOTING REAR FUSE 70105
Zone 3.4 | METHODS | Q321008517-8 | STANDARD | 2021-05-06 17:45 | AGX952AA | AGX952B | 70105 | G00654510-001 | ENGINE MOUNTS | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | SHOOTING REAR FUSE 70105
Zone 3.4 | METHODS | Q321008521-1 | STANDARD | 2021-05-06 18:32 | AGX952AA | AGX952B | 70105 | G05360001-003 | STRINGER RADIAL | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | SHOOTING REAR FUSE 70105
Zone 3.4 | METHODS | Q321008534-3 | STANDARD | 2021-05-07 07:54 | AGX952AA | AGX952B | 70105 | G05450054-008 | PANEL ASSY, CTR BOX, PYLON | YES | YES | COS | G05450504-106-02 | 4 Solución en espera de ser aprobada |  | 70113-X | CSK deep pylons
Zone 3.4 | METHODS | Q321008534-2 | STANDARD | 2021-05-07 07:54 | AGX952AA | AGX952B | 70105 | G05450058-008 | PANEL ASSY, CTR BOX, PYLON | YES | YES | COS | G05450510-106-02 | 4 Solución en espera de ser aprobada |  | 70109-X | CSK deep pylons
Zone 3.4 | METHODS | Q321008534-4 | STANDARD | 2021-05-07 07:54 | AGX952AA | AGX952B | 70105 | G05450055-008 | PANEL ASSY, CTR BOX, PYLON | YES | YES | COS | G05450505-106-02 | 4 Solución en espera de ser aprobada |  | 70111-X | CSK deep pylons
Zone 3.4 | METHODS | Q321008539-1 | STANDARD | 2021-05-07 08:13 | AGX952AA | AGX952B | 70105 | G05450057-N0014 | TE ASSY, REMOVABLE, PYLON | YES | YES | COS | G05450508-108-02 & G05450509-108-03 | 4 Solución en espera de ser aprobada |  | 70113-X & 70130-X | CSK deep pylons
Zone 3.4 | METHODS | Q321008540-1 | STANDARD | 2021-05-07 08:18 | AGX952AA | AGX952B | 70105 | G05450052-006 | LE ASSY, REMOVABLE, PYLON | YES | YES | COS | G05450501-106-02 | 4 Solución en espera de ser aprobada |  | 70130-X | CSK deep pylons
Zone 3.1 | METHODS | Q321008553-1 | STANDARD | 2021-05-07 09:40 | AGX802 | AGX802 | 70110 | G05372102-003 | ECS INSTL TRIM AIR PROVISIONS | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | TBD | Bonding test/QUERY 4688
Zone 3.4 | METHODS | Q321008563-1 | STANDARD | 2021-05-07 10:14 | AGX952 | AGX952 | 70106 | G05450490-101-02 | ANGLE, CTR BOX, PYLON | YES | YES | COS | G05450490-101-03 | 4 Solución en espera de ser aprobada |  | 2021-05-28 | Query 4472
Zone 4 | METHODS | Q321008566-1 | SR | 2021-05-07 10:42 | AGX955AA | AGX955AA | 70104 | G05363514-101 | FRAME, AFT ENG MOUNT, REAR FUSE | YES | YES | RFC | 61756 | 4 Solución en espera de ser aprobada |  | TBD | Standoff corto, fouling arnés vs estructura
Zone 3.4 | METHODS | Q321008569-1 | STANDARD | 2021-05-07 11:00 | AGX952AA | AGX952AA | 70106 | G05450606-101-01 | ANGLE, DRAG, CTR BOX, PYLON | YES | YES | COS | G05450606-101-04 | 4 Solución en espera de ser aprobada |  | 70108-X | Query 2560
Zone 3.3 | METHODS | Q321008582-1 | STANDARD | 2021-05-07 12:59 | AGX950 | AGX950 | 70106 | G05363921-003 | JOINT INSTL, STA 1016. REAR FUSE | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Stringers misalignment lower panel / Modif JIG AGX810 + RFC shim
Zone 3.4 | METHODS | Q321008585-1 | STANDARD | 2021-05-07 13:13 | AGX952 | AGX952 | 70105 | G05450605-102 | ANGLE, DRAG, CTR BOX, PYLON | YES | YES | COS | G05450605-102-05 | 4 Solución en espera de ser aprobada |  | 70109-X | Query 2560
Zone 3.3 | METHODS | Q321008586-1 | STANDARD | 2021-05-07 13:25 | AGX950 | AGX950 | 70105 | G05530170-001 | FAIRING INSTL, DORSAL | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.1 | METHODS | Q321008597-1 | STANDARD | 2021-05-07 14:46 | AGX810AA | AGX810AA | 70110 | G05362074-104-01 | FITTING, STGR EXTENSION, AFT FUSE | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD
Zone 3.2 | METHODS | Q321008608-1 | STANDARD | 2021-05-07 18:23 | AGX830AA | AGX830AA | 70109 | G05372202-001-02 | ECS INSTL, LP PROVISIONS, BELOW FLOOR | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD | Under investigation
Zone 3.3 | METHODS | Q321008624-1 | STANDARD | 2021-05-08 09:13 | AGX950 | AGX950 | 70107 | G05363921-003 | JOINT INSTL, STA 1016. REAR FUSE | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Stringers misalignment lower panel / Modif JIG AGX810 + RFC shim
Zone 3.3 | METHODS | Q321008624-2 | STANDARD | 2021-05-08 09:20 | AGX950 | AGX950 | 70107 | G05363921-003 | JOINT INSTL, STA 1016. REAR FUSE | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Stringers misalignment lower panel / Modif JIG AGX810 + RFC shim
Zone 2 | METHODS | Q321008637-1 | STANDARD | 2021-05-10 | AGX880AA | AGX880 |  | B0305102-004 | FAIRLEAD, TWO HOLES | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD
Zone 1 | METHODS | Q321008657-1 | STANDARD | 2021-05-10 | AGX770AA | AGX770 |  | G05363133-003 | PANEL ASSY, SIDE LH, BARREL, REAR FUSE | YES | YES | CN | 2498025 | 5 Monitoreo y mejora | LEAD ZONE 3 | 2091-12-19 | Acciones terminadas e implementadas Contenido con Visual help y soporte en lo que se incorporo el cambio
Zone 3.2 | METHODS | Q321008659-1 | STANDARD | 2021-05-10 | AGX820AA | AGX820 |  | G05364510-001 | CELL INSTL, FLEXIBLE, AFT FUEL TANK | YES | YES | RFC | 3000167934 | 4 Solución en espera de ser aprobada |  | 2091-12-18 | Velcro pads process modification
Zone 3.2 | METHODS | Q321008661-1 | STANDARD | 2021-05-10 | AGX820AA | AGX820 |  | G05364510-001 | CELL INSTL, FLEXIBLE, AFT FUEL TANK | YES | YES | RFC | 3000167934 | 4 Solución en espera de ser aprobada |  | 2091-12-18 | Velcro pads process modification
Zone 3.2 | METHODS | Q321008681-1 | STANDARD | 2021-05-10 | AGX830AA | AGX830 |  | G05364510-001 | CELL INSTL, FLEXIBLE, AFT FUEL TANK | YES | YES | RFC | 3000167934 | 4 Solución en espera de ser aprobada |  | 2091-12-18 | Fouling condition btw bladder y safety cable
Zone 5 | METHODS | Q321008705-1 | STANDARD | 2021-05-10 | AGX280 | AGX280 |  | G05310782-104 | FITTING, RADOME BULKHEAD JOINING, FR1 | NO | NO | N/A | N/A | 2 Análisis en Proceso | NO | TBD | NOT REPETITIVE ISSUE UNDER INVESTIGATION ONE OFF
Zone 3.1 | METHODS | Q321008708-1 | STANDARD | 2021-05-10 | AGX810AA | AGX810 |  | G05364116-003 | PANEL ASSY, SHEAR, FLOOR | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD
Zone 3.1 | METHODS | Q321008721-1 | STANDARD | 2021-05-11 | AGX810AA | AGX810 |  | G053709000-001 | WASTE INSTL, PROVISIONS, REAR FUSE | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | 2091-12-17 | Modification already made; no issue on AC 70114
Zone 3.1 | METHODS | Q321008726-1 | EXTENSION | 2021-05-11 | AGX810AA |  | 70109 | G05362013-101-09 | SPLICE, ORBITAL JOINT, AFT FUSE | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Orbital splice, CAB ITEM; new COs is not working for RHS
Zone 3.1 | METHODS | Q321008727-1 | EXTENSION | 2021-05-11 | AGX810AA |  | 70110 | G05362013-101-09 | SPLICE, ORBITAL JOINT, AFT FUSE | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Orbital splice, CAB ITEM; new COs is not working for RHS
Zone 3.1 | METHODS | Q321008728-1 | EXTENSION | 2021-05-11 | AGX810AA |  | 70111 | G05362013-101-09 | SPLICE, ORBITAL JOINT, AFT FUSE | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Orbital splice, CAB ITEM; new COs is not working for RHS
Zone 3.1 | METHODS | Q321008729-1 | EXTENSION | 2021-05-11 | AGX810AA |  | 70112 | G05362013-101-09 | SPLICE, ORBITAL JOINT, AFT FUSE | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Orbital splice, CAB ITEM; new COs is not working for RHS
Zone 3.1 | METHODS | Q321008730-1 | EXTENSION | 2021-05-11 | AGX810AA |  | 70113 | G05362013-101-09 | SPLICE, ORBITAL JOINT, AFT FUSE | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Orbital splice, CAB ITEM; new COs is not working for RHS
Zone 3.1 | METHODS | Q321008731-1 | EXTENSION | 2021-05-11 | AGX810AA |  | 70114 | G05362013-101-09 | SPLICE, ORBITAL JOINT, AFT FUSE | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Orbital splice, CAB ITEM; new COs is not working for RHS
Zone 3.1 | METHODS | Q321008732-1 | EXTENSION | 2021-05-11 | AGX810AA |  | 70115 | G05362013-101-09 | SPLICE, ORBITAL JOINT, AFT FUSE | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Orbital splice, CAB ITEM; new COs is not working for RHS
Zone 3.1 | METHODS | Q321008733-1 | EXTENSION | 2021-05-11 | AGX810AA |  | 70116 | G05362013-101-09 | SPLICE, ORBITAL JOINT, AFT FUSE | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Orbital splice, CAB ITEM; new COs is not working for RHS
Zone 3.1 | METHODS | Q321008734-1 | EXTENSION | 2021-05-11 | AGX810AA |  | 70117 | G05362013-101-09 | SPLICE, ORBITAL JOINT, AFT FUSE | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Orbital splice, CAB ITEM; new COs is not working for RHS
Zone 3.1 | METHODS | Q321008735-1 | EXTENSION | 2021-05-11 | AGX810AA |  | 70118 | G05362013-101-09 | SPLICE, ORBITAL JOINT, AFT FUSE | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Orbital splice, CAB ITEM; new COs is not working for RHS
Zone 3.1 | METHODS | Q321008736-1 | EXTENSION | 2021-05-11 | AGX810AA |  | 70119 | G05362013-101-09 | SPLICE, ORBITAL JOINT, AFT FUSE | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Orbital splice, CAB ITEM; new COs is not working for RHS
Zone 3.1 | METHODS | Q321008737-1 | EXTENSION | 2021-05-11 | AGX810AA |  | 70120 | G05362013-101-09 | SPLICE, ORBITAL JOINT, AFT FUSE | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Orbital splice, CAB ITEM; new COs is not working for RHS
Zone 3.4 | METHODS | Q321008744-1 | STANDARD | 2021-05-11 | AGX952 | AGX952 | 70107 | G05363449-102 | DOUBLER, SIDE PANEL, AFT BARREL | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Possible RFC
Zone 3.4 | METHODS | Q321008744-4 | STANDARD | 2021-05-11 | AGX952 | AGX952 | 70107 | G05450428-104 | RIB, CTR BOX, PYLON | YES | YES | COS | G05450485-102-03 | 4 Solución en espera de ser aprobada |  | 2021-05-28 | Query 4503
Zone 1 | METHODS | Q321008752-1 | STOCK PURGE | 2021-05-11 | AGX908AA | AGX908AA |  | B0803008-69-12 | BACKSHELL, STRAIGHT, SELF-LKG | YES | YES | CN | 2686419 | 5 Monitoreo y mejora |  | 2091-12-12 | Demanda de P/N erroneo sb eliminado, ya se envia desde electrico
Zone 3.2 | METHODS | Q321008755-1 | STANDARD | 2021-05-11 | AGX950AA | AGX952 | 70106 | G02100001-001 | DUCT, RAM AIR | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD | CAB ITEM GX
Zone 3.1 | METHODS | Q321008763-1 | STANDARD | 2021-05-11 | AGX810 | AGX810AA | 70110 | G05366015-101 | FITTING, FWD ENGINE FRAME | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Under investigation; this issue can be made because of issue with paneles or because of discrepant on measures taken
Zone 3.1 | METHODS | Q321008763-3 | STANDARD | 2021-05-11 | AGX810 | AGX810AA | 70110 | G05366015-102 | FITTING, FWD ENGINE FRAME | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD | Under investigation; this issue can be made because of issue with paneles or because of discrepant on measures taken
Zone 3.4 | METHODS | Q321008772-1 | STANDARD | 2021-05-11 | AGX944 | AGX944 | 70110 | G05450500-104-03 | SKIN, FIXED LE, PYLON | NO | NO | N/A | N/A | 3 Causa Raiz detectada |  | TBD | DOBLE HOYO GENERADO POR WORKAROUND. MALA INSTRUCCION DE METODOS. LA PIEL ESTABA MAL, PERO SE DIO LA INSTRUCCION DE CONTINUAR.
Zone 3.2 | METHODS | Q321008778-1 | STANDARD | 2021-05-11 | AGX830AA | AGX830AA | 70107 | G05364500-001-01 | STRUCTURE ASSY, FUEL TANK, REAR FUSE | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Gaps gussets tanque
Zone 3.4 | METHODS | Q321008800-1 | STANDARD | 2021-05-11 | AGX952 | AGX952 | 70107 | G05450606-101 | ANGLE, DRAG, CTR BOX, PYLON | YES | YES | COS | G05450606-101-05 | 4 Solución en espera de ser aprobada |  | 70128-X | Query 3116
Zone 4 | METHODS | Q321008801-1 | STANDARD | 2021-05-11 | AGX985AA | AGX985AA | 70102 | G05530140-003 | PANEL INSTL, ACCESS PANEL, VSTAB | YES | YES | RFC | 3000168061 | 4 Solución en espera de ser aprobada | Query #4421 | 70125-X | Flushness paneles VSTAB
Zone 3.1 | METHODS | Q321008400-2 | STANDARD | 2021-05-12 | AGX810AA | AGX810AA | 70110 | G05360040-001 | FLOOR INSTL | NO | NO | N/A | N/A | 3 Causa Raiz detectada | 34 | TBD | Gaps localización piso/PSS 034
Zone 3.4 | METHODS | Q321008744-6 | STANDARD | 2021-05-12 | AGX952 | AGX952 | 70107 | G05450503-104 | SKIN, LWR, CTR BOX, PYLON | YES | YES | COS | G05450062-009-03 | 4 Solución en espera de ser aprobada |  | 2021-05-28 | Query 4470. Reemplazo de 3500
Zone 3.3 | METHODS | Q321008813-1 | STANDARD | 2021-05-12 | AGX950 | AGX950 | 70108 | G05363921-003 | JOINT INSTL, STA 1016, REAR FUSE | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD | Elongated hole longeron under investigation first time
Zone 3.4 | METHODS | Q321008815-1 | STANDARD | 2021-05-12 | AGX952AA | AGX952AA | 70106 | G05360001-003 | STRINGER RADIAL | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | KCCP 70106
Zone 3.4 | METHODS | Q321008816-4 | STANDARD | 2021-05-12 | AGX952AA | AGX952AA | 70106 | G00606104-001 | SYM POINTS | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | KCCP 70106
Zone 3.4 | METHODS | Q321008816-8 | STANDARD | 2021-05-12 | AGX952AA | AGX952AA | 70106 | G00654510-001 | ENGINE MOUNTS | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | KCCP 70106
Zone 3.4 | METHODS | Q321008816-1 | STANDARD | 2021-05-12 | AGX952AA | AGX952AA | 70106 | G00653060-003 | FLOOR BEAM EOP/WL/BL | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | KCCP 70106
Zone 3.4 | METHODS | Q321008816-3 | STANDARD | 2021-05-12 | AGX952AA | AGX952AA | 70106 | G00653060-003 | SKIN EOP | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | KCCP 70106
Zone 3.4 | METHODS | Q321008816-2 | STANDARD | 2021-05-12 | AGX952AA | AGX952AA | 70106 | G00653060-003 | BUTT STRAP OML | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | KCCP 70106
Zone 3.4 | METHODS | Q321008816-5 | STANDARD | 2021-05-12 | AGX952AA | AGX952AA | 70106 | G00606104-001 | HSTAB PIVOT FITTINGS | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | KCCP 70106
Zone 3.4 | METHODS | Q321008816-7 | STANDARD | 2021-05-12 | AGX952AA | AGX952AA | 70106 | G00653060-003 | KEEL BEAM | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | KCCP 70106
Zone 3.3 | METHODS | Q321008820-2 | STANDARD | 2021-05-12 | AGX950AA | AGX950AA | 70106 | G05363926-102 | INTERCOSTAL, MOORING, FTG AFT BARREL | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Gap mooring fitting
Zone 3.3 | METHODS | Q321008820-1 | STANDARD | 2021-05-12 | AGX950AA | AGX950AA | 70106 | G05362220-104 | STR 20 AFT, FUSE | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD | Double hole stringer 20 under inv. firts time
Zone 5 | METHODS | Q321008821-1 | STANDARD | 2021-05-12 | AGX964A | AGX964A | 70104 | B0302167E16 | UNION, FLARELESS | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | 2091-12-09 | Tool mark tubes
Zone 3.4 | METHODS | Q321008827-1 | STANDARD | 2021-05-12 | AGX952 | AGX952 | 70107 | G05450484-101-02 | FITTING, CTR BOX, PYLON | YES | YES | COS | G05450061-003-05 | 4 Solución en espera de ser aprobada |  | 2021-05-28 | Query 4470. Reemplazo de 3500
Zone 3.4 | METHODS | Q321008830-1 | STANDARD | 2021-05-12 | AGX952 | AGX952 | 70107 | G05450489-102 | ANGLE, CTR BOX, PYLON | YES | YES | COS | G05450490-102-03 | 4 Solución en espera de ser aprobada |  | 2021-05-28 | Query 4472. Reemplazo de 3500
Zone 3.2 | DESIGN | Q321008835-1 | STANDARD | 2021-05-12 | AGX820AA | AGX820AA | 70108 | G05364510-001 | CELL INSTL, FLEXIBLE, AFT FUEL TANK | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | 70118-X | Adhesivo velcros
Zone 3.2 | METHODS | Q321008839-1 | STANDARD | 2021-05-12 | AGX830AA | AGX830AA | 70109 | G05372201-001 | ECS INSTL, LP PROVISIONS, ABOVE FLOOR | YES | YES | COS | CIN CSD-G05362500-003-0036 | 4 Solución en espera de ser aprobada |  | 70117-x | Mismatch bracket LP
Zone 3.4 | METHODS | Q321008845-1 | STANDARD | 2021-05-12 | AGX952AA | AGX952AA | 70106 | G05450606-101-03 | ANGLE, DRAG, CTR BOX, PYLON | YES | YES | COS | G05450606-101-05 | 4 Solución en espera de ser aprobada |  | 70128-X | Query 3116
Zone 1 | METHODS | Q321008846-1 | STANDARD | 2021-05-12 | AGX738 | AGX738 | 70105 | G05291600-001 | ELECTRICAL INSTL, CARGO ACCESS DR | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Query 4450 solicitando RFC EDC: 25 Junio para levantar RFC
Zone 3.4 | METHODS | Q321008851-1 | STANDARD | 2021-05-12 | AGX952 | AGX952 | 70107 | G05363449-101 | DOUBLER SIDE PANEL AFT BARREL | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Possible RFC
Zone 5 | METHODS | Q321008853-4 | STANDARD | 2021-05-12 | AGX290 | AGX290 | 70111 | G05310750-001-01 | COCKPIT NOSE ASSY | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | PSS ON GOING NEW LOTE WILL BE VALIDATE FOR AC 70116 FOR OML CHECK FROM SUPPLIER
Zone 5 | METHODS | Q321008853-2 | STANDARD | 2021-05-12 | AGX290 | AGX290 | 70111 | G05310750-001-01 | COCKPIT NOSE ASSY | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | PSS WIP for analisys from disc 002 from Dimensional Capsule Nose new Jig from Uplock fitting
Zone 5 | METHODS | Q321008853-1 | STANDARD | 2021-05-12 | AGX290 | AGX290 | 70111 | G05310750-001-01 | COCKPIT NOSE ASSY | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | PSS WIP for analisys from disc 001 from Dimensional Capsule Nose
Zone 5 | METHODS | Q321008853-3 | STANDARD | 2021-05-12 | AGX290 | AGX290 | 70111 | G05310750-001-01 | COCKPIT NOSE ASSY | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | PSS WIP for analisys from disc 003 from Dimensional Capsule Nose some details parts seems to be out of tol contour analisys WIP.
Zone 4 | METHODS | Q321008854-1 | STANDARD | 2021-05-12 | AGX964AA | AGX964AA | 70104 | 627700-1002 | PTU - MOTOR/PUMP PACKAGE INTERFACE DEF | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD
Zone 2 | METHODS | Q321008865-1 | STANDARD | 2021-05-12 | AGX870AA | AGX890AA | 70109 | G05363136-007-01 | FRAME ASSY, AFT ENG MOUNT | YES | YES | COS | G05363136-007-01 | 4 Solución en espera de ser aprobada |  | 2091-12-23
Zone 3.4 | METHODS | Q321008868-1 | STANDARD | 2021-05-12 | AGX952AA | AGX952AA | 70106 | G05363449-101 | DOUBLER SIDE PANEL AFT BARREL | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Possible RFC
Zone 2 | METHODS | Q321008881-1 | EXTENSION | 2021-05-12 | AGX870AA |  | 70110 | G05363136-007-01 | FRAME ASSY, AFT ENG MOUNT | YES | YES | COS | G05363136-007-01 | 4 Solución en espera de ser aprobada |  | 2091-12-23
Zone 2 | METHODS | Q321008882-1 | EXTENSION | 2021-05-12 | AGX870AA |  | 70111 | G05363136-007-01 | FRAME ASSY, AFT ENG MOUNT | YES | YES | COS | G05363136-007-01 | 4 Solución en espera de ser aprobada |  | 2091-12-23
Zone 2 | METHODS | Q321008883-1 | EXTENSION | 2021-05-12 | AGX870AA |  | 70112 | G05363136-007-01 | FRAME ASSY, AFT ENG MOUNT | YES | YES | COS | G05363136-007-01 | 4 Solución en espera de ser aprobada |  | 2091-12-23
Zone 2 | METHODS | Q321008884-1 | EXTENSION | 2021-05-12 | AGX870AA |  | 70113 | G05363136-007-01 | FRAME ASSY, AFT ENG MOUNT | YES | YES | COS | G05363136-007-01 | 4 Solución en espera de ser aprobada |  | 2091-12-23
Zone 3.3 | METHODS | Q321008886-1 | STANDARD | 2021-05-12 | AGX950 | AGX950 | 70106 | G05363921-003 | JOINT INSTL, STA 1016, REAR FUSE | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Gaps stringers TOP (QUERY 4365, gap intercostal vs frame)
Zone 4 | METHODS | Q321008888-1 | STANDARD | 2021-05-12 | AGX985AA | AGX985AA | 70102 | G05530150-001-90 | FAIRING INSTL, BULLET | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | TBD | CSK deep bullet fairing
Zone 3.4 | METHODS | Q321008800-2 | STANDARD | 2021-05-13 | AGX952 | AGX952 | 70107 | G05450502-103 | SKIN, UPR, CTR BOX | YES | NO | COS | G05450606-101-05 | 4 Solución en espera de ser aprobada |  | 70128-X | Elongated holes due to drag angle replacement and repair from Q321008800-001
Zone 3.4 | METHODS | Q321008800-3 | STANDARD | 2021-05-13 | AGX952 | AGX952 | 70107 | G05450606-101 | ANGLE, DRAG, CTR BOX, PYLON | YES | YES | COS | G05450606-101-04 | 4 Solución en espera de ser aprobada |  | 70108-X | Query 2560
Zone 3.2 | METHODS | Q321008908-1 | EXTENSION | 2021-05-13 | AGX820AA |  | 70109 | G05364510-001 | CELL INSTL, FLEXIBLE, AFT FUEL TANK | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | 70118-X | Adhesivo bladders
Zone 3.2 | METHODS | Q321008909-1 | EXTENSION | 2021-05-13 | AGX820AA |  | 70110 | G05364510-001 | CELL INSTL, FLEXIBLE, AFT FUEL TANK | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | 70118-X
Zone 3.2 | METHODS | Q321008910-1 | EXTENSION | 2021-05-13 | AGX820AA |  | 70111 | G05364510-001 | CELL INSTL, FLEXIBLE, AFT FUEL TANK | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | 70118-X
Zone 3.2 | METHODS | Q321008911-1 | EXTENSION | 2021-05-13 | AGX820AA |  | 70112 | G05364510-001 | CELL INSTL, FLEXIBLE, AFT FUEL TANK | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | 70118-X
Zone 3.2 | METHODS | Q321008912-1 | EXTENSION | 2021-05-13 | AGX820AA |  | 70113 | G05364510-001 | CELL INSTL, FLEXIBLE, AFT FUEL TANK | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | 70118-X
Zone 3.2 | METHODS | Q321008913-1 | EXTENSION | 2021-05-13 | AGX820AA |  | 70114 | G05364510-001 | CELL INSTL, FLEXIBLE, AFT FUEL TANK | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | 70118-X
Zone 2 | METHODS | Q321008921-1 | STANDARD | 2021-05-13 | AGX890AA | AGX890AA | 70109 | G05530400-009-01 | STRAP ASSY, FRONT SPAR, VSTAB | YES | YES | RFC | 168585 | 4 Solución en espera de ser aprobada |  | TBD
Zone 2 | METHODS | Q321008922-1 | STANDARD | 2021-05-13 | AGX890AA | AGX890AA | 70109 | G05530400-010-01 | STRAP ASSY, FRONT SPAR, VSTAB | YES | YES | RFC | 168585 | 4 Solución en espera de ser aprobada |  | TBD
Zone 3.3 | METHODS | Q321008923-1 | STANDARD | 2021-05-13 | AGX950AA | AGX950AA | 70108 | G05530213-106 | FITTING, INTERFACE, FRONT SPAR, VS | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Oversize cruciform
Zone 3.4 | METHODS | Q321008925-1 | STANDARD | 2021-05-13 | AGX952 | AGX952B | 70106 | G05370026-001-01 | FIDEX INSTL, PROVISIONS, REAR FUSE | YES | YES | COS | G05363284-101-02 | 4 Solución en espera de ser aprobada |  | 70124-X | Query 4145. DDA 11138A. Oversize bracket FIDEX
Zone 3.1 | METHODS | Q321008953-2 | STANDARD | 2021-05-13 | AGX810AA | AGX810AA | 70111 | G05360040-001 | FLOOR INSTL | NO | YES | N/A | N/A | 2 Análisis en Proceso | 34 | TBD | gaps localización piso/PSS 034
Zone 2 | METHODS | Q321008957-1 | STANDARD | 2021-05-13 | AGX880 | AGX880AA | 70110 | G05530119-003 | SKIN INSTL, VSTAB, LH | YES | YES | RFC | 3000168585 | 4 Solución en espera de ser aprobada |  | TBD
Zone 2 | METHODS | Q321008961-1 | EXTENSION | 2021-05-14 | AGX890AA |  | 70110 | G05530400-009-01 | STRAP ASSY, FRONT SPAR, VSTAB | YES | YES | RFC | 168585 | 4 Solución en espera de ser aprobada |  | TBD | Cambio de fastener por acceso
Zone 2 | METHODS | Q321008962-1 | EXTENSION | 2021-05-14 | AGX890AA |  | 70111 | G05530400-009-01 | STRAP ASSY, FRONT SPAR, VSTAB | YES | YES | RFC | 168585 | 4 Solución en espera de ser aprobada |  | TBD | Cambio de fastener por acceso
Zone 2 | METHODS | Q321008963-1 | EXTENSION | 2021-05-14 | AGX890AA |  | 70112 | G05530400-009-01 | STRAP ASSY, FRONT SPAR, VSTAB | YES | YES | RFC | 168585 | 4 Solución en espera de ser aprobada |  | TBD | Cambio de fastener por acceso
Zone 2 | METHODS | Q321008964-1 | EXTENSION | 2021-05-14 | AGX890AA |  | 70113 | G05530400-009-01 | STRAP ASSY, FRONT SPAR, VSTAB | YES | YES | RFC | 168585 | 4 Solución en espera de ser aprobada |  | TBD | Cambio de fastener por acceso
Zone 2 | METHODS | Q321008976-1 | EXTENSION | 2021-05-14 | AGX890AA |  | 70110 | G05530400-010-01 | STRAP ASSY, FRONT SPAR, VSTAB | YES | YES | RFC | 168585 | 4 Solución en espera de ser aprobada |  | TBD | Cambio de fastener por acceso
Zone 2 | METHODS | Q321008977-1 | EXTENSION | 2021-05-14 | AGX890AA |  | 70111 | G05530400-010-01 | STRAP ASSY, FRONT SPAR, VSTAB | YES | YES | RFC | 168585 | 4 Solución en espera de ser aprobada |  | TBD | Cambio de fastener por acceso
Zone 2 | METHODS | Q321008978-1 | EXTENSION | 2021-05-14 | AGX890AA |  | 70112 | G05530400-010-01 | STRAP ASSY, FRONT SPAR, VSTAB | YES | YES | RFC | 168585 | 4 Solución en espera de ser aprobada |  | TBD | Cambio de fastener por acceso
Zone 2 | METHODS | Q321008979-1 | EXTENSION | 2021-05-14 | AGX890AA |  | 70113 | G05530400-010-01 | STRAP ASSY, FRONT SPAR, VSTAB | YES | YES | RFC | 168585 | 4 Solución en espera de ser aprobada |  | TBD | Cambio de fastener por acceso
Zone 3.3 | METHODS | Q321008999-1 | STANDARD | 2021-05-14 | AGX950AA | AGX950AA | 70107 | G05363926-102 | INTERCOSTAL, MOORING, FTG AFT BARREL | NO | YES | N/A | N/A | 3 Causa Raiz detectada |  | TBD
Zone 3.4 | METHODS | Q321009007-1 | STANDARD | 2021-05-14 | AGX952 | AGX952B | 70106 | G05450059-007 | PANEL ASSY, CTR BOX, PYLON | YES | YES | COS | G05450511-105-02 | 4 Solución en espera de ser aprobada |  | 70150-X | Query 3274
Zone 3.4 | METHODS | Q321009007-3 | STANDARD | 2021-05-14 | AGX952 | AGX952B | 70106 | G05450054-007 | PANEL ASSY, CTR BOX, PYLON | YES | YES | COS | G05450504-105-02 | 4 Solución en espera de ser aprobada |  | 70116-X | Query 3274
Zone 3.4 | METHODS | Q321009007-2 | STANDARD | 2021-05-14 | AGX952 | AGX952B | 70106 | G05450058-007 | PANEL ASSY, CTR BOX, PYLON | YES | YES | COS | G05450510-105-02 | 4 Solución en espera de ser aprobada |  | 70108-X | Query 3274
Zone 3.4 | METHODS | Q321009007-4 | STANDARD | 2021-05-14 | AGX952 | AGX952B | 70106 | G05450055-007 | PANEL ASSY, CTR BOX, PYLON | YES | YES | COS | G05450505-105-02 | 4 Solución en espera de ser aprobada |  | 70110-X | Query 3274
Zone 2 | METHODS | Q321009008-1 | STANDARD | 2021-05-14 | AGX890 | AGX890 | 70109 | G05363100-003 | BARREL ASSY, REAR FUSELAGE | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.4 | METHODS | Q321009013-4 | STANDARD | 2021-05-14 | AGX952 | AGX952B | 70106 | G05450055-008 | PANEL ASSY, CTR BOX, PYLON | YES | YES | COS | G05450505-106-02 | 4 Solución en espera de ser aprobada |  | 70111-X | Query 3274
Zone 3.4 | METHODS | Q321009013-2 | STANDARD | 2021-05-14 | AGX952 | AGX952B | 70106 | G05450058-008 | PANEL ASSY, CTR BOX, PYLON | YES | YES | COS | G05450510-106-02 | 4 Solución en espera de ser aprobada |  | 70109-X | Query 3274
Zone 3.4 | METHODS | Q321009013-3 | STANDARD | 2021-05-14 | AGX952 | AGX952B | 70106 | G05450054-008 | PANEL ASSY, CTR BOX, PYLON | YES | YES | COS | G05450504-106-02 | 4 Solución en espera de ser aprobada |  | 70113-X | Query 3274
Zone 3.4 | METHODS | Q321009016-1 | STANDARD | 2021-05-14 | AGX952 | AGX954B | 70106 | G05450057-013-01 | TE ASSY, REMOVABLE, PYLON | YES | YES | COS | G05450508-107-02 & G05450509-107-03 | 4 Solución en espera de ser aprobada |  | 70112-X & 70130-X | Query 3274
Zone 3.4 | METHODS | Q321009018-1 | STANDARD | 2021-05-14 | AGX952 | AGX954B | 70106 | G05450057-014 | TE ASSY, REMOVABLE, PYLON | YES | YES | COS | G05450508-108-02 & G05450509-108-03 | 4 Solución en espera de ser aprobada |  | 70113-X & 70130-X | Query 3274
Zone 4 | METHODS | Q321009038-1 | STANDARD | 2021-05-14 | AGX975A | AGX965A | 70103 | G02895000-001 | FUEL INSTL.VENT, REAR FUSE | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Coupling removido, Meth ??
Zone 4 | METHODS | Q321009059-1 | STANDARD | 2021-05-14 | AGX955AA | AGX955AA | 70105 | G09172051-019 | HARNESS, AFT FUSE, REAR RHS RBB | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD | Clamp size arnéses
Zone 4 | METHODS | Q321009060-1 | SNC | 2021-05-14 | AGX955AA | AGX955AA | 70105 | G09171071-005 | CABLE, PWR FDR, ACEPC 1 APU TB RAP | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD | Uso más de 5 vueltas cinta fiber glass
Zone 4 | METHODS | Q321009060-2 | SNC | 2021-05-14 | AGX955AA | AGX955AA | 70105 | G09171057-007 | CABLE, PWR FDDR, VFG LHS ACEPC 1 PH A RL | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD | Uso más de 5 vueltas cinta fiber glass
Zone 3.4 | METHODS | Q321009087-1 | STANDARD | 2021-05-17 | AGX952B | AGX952B | 70107 | G09172001-017-01 | HARNESS, AFT FUSE, BAGGAGE RHS RBA | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | CLAMPS SIZE / ESPERANDO EL QUINTO RNC PARA LEVANTAR EL RFC
Zone 3.1 | METHODS | Q321009100-1 | STANDARD | 2021-05-17 | AGX810 |  | 70111 | G05361001-103 | SKIN, UPPER PANEL, AFT FUSE | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD | Oversize skin upper & stringer 4
Zone 3.3 | METHODS | Q321009113-1 | STANDARD | 2021-05-17 | AGX950 |  | 70106 | G05530170-001 | FAIRING INSTL, DORSAL | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Query 4475
Zone 4 | METHODS | Q321009130-1 | STANDARD | 2021-05-18 | AGX955 |  | 70105 | G09172051-019-01 | HARNESS, AFT FUSE, REAR RHS RBB | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Clamp size, query Q4451, Q4447
Zone 4 | METHODS | Q321009069-2 | STANDARD | 2021-05-18 | AGX955A | AGX965AA | 70105 | G02691200-001-03 | FIDEX INSTL, AFT FUSE | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD | 1OFF - Daño pieza, obvious scrap
Zone 4 | METHODS | Q321009157-1 | STANDARD | 2021-05-18 | AGX955 | AGX955AA | 70105 | G05363514-101 | FRAME, AFT ENG MOUNT, REAR FUSE | YES | YES | RFC | 61756 | 4 Solución en espera de ser aprobada |  | 70110-x | Fouling entre arnes y eng mount
Zone 3.3 | METHODS | Q321009175-1 | STANDARD | 2021-05-18 | AGX950 | AGX950AA | 70108 | G05363921-003 | JOINT INSTL, STA 1016, REAR FUSE | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Misalignment joining BELLY
Zone 3.3 | METHODS | Q321009175-2 | STANDARD | 2021-05-18 | AGX950 | AGX950AA | 70108 | G05363921-003 | JOINT INSTL, STA 1016, REAR FUSE | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Misalignment joining BELLY
Zone 3.1 | METHODS | Q321009187-1 | STANDARD | 2021-05-18 | AGX810 | AGX810AA | 70111 | G05362402-103 | FRAME, FS 864.00, UPPER, AFT FUSE LH | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD | STL PANEL ISSUES
Zone 3.1 | METHODS | Q321009187-2 | STANDARD | 2021-05-18 | AGX810 | AGX810AA | 70111 | G05360020-003 | JOINING ASSY SKIN PANEL AFT FUSE | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD
Zone 3.4 | METHODS | Q321009197-1 | STANDARD | 2021-05-18 | AGX952 | AGX952B | 70106 | G05450611-104. | ANGLE, DRAG, FIXED TE, PYLON | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD | Low Clearance TE FIXED
Zone 3.1 | METHODS | Q321009211-1 | STANDARD | 2021-05-19 | AGX806 |  | 70101 | G05362498-003 | SURROUND ASSY,CARGO DOOR,LHS PANEL | NO | NO | N/A | N/A | 2 Análisis en Proceso | PSS 034 | TBD
Zone 3.4 | METHODS | Q321009233-1 | STANDARD | 2021-05-19 | AGX952 | AGX952 | 70108 | G05450075-001 | BOX INSTL, CENTER, PYLON | YES | YES | COS | G05450606-101-05 | 4 Solución en espera de ser aprobada |  | 70128-X | Query 3116
Zone 5 | METHODS | Q321009257-1 | STANDARD | 2021-05-19 | AGX290 |  | 70112 | G05310750-001-01 | COCKPIT NOSE ASSY | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | PSS WIP for analisys from disc 001 from Dimensional Capsule Nose
Zone 5 | METHODS | Q321009257-2 | STANDARD | 2021-05-19 | AGX290 |  | 70112 | G05310750-001-01 | COCKPIT NOSE ASSY | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | PSS WIP for analisys from disc 002 from Dimensional Capsule Nose new Jig from Uplock fitting
Zone 5 | METHODS | Q321009257-3 | STANDARD | 2021-05-19 | AGX290 |  | 70112 | G05310750-001-01 | COCKPIT NOSE ASSY | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | PSS WIP for analisys from disc 003 from Dimensional Capsule Nose some details parts seems to be out of tol contour analisys WIP.
Zone 5 | METHODS | Q321009257-4 | STANDARD | 2021-05-19 | AGX290 |  | 70112 | G05310750-001-01 | COCKPIT NOSE ASSY | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | PSS ON GOING NEW LOTE WILL BE VALIDATE FOR AC 70116 FOR OML CHECK FROM SUPPLIER
Zone 3.4 | METHODS | Q321009223-1 | STOCK PURGE | 2021-05-19 | AGX952 | AGX952 |  | G05450490-101-02 | ANGLE, CTR BOX, PYLON | YES | NO | COS | G05450490-101-02 | 5 Monitoreo y mejora |  | TBD | Stock Purge para scrappear QTY -8- Angles de COS obsoleto re-identificado por Metodos
Zone 1 | METHODS | Q321009289-1 | STANDARD | 2021-05-20 | AGX744 |  | 70112 | G05372390-001 | ECS INSTL CPCS PROVISION REAR FUSE | YES | YES | PCR | 61582 | 4 Solución en espera de ser aprobada |  | TBD | David Lencz da seguimiento al PCR
Zone 2 | METHODS | Q321009325-1 | STANDARD | 2021-05-20 | AGX880 |  | 70111 | G05530119-003 | SKIN INSTL, VSTAB, LH | YES | YES | RFC | 3000168585 | 4 Solución en espera de ser aprobada |  | TBD
Zone 3.1 | METHODS | Q321009300-1 | STANDARD | 2021-05-20 | AGX806 |  | 70101 | G05360055-003 | BULKHEAD INSTL, PRESSURE | NO | NO | N/A | N/A | 2 Análisis en Proceso | 34 | TBD
Zone 3.2 | METHODS | Q321009285-1 | STANDARD | 2021-05-20 | AGX830 |  | 70110 | G05372201-001 | ECS INSTL, LP PROVISIONS, ABOVE FLOOR | YES | YES | COS | CIN CSD-G05362500-003-0036 | 4 Solución en espera de ser aprobada |  | TBD | Mismatch condition bracket vs stringer
Zone 3.3 | METHODS | Q321009306-1 | STANDARD | 2021-05-20 | AGX950 |  | 70109 | G05363921-003 | JOINT INSTL, STA 1016, REAR FUSE | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Gap cruciform
Zone 3.3 | METHODS | Q321009306-2 | STANDARD | 2021-05-20 | AGX950 |  | 70109 | G05363921-003 | JOINT INSTL, STA 1016, REAR FUSE | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Gap cruciform
Zone 3.3 | METHODS | Q321009306-3 | STANDARD | 2021-05-20 | AGX950 |  | 70109 | G05530215-101 | ANGLE, FRONT SPAR, VSTAB | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Gap angle common cruciform
Zone 3.3 | METHODS | Q321009321-1 | STANDARD | 2021-05-20 | AGX950 |  | 70109 | G05363668-103-01 | STRINGER 26, AFT BARREL, LH | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD | Barreno redundante joining stringer 26 UNDER INVESTIGATION
Zone 3.4 | METHODS | Q321009277-1 | EXTENSION | 2021-05-20 | AGX952 |  | 70108 | G09172001-017-01 | HARNESS, AFT FUSE, BAGGAGE RHS RBA | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | EWIS B-BAY cambio tamaño clamp
Zone 3.4 | METHODS | Q321009278-1 | EXTENSION | 2021-05-20 | AGX952 |  | 70109 | G09172001-017-01 | HARNESS, AFT FUSE, BAGGAGE RHS RBA | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | EWIS B-BAY cambio tamaño clamp
Zone 3.4 | METHODS | Q321009279-1 | EXTENSION | 2021-05-20 | AGX952 |  | 70110 | G09172001-017-01 | HARNESS, AFT FUSE, BAGGAGE RHS RBA | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | EWIS B-BAY cambio tamaño clamp
Zone 3.4 | METHODS | Q321009280-1 | EXTENSION | 2021-05-20 | AGX952 |  | 70111 | G09172001-017-01 | HARNESS, AFT FUSE, BAGGAGE RHS RBA | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | EWIS B-BAY cambio tamaño clamp
Zone 3.4 | METHODS | Q321009281-1 | EXTENSION | 2021-05-20 | AGX952 |  | 70112 | G09172001-017-01 | HARNESS, AFT FUSE, BAGGAGE RHS RBA | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | EWIS B-BAY cambio tamaño clamp
Zone 3.4 | METHODS | Q321009318-1 | STANDARD | 2021-05-20 | AGX952 | AGX952 | 70107 | G05370026-001-01 | FIDEX INSTL, PROVISIONS, REAR FUSE | YES | YES | COS | G05363284-101-02 | 4 Solución en espera de ser aprobada |  | 70124-X | Query 4145, doble hoyo entre bracket fidex y stringer
Zone 3.4 | METHODS | Q321009327-3 | STANDARD | 2021-05-20 | AGX952 | AGX952 | 70108 | G05450606-102 | ANGLE, DRAG, CTR BOX, PYLON | YES | YES | COS | G05450606-102-06 | 4 Solución en espera de ser aprobada |  | 70122-X
Zone 3.4 | METHODS | Q321009329-1 | STANDARD | 2021-05-20 | AGX952 | AGX952 | 70108 | G05450605-102-03 | ANGLE, DRAG, CTR BOX, PYLON | YES | YES | COS | G05450605-102-05 | 4 Solución en espera de ser aprobada |  | 70109-70141 | Query 2560
Zone 3.4 | METHODS | Q321009337-1 | STANDARD | 2021-05-21 | AGX952 | AGX952 | 70108 | G05450490-102-02 | ANGLE, CTR BOX, PYLON | YES | YES | COS | G05450490-102-03 | 4 Solución en espera de ser aprobada |  | 2021-05-28 | Query 4472
Zone 3.4 | METHODS | Q321009327-4 | STANDARD | 2021-05-21 10:03 | AGX952 | AGX952 | 70108 | G05450503-104 | SKIN, LWR, CTR BOX | YES | YES | COS | G05450062-010-03 | 4 Solución en espera de ser aprobada |  | 2021-05-28 | Query 4470.
Zone 1 | METHODS | Q321009352-1 | STANDARD | 2021-05-21 09:12 | AGX738 | AGX738 | 70106 | G05291600-001 | ELECTRICAL INSTL, CARGO ACCESS DR | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Query 4450 solicitando RFC EDC: 25 Junio para levantar RFC
Zone 3.4 | METHODS | Q321009358-1 | STANDARD | 2021-05-21 10:24 | AGX949 | AGX949 | 70109 | G05450084-005-01 | SKIN ASSY, FIXED TE, PYLON | YES | YES | COS | G05450085-001-04 | 4 Solución en espera de ser aprobada |  | 70124-X | FAI SNAG
Zone 3.1 | METHODS | Q321009363-1 | STANDARD | 2021-05-21 10:27 | AGX806 | AGX806 | 70101 | G05365500-003 | BULKHEAD ASSY | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD | Localizacion incorrecta de piso 1 OFF AC 70101
Zone 3.3 | METHODS | Q321009368-1 | STANDARD | 2021-05-21 11:04 | AGX950AA | AGX950AA | 70109 | G05363921-003 | JOINT INSTL, STA 1016, REAR FUSE | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Oversize joining
Zone 3.4 | METHODS | Q321009372-1 | STANDARD | 2021-05-21 12:23 | AGX952AA | AGX952B | 70107 | G05450057-014 | TE ASSY, REMOVABLE, PYLON | YES | YES | COS | G05450508-108-02 & G05450509-108-03 | 4 Solución en espera de ser aprobada |  | 70113-X & 70130-X | CSK DEPTH. QUERY 3274
Zone 3.3 | METHODS | Q321009373-1 | STANDARD | 2021-05-21 12:42 | AGX950 | AGX950 | 70108 | G05363921-003 | JOINT INSTL, STA 1016, REAR FUSE | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Gap fittings TOP PANEL
Zone 3.3 | METHODS | Q321009373-2 | STANDARD | 2021-05-21 12:45 | AGX950 | AGX950 | 70108 | G05363921-003 | JOINT INSTL, STA 1016, REAR FUSE | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Gap fittings TOP PANEL
Zone 3.4 | METHODS | Q321009377-2 | STANDARD | 2021-05-21 12:38 | AGX952AA | AGX952B | 70107 | G05450058-008 | PANEL ASSY, CTR BOX, PYLON | YES | YES | COS | G05450510-106-02 | 4 Solución en espera de ser aprobada |  | 70109-X | CSK DEPTH. QUERY 3274
Zone 3.4 | METHODS | Q321009377-3 | STANDARD | 2021-05-21 12:38 | AGX952AA | AGX952B | 70107 | G05450054-008 | PANEL ASSY, CTR BOX, PYLON | YES | YES | COS | G05450504-106-02 | 4 Solución en espera de ser aprobada |  | 70113-X | CSK DEPTH. QUERY 3274
Zone 3.4 | METHODS | Q321009377-4 | STANDARD | 2021-05-21 12:38 | AGX952AA | AGX952B | 70107 | G05450055-008 | PANEL ASSY, CTR BOX, PYLON | YES | YES | COS | G05450505-106-02 | 4 Solución en espera de ser aprobada |  | 70111-X | CSK DEPTH. QUERY 3274
Zone 3.2 | METHODS | Q321009382-1 | STANDARD | 2021-05-21 13:31 | AGX830AA | AGX830AA | 70106 | G05364510-001 | CELL INSTL, FLEXIBLE, AFT FUEL TANK | YES | YES | RFC | DDA #12314 | 4 Solución en espera de ser aprobada |  | 2091-12-18
Zone 3.4 | METHODS | Q321009383-1 | STANDARD | 2021-05-21 13:36 | AGX952AA | AGX952AA | 70108 | G05450073-002-01 | TE INSTL, PYLON | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD | LOW CLEARANCE TE FIXED VS DOUBLER FROM BUCKET SKIN
Zone 3.4 | METHODS | Q321009386-1 | STANDARD | 2021-05-21 14:03 | AGX952 | AGX952 | 70108 | G05450075-001-01 | BOX INSTL, CENTER, PYLON | YES | YES | COS | G05450427-103-03 | 4 Solución en espera de ser aprobada |  | 2021-05-28 | Query 4472.
Zone 3.1 | METHODS | Q321009404-2 | STANDARD | 2021-05-21 15:25 | AGX810AA | AGX810AA | 70112 | G05360040-001 | FLOOR INSTL | NO | YES | N/A | N/A | 2 Análisis en Proceso | PSS 034 | TBD | PSS 034
Zone 3.4 | METHODS | Q321009411-2 | STANDARD | 2021-05-21 18:34 | AGX952AA | AGX952AA | 70107 | G00653060-003 | BUTT STRAP OML | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | SHOOTING 70107
Zone 3.4 | METHODS | Q321009411-3 | STANDARD | 2021-05-21 18:34 | AGX952AA | AGX952AA | 70107 | G00653060-003 | SKIN EOP | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | SHOOTING 70107
Zone 3.4 | METHODS | Q321009411-4 | STANDARD | 2021-05-21 18:34 | AGX952AA | AGX952AA | 70107 | G00606104-001 | SYM POINTS | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | SHOOTING 70107
Zone 3.4 | METHODS | Q321009411-5 | STANDARD | 2021-05-21 18:34 | AGX952AA | AGX952AA | 70107 | G00606104-001 | HSTAB PIVOT FITTINGS | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | SHOOTING 70107
Zone 3.4 | METHODS | Q321009411-8 | STANDARD | 2021-05-21 18:34 | AGX952AA | AGX952AA | 70107 | G00654510-001 | ENGINE MOUNTS | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | SHOOTING 70107
Zone 4 | METHODS | Q321009414-1 | STANDARD | 2021-05-21 19:12 | AGX985AA | AGX985AA | 70103 | G05530140-003 | PANEL INSTL, ACCESS PANEL, VSTAB | YES | YES | RFC | 3000168061 | 4 Solución en espera de ser aprobada |  | 70125-X | Query 4421 / CSK Deep VSTAB / 70107-x paneles sin CSK
Zone 3.4 | METHODS | Q321009415-1 | STANDARD | 2021-05-21 19:13 | AGX952AA | AGX952AA | 70107 | G05360001-003 | STRINGER RADIAL | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | SHOOTING 70107
Zone 4 | METHODS | Q321009416-1 | STANDARD | 2021-05-21 19:48 | AGX955AA | AGX965AA | 70106 | G09172051-019-01 | HARNESS, AFT FUSE, REAR RHS RBB | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 4 | METHODS | Q321009417-1 | SNC | 2021-05-21 19:58 | AGX955AA | AGX965AA | 70106 | G09171071-005 | CABLE, PWR FDR, ACEPC 1 APU TB RAP | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 4 | METHODS | Q321009417-2 | SNC | 2021-05-21 19:58 | AGX955AA | AGX965AA | 70106 | G09171057-007 | CABLE, PWR FDDR, VFG LHS ACEPC 1 PH A RL | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.1 | METHODS | Q321009496-1 | STANDARD | 2021-05-24 | AGX810 |  | 70111 | G05365622-101-02 | FITTING, STGR 16 EXT, AFT PRESS BHD | YES | YES | COS | Query 4022 | 4 Solución en espera de ser aprobada |  | AC 70115 | Query 4022
Zone 3.3 | METHODS | Q321009476-1 | STANDARD | 2021-05-24 | AGX950 |  | 70107 | G05530170-001 | FAIRING INSTL, DORSAL | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Trimming dorsal
Zone 3.4 | METHODS | Q321009453-1 | STANDARD | 2021-05-24 | AGX952 |  | 70107 | G05397211-005 | PANEL ASSY, UPPER, RH, | YES | YES | RFC | M170-SH0395 | 4 Solución en espera de ser aprobada |  | TBD | Q3556
Zone 3.4 | METHODS | Q321009462-1 | STANDARD | 2021-05-24 | AGX952 |  | 70108 | G05363449-101 | DOUBLER SIDE PANEL AFT BARREL | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | LOW ED DOUBLER DUE TO WL DEVIATION
Zone 3.4 | METHODS | Q321009465-1 | STANDARD | 2021-05-24 | AGX948 |  | 70109 | G05450084-006-01 | SKIN ASSY FIXED TE PYLON | YES | YES | COS | G05450085-002-05 | 4 Solución en espera de ser aprobada |  | 70124-x
Zone 3.4 | METHODS | Q321009493-1 | STANDARD | 2021-05-24 | AGX952 |  | 70107 | G05450073-001-01 | TE INSTL, PYLON | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | ARODYNAMIC SEALING MISSING FROM TE INSTL DRAWING
Zone 4 | METHODS | Q321009475-1 | STANDARD | 2021-05-24 | AGX964 |  | 70106 | 627700-1002 | PTU - MOTOR/PUMP PACKAGE INTERFACE DEF | YES | YES | RFC | 3000166121 | 4 Solución en espera de ser aprobada |  | TBD
Zone 4 | METHODS | Q321009483-1 | STANDARD | 2021-05-24 | AGX975 |  | 70104 | G02197162-014-01 | INLET ASSY, MECH, PRECOOLER, PYLON | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | CSK Deep
Zone 3.1 | METHODS | Q321009508-2 | STANDARD | 2021-05-25 | AGX810 |  | 70101 | G05360040-001 | FLOOR INSTL | YES | YES | COS | Query 4022 | 4 Solución en espera de ser aprobada | PSS 034 | TBD | PSS 034
Zone 3.4 | METHODS | Q321009519-1 | EXTENSION | 2021-05-25 | AGX952 |  | 70108 | G05397211-005 | PANEL ASSY, UPPER, RH, | YES | YES | RFC | SH0395 | 4 Solución en espera de ser aprobada |  | TBD | Q3556 - Belfast RFC
Zone 3.4 | METHODS | Q321009520-1 | EXTENSION | 2021-05-25 | AGX952 |  | 70109 | G05397211-005 | PANEL ASSY, UPPER, RH, | YES | YES | RFC | SH0395 | 4 Solución en espera de ser aprobada |  | TBD | Q3556 - Belfast RFC
Zone 3.4 | METHODS | Q321009521-1 | EXTENSION | 2021-05-25 | AGX952 |  | 70110 | G05397211-005 | PANEL ASSY, UPPER, RH, | YES | YES | RFC | SH0395 | 4 Solución en espera de ser aprobada |  | TBD | Q3556 - Belfast RFC
Zone 3.4 | METHODS | Q321009522-1 | EXTENSION | 2021-05-25 | AGX952 |  | 70111 | G05397211-005 | PANEL ASSY, UPPER, RH, | YES | YES | RFC | SH0395 | 4 Solución en espera de ser aprobada |  | TBD | Q3556 - Belfast RFC
Zone 3.4 | METHODS | Q321009523-1 | EXTENSION | 2021-05-25 | AGX952 |  | 70112 | G05397211-005 | PANEL ASSY, UPPER, RH, | YES | YES | RFC | SH0395 | 4 Solución en espera de ser aprobada |  | TBD | Q3556 - Belfast RFC
Zone 3.4 | METHODS | Q321009524-1 | EXTENSION | 2021-05-25 | AGX952 |  | 70113 | G05397211-005 | PANEL ASSY, UPPER, RH, | YES | YES | RFC | SH0395 | 4 Solución en espera de ser aprobada |  | TBD | Q3556 - Belfast RFC
Zone 3.4 | METHODS | Q321009525-1 | EXTENSION | 2021-05-25 | AGX952 |  | 70114 | G05397211-005 | PANEL ASSY, UPPER, RH, | YES | YES | RFC | SH0395 | 4 Solución en espera de ser aprobada |  | TBD | Q3556 - Belfast RFC
Zone 3.4 | METHODS | Q321009526-1 | EXTENSION | 2021-05-25 | AGX952 |  | 70115 | G05397211-005 | PANEL ASSY, UPPER, RH, | YES | YES | RFC | SH0395 | 4 Solución en espera de ser aprobada |  | TBD | Q3556 - Belfast RFC
Zone 3.4 | METHODS | Q321009527-1 | EXTENSION | 2021-05-25 | AGX952 |  | 70116 | G05397211-005 | PANEL ASSY, UPPER, RH, | YES | YES | RFC | SH0395 | 4 Solución en espera de ser aprobada |  | TBD | Q3556 - Belfast RFC
Zone 3.4 | METHODS | Q321009528-1 | EXTENSION | 2021-05-25 | AGX952 |  | 70117 | G05397211-005 | PANEL ASSY, UPPER, RH, | YES | YES | RFC | SH0395 | 4 Solución en espera de ser aprobada |  | TBD | Q3556 - Belfast RFC
Zone 3.4 | METHODS | Q321009529-1 | EXTENSION | 2021-05-25 | AGX952 |  | 70118 | G05397211-005 | PANEL ASSY, UPPER, RH, | YES | YES | RFC | SH0395 | 4 Solución en espera de ser aprobada |  | TBD | Q3556 - Belfast RFC
Zone 3.4 | METHODS | Q321009530-1 | EXTENSION | 2021-05-25 | AGX952 |  | 70119 | G05397211-005 | PANEL ASSY, UPPER, RH, | YES | YES | RFC | SH0395 | 4 Solución en espera de ser aprobada |  | TBD | Q3556 - Belfast RFC
Zone 3.4 | METHODS | Q321009531-1 | EXTENSION | 2021-05-25 | AGX952 |  | 70120 | G05397211-005 | PANEL ASSY, UPPER, RH, | YES | YES | RFC | SH0395 | 4 Solución en espera de ser aprobada |  | TBD | Q3556 - Belfast RFC
Zone 3.4 | METHODS | Q321009532-1 | EXTENSION | 2021-05-25 | AGX952 |  | 70121 | G05397211-005 | PANEL ASSY, UPPER, RH, | YES | YES | RFC | SH0395 | 4 Solución en espera de ser aprobada |  | TBD | Q3556 - Belfast RFC
Zone 4 | METHODS | Q321009538-1 | STANDARD | 2021-05-25 | AGX955 |  | 70105 | G05450073-001-01 | TE INSTL, PYLON | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Q4619. AERODYNAMIC SEAL
Zone 4 | METHODS | Q321009539-1 | STANDARD | 2021-05-25 | AGX955 |  | 70106 | G05450073-001-01 | TE INSTL, PYLON | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Q4619. AERODYNAMIC SEAL
Zone 4 | METHODS | Q321009540-1 | STANDARD | 2021-05-25 | AGX975 |  | 70104 | G02197162-013-01 | INLET ASSY, MECH, PRECOOLER, PYLON | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Q3274 / CSK deep precooler
Zone 4 | METHODS | Q321009541-1 | STANDARD | 2021-05-25 | AGX975 |  | 70104 | G05450073-001-01 | TE INSTL, PYLON | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Q4619. AERODYNAMIC SEAL
Zone 1 | METHODS | Q321009549-1 | STANDARD | 2021-05-25 | AGX744 |  | 70113 | G05372390-001 | ECS INSTL CPCS PROVISION REAR FUSE | YES | YES | PCR | 61582 | 4 Solución en espera de ser aprobada |  | TBD | David Lencz da seguimiento al PCR
Zone 3.1 | METHODS | Q321009567-1 | STANDARD | 2021-05-25 | AGX810 |  | 70112 | G05372201-001 | ECS INSTL. LP PROVISIONS | YES | YES | COS | Query 4923 | 4 Solución en espera de ser aprobada |  | TBD
Zone 3.2 | METHODS | Q321009582-1 | STANDARD | 2021-05-26 | AGX830 |  | 70108 | G05364500-001-01 | STRUCTURE ASSY, FUEL TANK, REAR FUSE | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | PSS required
Zone 3.2 | METHODS | Q321009583-1 | STANDARD | 2021-05-26 | AGX830 |  | 70111 | G05372201-001 | ECS INSTL, LP PROVISIONS, ABOVE FLOOR | YES | YES | COS | CIN CSD-G05362500-003-0036 | 4 Solución en espera de ser aprobada |  | 70117-x | Query 3232
Zone 3.4 | METHODS | Q321009542-1 | STANDARD | 2021-05-25 | AGX952 | AGX952 | 70103 | G05450073-001-01 | TE INSTL, PYLON | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Q4619. AERODYNAMIC SEAL
Zone 3.2 | METHODS | Q321009582-1 | STANDARD | 2021-05-26 | AGX830 |  | 70108 | G05364500-001-01 | STRUCTURE ASSY, FUEL TANK, REAR FUSE | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.2 | METHODS | Q321009583-1 | STANDARD | 2021-05-26 | AGX830 |  | 70111 | G05372201-001 | ECS INSTL, LP PROVISIONS, ABOVE FLOOR | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.2 | METHODS | Q321009639-1 | STANDARD | 2021-05-26 | AGX830 |  | 70110 | G02585204-001 | INSULATION INSTL, DAMPING, BULKHEAD UPR | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | En revisión con programa, posible ON HOLD
Zone 3.4 | METHODS | Q321009594-1 | STANDARD | 2021-05-26 | AGX952 | AGX952 | 70109 | G05363449-102 | DOUBLER, SIDE PANEL, AFT BARREL | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | LOW ED EN DOUBLER G05363449 DUE TO ACCUMULATION OF TOLERANCES
Zone 3.2 | METHODS | Q321009648-1 | EXTENSION | 2021-05-26 | AGX830AA |  | 70111 | G02585204-001 | INSULATION INSTL, DAMPING, BULKHEAD UPR | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | En revisión con programa, posible ON HOLD
Zone 3.2 | METHODS | Q321009649-1 | EXTENSION | 2021-05-26 | AGX830AA |  | 70112 | G02585204-001 | INSULATION INSTL, DAMPING, BULKHEAD UPR | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | En revisión con programa, posible ON HOLD
Zone 3.2 | METHODS | Q321009650-1 | EXTENSION | 2021-05-26 | AGX830AA |  | 70113 | G02585204-001 | INSULATION INSTL, DAMPING, BULKHEAD UPR | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | En revisión con programa, posible ON HOLD
Zone 3.2 | METHODS | Q321009651-1 | EXTENSION | 2021-05-26 | AGX830AA |  | 70114 | G02585204-001 | INSULATION INSTL, DAMPING, BULKHEAD UPR | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | En revisión con programa, posible ON HOLD
Zone 3.2 | METHODS | Q321009652-1 | EXTENSION | 2021-05-26 | AGX830AA |  | 70115 | G02585204-001 | INSULATION INSTL, DAMPING, BULKHEAD UPR | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | En revisión con programa, posible ON HOLD
Zone 3.2 | METHODS | Q321009653-1 | EXTENSION | 2021-05-26 | AGX830AA |  | 70116 | G02585204-001 | INSULATION INSTL, DAMPING, BULKHEAD UPR | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | En revisión con programa, posible ON HOLD
Zone 3.2 | METHODS | Q321009654-1 | EXTENSION | 2021-05-26 | AGX830AA |  | 70117 | G02585204-001 | INSULATION INSTL, DAMPING, BULKHEAD UPR | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | En revisión con programa, posible ON HOLD
Zone 3.2 | METHODS | Q321009655-1 | EXTENSION | 2021-05-26 | AGX830AA |  | 70118 | G02585204-001 | INSULATION INSTL, DAMPING, BULKHEAD UPR | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | En revisión con programa, posible ON HOLD
Zone 3.2 | METHODS | Q321009656-1 | EXTENSION | 2021-05-26 | AGX830AA |  | 70119 | G02585204-001 | INSULATION INSTL, DAMPING, BULKHEAD UPR | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | En revisión con programa, posible ON HOLD
Zone 2 | METHODS | Q321009749-1 | STANDARD | 2021-05-27 | AGX890 |  | 70111 | G05363100-003 | BARREL ASSY, REAR FUSELAGE | YES | YES | COS | G05363529-111-02 | 5 Monitoreo y mejora |  | 70126-X | QUERY 4033
Zone 3.2 | METHODS | Q321009642-1 | STANDARD | 2021-05-27 | AGX830 |  | 70110 | G05360045-001 | TANK INSTL, FUEL, REAR FUSE | NO | NO | N/A | N/A | 1 Problema detectado |  | TBD
Zone 3.2 | METHODS | Q321009761-1 | STANDARD | 2021-05-27 | AGX830 |  | 70111 | G02193000-001 | CPCS TUBE UNDER FUEL TANK INSTLN | YES | YES | RFC | 61602 | 4 Solución en espera de ser aprobada |  | 2091-12-13
Zone 3.2 | METHODS | Q321009763-1 | STANDARD | 2021-05-27 | AGX830 |  | 70112 | G02193000-001 | CPCS TUBE UNDER FUEL TANK INSTLN | YES | YES | RFC | 61602 | 4 Solución en espera de ser aprobada |  | 2091-12-13
Zone 3.4 | METHODS | Q321009711-1 | STANDARD | 2021-05-27 | AGX952 | AGX952 | 70109 | G05450084-005 | SKIN ASSY, FIXED TE, PYLON | YES | YES | COS | G05450612-104-03 | 4 Solución en espera de ser aprobada |  | 2021-05-28 | QUERY 4452
Zone 3.4 | METHODS | Q321009746-1 | STANDARD | 2021-05-27 | AGX952 | AGX952 | 70109 | G05450606-101 | ANGLE, DRAG, CTR BOX, PYLON | YES | YES | COS | G05450606-101-05 | 4 Solución en espera de ser aprobada |  | 70128-X | QUERY 3116. NCR CRITICO QTY -4- DOUBLE HOLES ON DRAG ANGLE NEAR AFT ENG MOUNT
Zone 3.4 | METHODS | Q321009746-2 | STANDARD | 2021-05-27 | AGX952 | AGX952 | 70109 | G05363449-101 | DOUBLER SIDE PANEL AFT BARREL | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | LOW ED ON DOUBLER G05363449 DUE TO ACCUMULATION OF TOLERANCES/ WL DEVIATION
Zone 2 | METHODS | Q321009770-1 | STANDARD | 2021-05-28 | AGX880 |  | 70112 | G05530119-003 | SKIN INSTL, VSTAB, LH | YES | YES | RFC | G05530529-103 | 4 Solución en espera de ser aprobada |  | 2021-05-28 | QUERY 4218 / CLEATS
Zone 3.2 | METHODS | Q321009790-1 | STANDARD | 2021-05-28 | AGX830 |  | 70111 | G05379140-001 | BRACKET ASSY, HARNESS SUPPORT | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD | Fouling bracket harness and cleat
Zone 3.2 | METHODS | Q321009817-1 | STANDARD | 2021-05-28 | AGX830 |  | 70111 | G05360045-001 | TANK INSTL, FUEL, REAR FUSE | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD | Low clearance web and cleat
Zone 3.3 | METHODS | Q321009812-1 | STANDARD | 2021-05-28 | AGX950 |  | 70109 | G05363921-003 | JOINT INSTL, STA 1016, REAR FUSE | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Stringers misalignment belly R24
Zone 3.4 | METHODS | Q321009767-1 | STANDARD | 2021-05-28 | AGX952 | AGX952 | 70109 | G05450075-002-01 | BOX INSTL, CENTER, PYLON | YES | YES | COS | G05450628-102-03 | 4 Solución en espera de ser aprobada |  | 2021-05-28 | Query 4503
Zone 3.4 | METHODS | Q321009767-2 | STANDARD | 2021-05-28 | AGX952 | AGX952 | 70109 | G05450075-002-01 | BOX INSTL, CENTER, PYLON | YES | YES | COS | G05450062-010-03 | 4 Solución en espera de ser aprobada |  | 2021-05-28 | Query 4470
Zone 3.4 | METHODS | Q321009767-3 | STANDARD | 2021-05-28 | AGX952 | AGX952 | 70109 | G05450605-102-01 | ANGLE, DRAG, CTR BOX, PYLON | YES | YES | COS | G05450062-010-02 | 4 Solución en espera de ser aprobada |  | 70110-X | Quer 2560
Zone 3.4 | METHODS | Q321009777-1 | STANDARD | 2021-05-28 | AGX952 | AGX952 | 70108 | G00653060-003 | FLOOR BEAM EOP/WL/BL | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | SHOOTING
Zone 3.4 | METHODS | Q321009777-2 | STANDARD | 2021-05-28 | AGX952 | AGX952 | 70108 | G00653060-003 | BUTT STRAP OML | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | SHOOTING
Zone 3.4 | METHODS | Q321009777-3 | STANDARD | 2021-05-28 | AGX952 | AGX952 | 70108 | G00653060-003 | SKIN EOP | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | SHOOTING
Zone 3.4 | METHODS | Q321009777-4 | STANDARD | 2021-05-28 | AGX952 | AGX952 | 70108 | G00606104-001 | SYM POINTS | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | SHOOTING
Zone 3.4 | METHODS | Q321009777-5 | STANDARD | 2021-05-28 | AGX952 | AGX952 | 70108 | G00606104-001 | HSTAB PIVOT FITTINGS | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | SHOOTING
Zone 3.4 | METHODS | Q321009777-8 | STANDARD | 2021-05-28 | AGX952 | AGX952 | 70108 | G00654510-001 | ENGINE MOUNTS | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | SHOOTING
Zone 3.4 | METHODS | Q321009778-1 | STANDARD | 2021-05-28 | AGX952 | AGX952 | 70108 | G05360001-003 | STRINGER RADIAL | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | SHOOTING
Zone 3.4 | METHODS | Q321009803-1 | STANDARD | 2021-05-28 | AGX952 | AGX952 | 70109 | G05450611-103 | ANGLE, DRAG, FIXED TE, PYLON | YES | YES | COS | G05450611-103-03 | 4 Solución en espera de ser aprobada |  | 2021-05-28 | QUERY 4452
Zone 3.4 | METHODS | Q321009815-1 | STANDARD | 2021-05-28 | AGX952 | AGX952 | 70109 | G05450490-101 | ANGLE, CTR BOX, PYLON | YES | YES | COS | G05450427-103-03 | 4 Solución en espera de ser aprobada |  | 2021-05-28 | Query 4472
Zone 4 | METHODS | Q321009787-1 | STANDARD | 2021-05-28 | AGX955 |  | 70106 | G02691203-005 | TUBE ASSY, FIDEX, APU | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Fouling condition FIDEX
Zone 4 | METHODS | Q321009813-1 | STANDARD | 2021-05-28 | AGX985 |  | 70104 | G05530170-001 | FAIRING INSTL, DORAL | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD | Aplicación sellador aerodinámico DORSAL / diseño
Zone 5 | METHODS | Q321009833-1 | STANDARD | 2021-05-28 | AGX290 |  | 70113 | G05310750-001-01 | COCKPIT NOSE ASSY | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | PSS WIP for analisys from disc 001 from Dimensional Capsule Nose
Zone 5 | METHODS | Q321009833-2 | STANDARD | 2021-05-28 | AGX290 |  | 70113 | G05310750-001-01 | COCKPIT NOSE ASSY | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | PSS WIP for analisys from disc 002 from Dimensional Capsule Nose new Jig from Uplock fitting
Zone 5 | METHODS | Q321009833-3 | STANDARD | 2021-05-28 | AGX290 |  | 70113 | G05310750-001-01 | COCKPIT NOSE ASSY | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | PSS WIP for analisys from disc 003 from Dimensional Capsule Nose some details parts seems to be out of tol contour analisys WIP.
Zone 5 | METHODS | Q321009833-4 | STANDARD | 2021-05-28 | AGX290 |  | 70113 | G05310750-001-01 | COCKPIT NOSE ASSY | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | PSS ON GOING NEW LOTE WILL BE VALIDATE FOR AC 70116 FOR OML CHECK FROM SUPPLIER
Zone 3.1 | METHODS | Q321009888-1 | STANDARD | 2021-05-31 | AGX810 |  | 70112 | G05362810-105 | FRAME, FS 846.50, AFT FUSE RH | NO | NO | N/A | N/A | 2 Análisis en Proceso |  | TBD | Gap frame versus skin lower and strap
Zone 3.2 | METHODS | Q321009892-1 | STANDARD | 2021-05-31 | AGX830 |  | 70109 | G05364500-001-01 | STRUCTURE ASSY, FUEL TANK, REAR FUSE | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Gap gussets tanque / PSS WIP
Zone 3.3 | METHODS | Q321009858-1 | STANDARD | 2021-05-31 | AGX950 |  | 70108 | G05530170-001 | FAIRING INSTL, DORSAL | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Trim dorsal angles / PSS WIP
Zone 3.4 | METHODS | Q321009872-1 | STANDARD | 2021-05-31 | AGX948 | AGX948 | 70110 | G05450084-006-01 | SKIN ASSY FIXED TE PYLON | YES | YES | COS | G05450085-002-05 | 4 Solución en espera de ser aprobada |  | 70124-X | FAI SNAG
Zone 4 | METHODS | Q321009846-1 | STANDARD | 2021-05-31 | AGX955 |  | 70107 | G09172051-019-01 | HARNESS, AFT FUSE, REAR RHS RBB | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Cambio de clamps size EWIS Query 4457
Zone 4 | METHODS | Q321009879-1 | SNC | 2021-05-31 | AGX955 |  | 70107 | G09171071-005 | CABLE, PWR FDR, ACEPC 1 APU TB RAP | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Uso de más de cinco vueltas de cinta fiber glass Query 4178
Zone 4 | METHODS | Q321009879-2 | SNC | 2021-05-31 | AGX955 |  | 70107 | G09171057-007 | CABLE, PWR FDDR, VFG LHS ACEPC 1 PH A RL | NO | YES | N/A | N/A | 2 Análisis en Proceso |  | TBD | Uso de más de cinco vueltas de cinta fiber glass Query 4178