## Old Data
Zone | BADGE | NCR # | NCR Type | Disc. Create Date | Work Centre | Norm. Line Position | Tail # | Part # | Part Desc | Action | ¿Repetitivo? | COS | Number | Phase | PSS # | ECD_or_AC | Comments | Query
MTS | Meth | Q321004221-1 | STANDARD | 2021-03-02 | SGX730A | SGX730A |  | G05293050-001-06 | PLATE ASSY, INBD HDL, CARGO ACCESS DR | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | QUERY 4320/ ECD APRIL. 30TH
MTS | Meth | Q321004300-1 | STANDARD | 2021-03-03 | SGX975A | SGX975A | 70070 | G02197162-012-01 | INLET ASSY, MECH, PRECOOLER, PYLON | Yes | Yes | RFC | RFC 3000163508 | 5 Monitoreo y mejora |  | 70100 | query 2757
MTS | Meth | Q321004356-1 | STANDARD | 2021-03-03 | SGX948A | SGX948A |  | G05450432-002-04 | BRACKET ASSY, CTR BOX, PYLON | Yes | Yes | RFC | RFC 3000165719 | 5 Monitoreo y mejora |  | 70110 | Query 2682
MTS | Meth | Q321004707-1 | STANDARD | 2021-03-09 | SGX948A | SGX948A |  | G05450432-002-04 | BRACKET ASSY, CTR BOX, PYLON | Yes | Yes | RFC | RFC 3000165719 | 5 Monitoreo y mejora |  | 70110 | Query 2682
MTS | Meth | Q321004709-1 | STANDARD | 2021-03-09 | SGX949A | SGX949A |  | G05450432-001-04 | BRACKET ASSY, CTR BOX, PYLON | Yes | Yes | RFC | RFC 3000165719 | 5 Monitoreo y mejora |  | 70110 | Query 2682
MTS | Meth | Q321004792-1 | STANDARD | 2021-03-10 | SGX965A | SGX965A |  | G02490961-103 | SUPPORT, PANEL SERVICE LIGHTS, AFT FUSE | Yes | Yes | RFC | RFC 61563 | 4 Solución en espera de ser aprobada |  | April 30th
MTS | Meth | Q321004834-1 | STANDARD | 2021-03-10 | SGX975A | SGX975A | 70070 | G02197168-105-01 | PANEL, DOOR, PRECOOLER INLET, PYLON | Yes | Yes | RFC | RFC 3000163508 | 5 Monitoreo y mejora |  | 70100 | query 2757
MTS | METH | Q321004959-1 | STANDARD | 2021-03-11 | SGX730A | SGX730A |  | G05293050-001-06 | PLATE ASSY, INBD HDL, CARGO ACCESS DR | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | QUERY 4320/ ECD APRIL. 30TH
MTS | Meth | Q321004994-1 | STANDARD | 2021-03-12 | SGX900A | SGX900A |  | G05211418-101 | PLATE, HINGE STEP, PASS ACS DR | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | QUERY 4502/VALIDACION DE DATOS EN NCR CON QC POR 4 A/C
MTS | Meth | Q321005038-1 | STANDARD | 2021-03-12 | SGX975A | SGX975A | 70070 | G02197162-012-01 | INLET ASSY, MECH, PRECOOLER, PYLON | Yes | Yes | RFC | RFC 3000163508 | 5 Monitoreo y mejora |  | 70100 | query 2757
MTS |  | Q321005177-1 | STANDARD | 2021-03-17 | SGX900 | SGX900 | 70070 | G05211418-101 | PLATE, HINGE STEP, PASS ACS DR | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | QUERY 4502/VALIDACION DE DATOS EN NCR CON QC POR 4 A/C
MTS | Meth | Q321005286-1 | STANDARD | 2021-03-18 | SGX975 | SGX975 | 70070 | G02197168-105-01 | PANEL, DOOR, PRECOOLER INLET, PYLON | Yes | Yes | RFC | RFC 3000163508 | 5 Monitoreo y mejora |  | 70100 | query 2757
MTS | Meth | Q321005304-1 | STANDARD | 2021-03-18 | SGX730 | SGX730 |  | G05293053-101 | RETAINER, BEARING | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | QUERY 4320/ ECD APRIL. 30TH
MTS |  | Q321005626-1 | STANDARD | 2021-03-22 | SGX949A | SGX949A |  | G05450432-001-05 | BRACKET ASSY, CTR BOX, PYLON | Yes | Yes | RFC | RFC 3000165719 | 5 Monitoreo y mejora |  | 70110 | Query 2682
MTS | Meth | Q321005654-1 | STANDARD | 2021-03-23 | SGX965A | SGX965A |  | G02490961-103 | SUPPORT, PANEL SERVICE LIGHTS, AFT FUSE | Yes | Yes | RFC | RFC 61563 | 4 Solución en espera de ser aprobada |  | April 30th
MTS | Meth | Q321005654-1 | STANDARD | 2021-03-23 | SGX965A | SGX965A |  | G02490961-103 | SUPPORT, PANEL SERVICE LIGHTS, AFT FUSE | Yes | Yes | RFC | RFC 61563 | 4 Solución en espera de ser aprobada |  | April 30th
MTS |  | Q321005710-1 | STANDARD | 2021-03-23 | SGX900A | SGX900A |  | G05211418-101 | PLATE, HINGE STEP, PASS ACS DR | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | Query 4502/4/30/2021 EN ESPERA DE 5 NCR'S
Zone 1 | Meth | Q321004298-1 | STANDARD | 2021-03-03 | AGX738 | AGX738 | 70096 | G05291600-001 | ELECTRICAL INSTL, CARGO ACCESS DR | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | Query Generado solicitando el RFC despues de 4 RNC's seguidos como es solicitado #4450 & #4411 (23-Apr)
Zone 1 | Meth | Q321004546-1 | TECHNICAL | 2021-03-05 | AGX744 | AGX744 | 70104 | G05372390-001 | ECS INSTL CPCS PROVISION REAR FUSE | Yes | Yes | RFC | RFC PCR 61582 | 4 Solución en espera de ser aprobada |  | Not Define | Query Generado solicitando el RFC #3356
Zone 1 | Meth | Q321004552-1 | TECHNICAL | 2021-03-05 | AGX744AA | AGX744AA | 70104 | G05372390-001 | ECS INSTL CPCS PROVISION REAR FUSE | Yes | Yes | RFC | RFC PCR 61582 | 4 Solución en espera de ser aprobada |  | Not Define | Query Generado solicitando el RFC #3356
Zone 1 | Meth | Q321004779-1 | STANDARD | 2021-03-10 | AGX738 | AGX738 | 70097 | G05291600-001 | ELECTRICAL INSTL, CARGO ACCESS DR | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | Query Generado solicitando el RFC despues de 4 RNC's seguidos como es solicitado #4450 & #4411 (23-Apr)
Zone 1 | METH | Q321004925-1 | STANDARD | 2021-03-11 | AGX744AA | AGX744AA | 70105 | G05372390-001 | ECS INSTL CPCS PROVISION REAR FUSE | Yes | Yes | RFC | RFC PCR 61582 | 4 Solución en espera de ser aprobada |  | Not Define | Query Generado solicitando el RFC #3356
Zone 5 |  | Q321005236-1 | STANDARD | 2021-03-17 | AGX290 | AGX290 | 70105 | G05310750-001-01 | COCKPIT NOSE ASSY | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso
Zone 5 |  | Q321005236-2 | STANDARD | 2021-03-17 | AGX290 | AGX290 | 70105 | G05310750-001-01 | COCKPIT NOSE ASSY | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  |  | 3508
Zone 5 |  | Q321005236-3 | STANDARD | 2021-03-17 | AGX290 | AGX290 | 70105 | G05310750-001-01 | COCKPIT NOSE ASSY | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  |  | 2560
Zone 5 |  | Q321005236-4 | STANDARD | 2021-03-17 | AGX290 | AGX290 | 70105 | G05310750-001-01 | COCKPIT NOSE ASSY | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  |  | 2560
Zone 1 | Meth | Q321005418-1 | STANDARD | 2021-03-19 | AGX738 | AGX738 | 70098 | G05291600-001 | ELECTRICAL INSTL, CARGO ACCESS DR | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | Query Generado solicitando el RFC despues de 4 RNC's seguidos como es solicitado #4450 & #4411 (23-Apr) | 2756
Zone 1 |  | Q321005551-1 | STANDARD | 2021-03-22 | AGX744AA | AGX744AA | 70106 | G05372390-001 | ECS INSTL CPCS PROVISION REAR FUSE | Yes | Yes | RFC | RFC PCR 61582 | 4 Solución en espera de ser aprobada |  | Not Define | Query Generado solicitando el RFC #3356 | 2560
Zone 1 | Meth | Q321005858-1 | STANDARD | 2021-03-25 | AGX738 | AGX738 | 70099 | G05291600-001 | ELECTRICAL INSTL, CARGO ACCESS DR | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | Query Generado solicitando el RFC despues de 4 RNC's seguidos como es solicitado #4450 & #4411 (23-Apr) | 2560
Zone 2 | Meth | Q321004197-1 | STANDARD | 2021-03-02 | AGX890AA | AGX890AA | 70101 | G05530400-007-01 | STRAP ASSY, FRONT SPAR, VSTAB | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | QUERY 4126/ Waiting RFC 26 May
Zone 2 | Meth | Q321004197-2 | STANDARD | 2021-03-02 | AGX890AA | AGX890AA | 70101 | G05530400-008-01 | STRAP ASSY, FRONT SPAR, VSTAB | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | QUERY 4126/ Waiting RFC 26 May
Zone 2 | Meth | Q321004653-1 | STANDARD | 2021-03-08 | AGX880AA | AGX880AA | 70103 | G05530119-003 | SKIN INSTL, VSTAB, LH | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | QUERY 4218/ Waiting RFC 28 May
Zone 2 | Meth | Q321004660-1 | STANDARD | 2021-03-09 | AGX890AA | AGX890AA | 70102 | G05530400-007-01 | STRAP ASSY, FRONT SPAR, VSTAB | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | QUERY 4126/ Waiting RFC 26 May
Zone 2 | Meth | Q321004660-2 | STANDARD | 2021-03-09 | AGX890AA | AGX890AA | 70102 | G05530400-008-01 | STRAP ASSY, FRONT SPAR, VSTAB | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | QUERY 4126/ Waiting RFC 26 May
Zone 2 | Meth | Q321004660-1 | STANDARD | 2021-03-09 | AGX890AA | AGX890AA | 70102 | G05530400-009-01 | STRAP ASSY, FRONT SPAR, VSTAB | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | QUERY 4126/ Waiting RFC 26 May
Zone 2 | Meth | Q321004660-2 | STANDARD | 2021-03-09 | AGX890AA | AGX890AA | 70102 | G05530400-008-01 | STRAP ASSY, FRONT SPAR, VSTAB | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | QUERY 4126/ Waiting RFC 26 May
Zone 2 | Meth | Q321004681-1 | STANDARD | 2021-03-09 | AGX890AA | AGX890AA | 70102 | G05530400-010-01 | STRAP ASSY, FRONT SPAR, VSTAB | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | QUERY 4126/ Waiting RFC 26 May
Zone 2 | Meth | Q321005128-1 | STANDARD | 2021-03-16 | AGX890AA | AGX890AA | 70103 | G05530400-010-01 | STRAP ASSY, FRONT SPAR, VSTAB | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | QUERY 4126/ Waiting RFC 26 May
Zone 2 | Meth | Q321005130-1 | STANDARD | 2021-03-16 | AGX890AA | AGX890AA | 70103 | G05530400-009-01 | STRAP ASSY, FRONT SPAR, VSTAB | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | QUERY 4126/ Waiting RFC 26 May
Zone 2 | Meth | Q321005147-1 | STANDARD | 2021-03-16 | AGX880AA | AGX880AA | 70103 | G05363136-007-01 | FRAME ASSY, AFT ENG MOUNT | Yes | Yes | COS | COS G05363136-009-01 | 4 Solución en espera de ser aprobada |  | 70120
Zone 2 |  | Q321005209-1 | STANDARD | 2021-03-17 | AGX880AA | AGX880AA | 70104 | G05530119-003 | SKIN INSTL, VSTAB, LH | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | QUERY 4126/ Waiting RFC 26 May
Zone 2 |  | Q321005220-1 | STANDARD | 2021-03-17 | AGX870AA | AGX890AA | 70103 | G05363136-007-01 | FRAME ASSY, AFT ENG MOUNT | Yes | Yes | COS | COS G05363136-009-01 | 4 Solución en espera de ser aprobada |  | 70120
Zone 3.1 | Meth | Q321004139-1 | STANDARD | 2021-03-01 | AGX810 | AGX810 | 70102 | G05362822-101-01 | SPLICE, FRAME, AFT FUSE | No | UNDEFINED | UNDEFINED | UNDEFINED | 0 Unknown
Zone 3.1 | Meth | Q321004294-1 | STANDARD | 2021-03-03 | AGX810AA | AGX810AA | 70103 | G05360040-001 | FLOOR INSTL | No | UNDEFINED | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Under investigation PSS 034
Zone 3.1 | Meth | Q321004294-2 | STANDARD | 2021-03-03 | AGX810AA | AGX810AA | 70103 | G05360040-001 | FLOOR INSTL | No | UNDEFINED | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | under investigation PSS 034
Zone 3.1 | Meth | Q321004567-1 | TECHNICAL | 2021-03-05 | AGX810AA | AGX810AA | 70103 | G05362084-101 | CLEAT, AFT FUSE | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  | 2021-04-14 | QUERY 4416
Zone 3.1 | Meth | Q321004716-1 | STANDARD | 2021-03-09 | AGX802AA | AGX802AA | 70103 | G05372102-003 | ECS INSTL TRIM AIR PROVISIONS | No | UNDEFINED | UNDEFINED | UNDEFINED | 2 Análisis en Proceso
Zone 3.1 | Meth | Q321004980-1 | STANDARD | 2021-03-12 | AGX804AA | AGX804AA | 70105 | G05363534-113 | FRAME, FRONT SPAR, REAR FUSE | No | Yes | UNDEFINED | UNDEFINED | 1 Problema detectado |  |  | Visual AID
Zone 3.1 | Meth | Q321004984-1 | STANDARD | 2021-03-12 | AGX806AA | AGX806AA | 70104 | G05372140-005 | BRACKET ASSY APS REAR FUSE | No | NO | UNDEFINED | UNDEFINED | 1 Problema detectado |  |  | Query 4442
Zone 3.1 | Meth | Q321005331-1 | STANDARD | 2021-03-18 | AGX802AA | AGX802AA | 70104 | G05372102-003 | ECS INSTL TRIM AIR PROVISIONS | No | UNDEFINED | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  | Under investigation
Zone 3.1 | Meth | Q321005382-1 | STANDARD | 2021-03-19 | AGX810 | AGX810AA | 70104 | G05366015-101 | FITTING, FWD ENGINE FRAME | No | UNDEFINED | UNDEFINED | UNDEFINED no | 2 Análisis en Proceso |  |  | no
Zone 3.1 |  | Q321005573-2 | STANDARD | 2021-03-22 | AGX810AA | AGX810AA | 70105 | G05360040-001 | FLOOR INSTL | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada | 34
Zone 3.2 | Meth | Q321004358-1 | STANDARD | 2021-03-03 | AGX830AA | AGX830AA | 70102 | G05360045-001 | TANK INSTL, FUEL, REAR FUSE | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  | 70104
Zone 3.2 | Meth | Q321004730-1 | STANDARD | 2021-03-09 | AGX830AA | AGX830AA | 70098 | G05364500-001-01 | STRUCTURE ASSY, FUEL TANK, REAR FUSE | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso
Zone 3.2 | Meth | Q321004839-1 | STANDARD | 2021-03-10 | AGX830AA | AGX830AA | 70101 | G02193000-001 | CPCS TUBE UNDER FUEL TANK INSTLN | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  | 30/4/21 | Query 3841
Zone 3.2 | Meth | Q321005154-1 | STANDARD | 2021-03-16 | AGX820AA | AGX820AA | 70103 | G05364510-001 | CELL INSTL, FLEXIBLE, AFT FUEL TANK | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  | 30/4/21 | QUERY 4397
Zone 3.2 | Meth | Q321005374-1 | STANDARD | 2021-03-19 | AGX830AA | AGX830AA | 70099 | G05364500-001-01 | STRUCTURE ASSY, FUEL TANK, REAR FUSE | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso
Zone 3.2 |  | Q321005639-1 | STANDARD | 2021-03-22 | AGX830AA | AGX830AA | 70099 | G05364510-001 | CELL INSTL, FLEXIBLE, AFT FUEL TANK | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  | 30/4/21 | Query 4228
Zone 3.2 |  | Q321005759-1 | STANDARD | 2021-03-24 | AGX830 | AGX830 | 70103 | G05372226-001 | BRACKET ASSY, LP SYSTEM | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  | 70117 | Query 3232
Zone 3.2 | Meth | Q321005860-1 | STANDARD | 2021-03-25 | AGX830AA | AGX830AA | 70102 | G02193000-001 | CPCS TUBE UNDER FUEL TANK INSTLN | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  | 30/4/21 | Query 3841
Zone 3.3 | Meth | Q321004247-1 | STANDARD | 2021-03-02 | AGX950 | AGX950 | 70100 | G05363447-106 | SPLICE, REAR SPAR, AFT BARREL | No | NO | UNDEFINED | UNDEFINED N/A | 2 Análisis en Proceso |  | - | CAMBIO DE SECUENCIA EN EL BARRENADO
Zone 3.3 | Meth | Q321004279-1 | STANDARD | 2021-03-02 | AGX950 | AGX950 | 70098 | G02100001-001 | DUCT, RAM AIR | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  | 70106 | CSD-G05361000-003-0019 CREATED (CSD PARA MOVER EL FITTING DE PLANTA 1001 A 1503 AL WBK GX830110045)
Zone 3.3 | Meth | Q321004523-1 | TECHNICAL | 2021-03-05 | AGX950 | AGX950 | 70101 | G05363921-003 | JOINT INSTL, STA 1016, REAR FUSE | No | Yes | UNDEFINED | UNDEFINED - | 2 Análisis en Proceso |  | - | GAP EXCESIVO/CAUSA:UNION Y ALINEACION JOINING AGX950) "CRUCI FORM"
Zone 3.3 | Meth | Q321004523-2 | TECHNICAL | 2021-03-05 | AGX950 | AGX950 | 70101 | G05530215-101 | ANGLE, FRONT SPAR, VSTAB | No | Yes | UNDEFINED | UNDEFINED - | 2 Análisis en Proceso |  | - | GAP EXCESIVO/CAUSA:UNION Y ALINEACION JOINING AGX950) "ANGLE, FRONT SPAR"
Zone 3.3 | Meth | Q321004818-1 | STANDARD | 2021-03-10 | AGX950 | AGX950 | 70101 | G05530213-106-01 | FITTING, INTERFACE, FRONT SPAR, VS | No | NO | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | POR JOINING
Zone 3.3 | METH | Q321004862-1 | STANDARD | 2021-03-11 | AGX950 | AGX950 | 70096 | G05530170-001 | FAIRING INSTL, DORSAL | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  | TBD | TRIM DE ANGLE DORSAL, QUERY 4475
Zone 3.3 | METH | Q321004883-1 | STANDARD | 2021-03-11 | AGX950 | AGX950 | 70098 | G05530170-001 | FAIRING INSTL, DORSAL | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  | TBD | TRIM DE ANGLE DORSAL, QUERY 4475
Zone 3.3 | METH | Q321004887-1 | STANDARD | 2021-03-11 | AGX950 | AGX950 | 70097 | G05530170-001 | FAIRING INSTL, DORSAL | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  | TBD | TRIM DE ANGLE DORSAL, QUERY 4475
Zone 3.3 | METH | Q321004934-1 | STANDARD | 2021-03-11 | AGX950AA | AGX950AA | 70101 | G02100001-001 | DUCT, RAM AIR | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  | 70106 | CSD-G05361000-003-0019 CREATED (CSD PARA MOVER EL FITTING DE PLANTA 1001 A 1503 AL WBK GX830110045)
Zone 3.3 | METH | Q321004941-1 | STANDARD | 2021-03-11 | AGX950 | AGX950 | 70101 | G05363133-003 | PANEL ASSY, SIDE LH, BARREL, REAR FUSE | No | UNDEFINED | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | MODIFICACION DE SECUENCIA
Zone 3.3 | METH | Q321004941-2 | STANDARD | 2021-03-11 | AGX950 | AGX950 | 70101 | G05363142-003 | PANEL ASSY, SIDE RH, BARREL, REAR FUSE | No | UNDEFINED | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | MODIFICACION DE SECUENCIA
Zone 3.3 | Meth | Q321004990-1 | STANDARD | 2021-03-12 | AGX950AA | AGX950AA | 70101 | G05363921-001 | JOINT INSTL, STA 1016, REAR FUSE | No | UNDEFINED | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | MANUFACTURE FITTING BY JOINING
Zone 3.3 | Meth | Q321004990-2 | STANDARD | 2021-03-12 | AGX950AA | AGX950AA | 70101 | G05363921-001 | JOINT INSTL, STA 1016, REAR FUSE | No | UNDEFINED | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | MANUFACTURE FITTING BY JOINING
Zone 3.3 | Meth | Q321005088-1 | STANDARD | 2021-03-16 | AGX950 | AGX950 | 70099 | G05530170-001 | FAIRING INSTL, DORSAL | No | UNDEFINED | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | BY POSITION
Zone 3.3 |  | Q321005184-1 | STANDARD | 2021-03-17 | AGX950AA | AGX950AA | 70102 | G05530213-106 | FITTING, INTERFACE, FRONT SPAR, VS | No | UNDEFINED | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  | TBD | QUERY 4475 (RFC)
Zone 3.3 | Meth | Q321005298-1 | STANDARD | 2021-03-18 | AGX950 | AGX950 | 70100 | G05530170-001 | FAIRING INSTL, DORSAL | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  | TBD | TRIM DE ANGLE DORSAL, QUERY 4475
Zone 3.3 |  | Q321005707-1 | STANDARD | 2021-03-23 | AGX950 | AGX950 | 70102 | G02100001-001 | DUCT, RAM AIR | No | UNDEFINED | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  | 70106 | CSD-G05361000-003-0019 CREATED (CSD PARA MOVER EL FITTING DE PLANTA 1001 A 1503 AL WBK GX830110045)
Zone 3.4 | Meth | Q321004173-1 | STANDARD | 2021-03-01 | AGX952 | AGX952 | 70099 | G05450410-102 | STIFFENER, CTR BOX, PYLON | Yes | Yes | COS | COS 4470 | 4 Solución en espera de ser aprobada |  | April 30th | New COS for skin G05450061-004-04
Zone 3.3 | Meth | Q321005854-1 | STANDARD | 2021-03-25 | AGX950 | AGX950 | 70102 | G05530170-001 | FAIRING INSTL, DORSAL | No | UNDEFINED | UNDEFINED | UNDEFINED | 0 Unknown
Zone 3.4 | Meth | Q321004173-2 | STANDARD | 2021-03-01 | AGX952 | AGX952 | 70099 | G05450439-102 | STIFFENER, CTR BOX, PYLON | Yes | Yes | COS | COS 4470 | 4 Solución en espera de ser aprobada |  | April 30th | New COS for skin G05450062-010-02
Zone 3.4 | Meth | Q321004204-1 | STANDARD | 2021-03-02 | AGX952 | AGX952 | 70099 | G05450502-104 | SKIN, UPPER, CTR BOX, PYLON | Yes | Yes | COS | COS 2560 | 5 Monitoreo y mejora |  | 70108-X | New COS for drag angle G05450606-102-04
Zone 3.4 | Meth | Q321004204-2 | STANDARD | 2021-03-02 | AGX952 | AGX952 | 70099 | G05450605-102-03 | ANGLE, DRAG, CTR BOX, PYLON | Yes | Yes | COS | COS 4402 | 4 Solución en espera de ser aprobada |  | TBD | New COS for drag angle G05450605-102
Zone 3.4 | Meth | Q321004233-1 | STANDARD | 2021-03-02 | AGX952 | AGX952 | 70098 | G05450073-002-01 | TE INSTL, PYLON | Yes | Yes | COS | COS 2756 | 4 Solución en espera de ser aprobada |  | 70105-X | New COS for rib G05450363-104-06
Zone 3.4 | Meth | Q321004289-1 | STANDARD | 2021-03-02 | AGX952 | AGX952 | 70099 | G05450620-104 | FITTING, TENSION, FIXED LE, PYLON | Yes | Yes | COS | COS 2560 | 4 Solución en espera de ser aprobada |  | 70108-X | New COS for fitting G05450379-102-03
Zone 3.4 | Meth | Q321004289-2 | STANDARD | 2021-03-02 | AGX952 | AGX952 | 70099 | G05450621-104 | FITTING, TENSION, FIXED LE, PYLON | Yes | Yes | COS | COS 2560 | 5 Monitoreo y mejora |  | 70108-X | New COS for fitting G05450376-102-03
Zone 3.4 | Meth | Q321004204-3 | STANDARD | 2021-03-03 | AGX952 | AGX952 | 70099 | G05450605-102 | ANGLE, DRAG, CTR BOX, PYLON | Yes | Yes | COS | COS 2560 | 4 Solución en espera de ser aprobada |  | 70108-X | New COS for drag angle G05450605-102-05
Zone 3.4 | Meth | Q321004302-3 | STANDARD | 2021-03-03 | AGX952 | AGX952 | 70099 | G05450606-101 | ANGLE, DRAG, CTR BOX, PYLON | Yes | Yes | COS | COS 2560 | 4 Solución en espera de ser aprobada |  | 70108-X | New COS for drag angle G05450606-101-04
Zone 3.4 | Meth | Q321004545-1 | TECHNICAL | 2021-03-05 | AGX945 | AGX945 | 70102 | G05450051-007 | LE ASSY FIXED PYLON | Yes | Yes | COS | COS 4183 | 4 Solución en espera de ser aprobada |  | TBD | Double hole due to workaround to fix problem with new COS for LE
Zone 3.4 | meth | Q321004553-1 | TECHNICAL | 2021-03-05 | AGX952AA | AGX952AA | 70098 | G05450057-N0013 | TE ASSY, REMOVABLE, PYLON | Yes | Yes | COS | COS G05450501-105-03 | 4 Solución en espera de ser aprobada |  | 70110-X | New COS for G05450508-107-02 70112-X & G05450509-107-02 70130-X
Zone 3.4 | Meth | Q321004583-1 | TECHNICAL | 2021-03-05 | AGX952AA | AGX952AA | 70098 | G05450059-007 | PANEL ASSY, CTR BOX, PYLON | Yes | Yes | COS | COS G05450501-105-03 | 4 Solución en espera de ser aprobada |  | 70110-X | New COS G05450511-105-02
Zone 3.4 | Meth | Q321004583-2 | TECHNICAL | 2021-03-05 | AGX952AA | AGX952AA | 70098 | G05450058-N0005 | PANEL ASSY, CTR BOX, PYLON | Yes | Yes | COS | COS G05450501-105-03 | 4 Solución en espera de ser aprobada |  | 70110-X | New COS G05450510-105-02
Zone 3.4 | Meth | Q321004583-4 | TECHNICAL | 2021-03-05 | AGX952AA | AGX952AA | 70098 | G05450055-N0003 | PANEL ASSY, CTR BOX, PYLON | Yes | Yes | COS | COS G05450501-105-03 | 4 Solución en espera de ser aprobada |  | 70110-X | New COS G05450505-105-02
Zone 3.4 | meth | Q321004586-1 | TECHNICAL | 2021-03-05 | AGX952AA | AGX952AA | 70098 | G05450052-005 | LE ASSY , REMOVABLE, PYLON | Yes | Yes | COS | COS G05450501-105-03 | 4 Solución en espera de ser aprobada |  | 70110-X | New COS G05450501-105-03
Zone 3.4 | Meth | Q321004609-1 | STANDARD | 2021-03-08 | AGX952 | AGX952 | 70100 | G05450225-101-02 | ANGLE, FIXED LE, PYLON | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada
Zone 3.4 | Meth | Q321004609-2 | STANDARD | 2021-03-08 | AGX952 | AGX952 | 70100 | G05450606-101-03 | ANGLE, DRAG, CTR BOX, PYLON | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso
Zone 3.4 | Meth | Q321004673-1 | STANDARD | 2021-03-09 | AGX948 | AGX948 | 70101 | G05450056-010-01 | TE ASSY, FIXED, PYLON | No | UNDEFINED | UNDEFINED | UNDEFINED | 0 Unknown
Zone 3.4 | Meth | Q321004689-5 | STANDARD | 2021-03-09 | AGX952 | AGX952 | 70100 | G05450439-102 | STIFFENER, CTR BOX, PYLON | Yes | Yes | COS | COS 4470 | 4 Solución en espera de ser aprobada |  | April 30th
Zone 3.4 | Meth | Q321004689-6 | STANDARD | 2021-03-09 | AGX952 | AGX952 | 70100 | G05450410-102 | STIFFENER, CTR BOX, PYLON | Yes | Yes | COS | COS 4470 | 4 Solución en espera de ser aprobada |  | April 30th
Zone 3.4 | Meth | Q321004689-8 | STANDARD | 2021-03-09 | AGX952 | AGX952 | 70100 | G05450075-002 | BOX INSTL, CENTER PYLON | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso
Zone 3.4 | Meth | Q321004733-1 | STANDARD | 2021-03-09 | AGX952 | AGX952 | 70100 | G05450484-102-02 | FITTING, CTR BOX, PYLON | Yes | Yes | COS | COS 4470 | 4 Solución en espera de ser aprobada |  | April 30th
Zone 3.4 | Meth | Q321004744-1 | STANDARD | 2021-03-09 | AGX952 | AGX952 | 70100 | G05450620-104 | FITTING, TENSION, FIXED LE, PYLON | Yes | Yes | COS | COS 2560 | 4 Solución en espera de ser aprobada |  | 70108-X
Zone 3.4 | Meth | Q321004744-2 | STANDARD | 2021-03-09 | AGX952 | AGX952 | 70100 | G05450621-104 | FITTING, TENSION, FIXED LE, PYLON | Yes | Yes | COS | COS 2560 | 5 Monitoreo y mejora |  | 70108-X
Zone 3.4B | Meth | Q321004748-1 | STANDARD | 2021-03-09 | AGX952 | AGX952B | 70099 | G05370026-001-01 | FIDEX INSTL, PROVISIONS, REAR FUSE | Yes | Yes | COS | COS 4145 | 4 Solución en espera de ser aprobada |  | TBD
Zone 3.4 | Meth | Q321004777-1 | STANDARD | 2021-03-10 | AGX952 | AGX952 | 70100 | G05450606-101-02 | ANGLE, DRAG, CTR BOX, PYLON | Yes | Yes | COS | COS 2560 | 4 Solución en espera de ser aprobada |  | 70108-X | New cos G05450606-101-04
Zone 3.4 | Meth | Q321004807-1 | STANDARD | 2021-03-10 | AGX952 | AGX952 | 70099 | G05450073-001-01 | TE INSTL, PYLON | Yes | Yes | COS | COS 2756 | 4 Solución en espera de ser aprobada |  | 70105-X | Low ED due to WL deviation/accumulation of tolerances. But it can be solved by New COS for Rib G05450363-103-05
Zone 3.4 | Meth | Q321004826-1 | STANDARD | 2021-03-10 | AGX944 | AGX944 | RR096 | G05450204-102-03 | STIFFENER, FIXED LE, PYLON | Yes | Yes | COS | COS 4203 | 4 Solución en espera de ser aprobada |  | TBD
Zone 3.4 | Meth | Q321004850-1 | STANDARD | 2021-03-10 | AGX952AA | AGX952AA | 70099 | G05450612-103-02 | ANGLE, DRAG, FIXED TE, PYLON | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Low ED due to WL deviation/accumulation of tolerances. En inv por CAM
Zone 3.4 | Meth | Q321004853-1 | STANDARD | 2021-03-10 | AGX952AA | AGX952AA | 70099 | G05363449-101 | DOUBLER SIDE PANEL AFT BARREL | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Low ED due to WL deviation/accumulation of tolerances. En inv por CAM
Zone 3.4B | Meth | Q321004810-1 | STANDARD | 2021-03-10 | AGX952AA | AGX952B | 70099 | G00653060-003 | FLOOR BEAM EOP/WL/BL | No | UNDEFINED | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Shooting
Zone 3.4B | Meth | Q321004810-2 | STANDARD | 2021-03-10 | AGX952AA | AGX952B | 70099 | G00653060-003 | STRINGER RADIAL POSITIONS (SECT BR-BR) | No | UNDEFINED | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Shooting
Zone 3.4B | Meth | Q321004810-3 | STANDARD | 2021-03-10 | AGX952AA | AGX952B | 70099 | G00653060-003 | BUTT STRAP OML | No | UNDEFINED | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Shooting
Zone 3.4 | Meth | Q321005102-1 | STANDARD | 2021-03-16 | AGX952 | AGX830 | 70102 | G05364600-001 | POST, FUEL TANK FLOOR | No | UNDEFINED | UNDEFINED | UNDEFINED | 0 Unknown
Zone 3.4B | Meth | Q321004810-4 | STANDARD | 2021-03-10 | AGX952AA | AGX952B | 70099 | G00653060-003 | SKIN EOP | No | UNDEFINED | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Shooting
Zone 3.4B | Meth | Q321004810-5 | STANDARD | 2021-03-10 | AGX952AA | AGX952B | 70099 | G00606104-001 | SYM POINTS | No | UNDEFINED | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Shooting
Zone 3.4B | Meth | Q321004810-6 | STANDARD | 2021-03-10 | AGX952AA | AGX952B | 70099 | G00606104-001 | HSTAB PIVOT FITTINGS | No | UNDEFINED | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Shooting
Zone 3.4B | Meth | Q321004810-7 | STANDARD | 2021-03-10 | AGX952AA | AGX952B | 70099 | G00654510-001 | ENGINE MOUNTS | No | UNDEFINED | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Shooting
Zone 3.4 | Meth | Q321005016-1 | STANDARD | 2021-03-12 | AGX952 | AGX952 | 70101 | G05450171-004 | RIB ASSY, CTR BOX, PYLON | No | NO | UNDEFINED | UNDEFINED | 1 Problema detectado |  |  | Fouling Rib VS engine Mount fitting. AC 70101
Zone 3.4 | Meth | Q321005099-1 | STANDARD | 2021-03-16 | AGX944 | AGX944 | RR096 | G05450500-104-03 | SKIN, FIXED LE, PYLON | Yes | Yes | COS | COS 4183 | 4 Solución en espera de ser aprobada |  | TBD
Zone 3.4 | Meth | Q321005227-1 | STANDARD | 2021-03-17 | AGX948 | AGX948 | 70102 | G05450056-010-01 | TE ASSY, FIXED, PYLON | Yes | Yes | COS | COS FAI snag | 4 Solución en espera de ser aprobada |  | 70124-X
Zone 3.4 | Meth | Q321005292-1 | STANDARD | 2021-03-18 | AGX952AA | AGX952AA | 70101 | G05450502-104 | SKIN, UPPER, CTR BOX, PYLON | Yes | Yes | COS | COS 2560 | 4 Solución en espera de ser aprobada |  | 70108-X | For query 2560 70102-X For query 4470, no effy yet
Zone 3.4 | Meth | Q321005292-2 | STANDARD | 2021-03-18 | AGX952AA | AGX952AA | 70101 | G05450410-102 | STIFFENER, CTR BOX, PYLON | Yes | Yes | COS | COS 4470 | 4 Solución en espera de ser aprobada |  | April 30th | No effy yet
Zone 3.4 | Meth | Q321005292-5 | STANDARD | 2021-03-18 | AGX952AA | AGX952AA | 70101 | G05450075-002 | BOX INSTL, CENTER, PYLON | Yes | Yes | COS | COS 2560 | 4 Solución en espera de ser aprobada |  | 70108-X | New COS for drag angle
Zone 3.4 | Meth | Q321005295-2 | STANDARD | 2021-03-18 | AGX952 | AGX952 | 70101 | G05450485-101-02 | ANGLE, CTR BOX, PYLON | Yes | Yes | COS | COS 4503 | 4 Solución en espera de ser aprobada |  | 2021-05-07
Zone 3.4 | Meth | Q321005295-3 | STANDARD | 2021-03-18 | AGX952 | AGX952 | 70101 | G05450606-101-03 | ANGLE, DRAG, CTR BOX, PYLON | Yes | Yes | COS | COS 2560 | 4 Solución en espera de ser aprobada |  | 70108-X | New COS for drag angle
Zone 3.4 | Meth | Q321005295-4 | STANDARD | 2021-03-18 | AGX952 | AGX952 | 70101 | G05450410-101-03 | STIFFENER, CTR BOX, PYLON | Yes | Yes | COS | COS 4470 | 4 Solución en espera de ser aprobada |  | April 30th | No effy yet
Zone 3.4 | Meth | Q321005327-1 | STANDARD | 2021-03-18 | AGX952 | AGX952 | 70101 | G05450611-103-02 | ANGLE, DRAG, FIXED TE, PYLON | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Hole close to radius due to accumulation of tolerances in WL.
Zone 3.4 | Meth | Q321005367-1 | STANDARD | 2021-03-18 | AGX952 | AGX952 | 70101 | G05450620-104 | FITTING, TENSION, FIXED LE, PYLON | Yes | Yes | COS | COS 2560 | 4 Solución en espera de ser aprobada |  | 70108-X | New COS for tension fitting
Zone 3.4 | Meth | Q321005395-1 | STANDARD | 2021-03-19 | AGX945 | AGX945 | 70103 | G05450500-103-03 | SKIN, FIXED LE, PYLON | Yes | Yes | COS | COS 4183 | 4 Solución en espera de ser aprobada |  | TBD | DDA 12219A. No effy yet
Zone 3.4 | Meth | Q321005404-1 | STANDARD | 2021-03-19 | AGX952 | AGX952 | 70101 | G05450612-103-02 | ANGLE, DRAG, FIXED TE, PYLON | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Low ED en angle por desv/acumulacion tol en WL
Zone 3.4 | Meth | Q321005419-1 | STANDARD | 2021-03-19 | AGX952 | AGX952 | 70101 | G05450628-102-02 | FITTING, CTR BOX, PYLON | Yes | Yes | COS | COS 4503 | 4 Solución en espera de ser aprobada |  | 2021-05-07 | Query rechazado. Nuevo query pendiente ECD 26 MAR
Zone 3.4 | Meth | Q321005292-6 | STANDARD | 2021-03-20 | AGX952 | AGX952B | 70101 | G05450606-102 | ANGLE, DRAG, CTR BOX, PYLON | No | UNDEFINED | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Hole clse to radius due to accumulation of tolerances/dev in WL
Zone 3.4 | Meth | Q321005534-1 | STANDARD | 2021-03-22 | AGX944 | AGX944 | 70104 | G05450500-104-03 | SKIN, FIXED LE, PYLON | Yes | Yes | COS | COS 4183 | 4 Solución en espera de ser aprobada |  | TBD
Zone 3.4 | Meth | Q321005619-1 | STANDARD | 2021-03-22 | AGX952 | AGX952 | 70101 | G05450073-002-01 | TE INSTL, PYLON | Yes | Yes | COS | COS 2756 | 4 Solución en espera de ser aprobada |  | 70105-X
Zone 3.4 | Meth | Q321005793-1 | STANDARD | 2021-03-24 | AGX952AA | AGX952B | 70100 | G00653060-003 | FLOOR BEAM EOP/WL/BL | No | UNDEFINED | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Shooting
Zone 3.4 | Meth | Q321005793-2 | STANDARD | 2021-03-24 | AGX952AA | AGX952B | 70100 | G00653060-003 | BUTT STRAP OML | No | UNDEFINED | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Shooting
Zone 3.4 | Meth | Q321005793-3 | STANDARD | 2021-03-24 | AGX952AA | AGX952B | 70100 | G00653060-003 | SKIN EOP | No | UNDEFINED | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Shooting
Zone 3.4 | Meth | Q321005793-4 | STANDARD | 2021-03-24 | AGX952AA | AGX952B | 70100 | G00606104-001 | SYM POINTS | No | UNDEFINED | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Shooting
Zone 3.4 | Meth | Q321005793-5 | STANDARD | 2021-03-24 | AGX952AA | AGX952B | 70100 | G00606104-001 | HSTAB PIVOT FITTINGS | No | UNDEFINED | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Shooting
Zone 3.4 | Meth | Q321005793-6 | STANDARD | 2021-03-24 | AGX952AA | AGX952B | 70100 | G00654510-001 | ENGINE MOUNTS | No | UNDEFINED | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Shooting
Zone 3.3 | Meth | Q321005839-1 | STANDARD | 2021-03-25 | AGX952AA | AGX952AA | 70100 | G05360001-003 | STRINGER RADIAL | No | UNDEFINED | UNDEFINED | UNDEFINED | 0 Unknown
Zone 3.3 | Meth | Q321005857-1 | STANDARD | 2021-03-25 | AGX952 | AGX952 | 70102 | G05450606-101 | ANGLE, DRAG, CTR BOX, PYLON | Yes | Yes | COS | COS 3116 | 4 Solución en espera de ser aprobada |  | 70128-X
Zone 4 | Meth | Q321004114-1 | STANDARD | 2021-03-01 | AGX955AA | AGX955AA | 70096 | G09171051-017 | HARNESS, AFT FUSE, REAR LHS RAB | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Query 3942
Zone 4 | Meth | Q321004123-1 | STANDARD | 2021-03-01 | AGX955AA | AGX955AA | 70096 | G09171051-017 | HARNESS, AFT FUSE, REAR LHS RAB | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Query 4173 Clamps*
Zone 4 | Meth | Q321004125-1 | STANDARD | 2021-03-01 | AGX955AA | AGX955AA | 70096 | G09181002-003 | CABLE, COAX, NAV 1 VOR LOC VLB | Yes | Yes | RFC | RFC 61498 | 4 Solución en espera de ser aprobada |  | Effect 70120
Zone 4 | Meth | Q321004130-1 | STANDARD | 2021-03-01 | AGX955AA | AGX955AA | 70096 | G09172051-017 | HARNESS, AFT FUSE, REAR RHS RBB | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Query 4173 Clamps*
Zone 4 | Meth | Q321004131-1 | STANDARD | 2021-03-01 | AGX955AA | AGX955AA | 70096 | G09172051-017 | HARNESS, AFT FUSE, REAR RHS RBB | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Query 4451 Clamps*
Zone 4 | Meth | Q321004131-2 | STANDARD | 2021-03-01 | AGX955AA | AGX955AA | 70096 | G09172051-017 | HARNESS, AFT FUSE, REAR RHS RBB | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Query 4173 Clamps*
Zone 4 | Meth | Q321004155-1 | STANDARD | 2021-03-01 | AGX975A | AGX975AA | 70095 | G02197162-012-01 | INLET ASSY, MECH, PRECOOLER, PYLON | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | Query 3274 Pylons CSK. DDA 10881 A
Zone 4 | Meth | Q321004293-1 | STANDARD | 2021-03-03 | AGX975AA | AGX975AA | 70095 | G02197162-011-01 | INLET ASSY, MECH, PRECOOLER, PYLON | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | Query 3274 Pylons CSK. DDA 10881 A
Zone 4 | Meth | Q321004293-1 | STANDARD | 2021-03-03 | AGX975AA | AGX975AA | 70095 | G02197162-011-01 | INLET ASSY, MECH, PRECOOLER, PYLON | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | Query 3274 Pylons CSK. DDA 10881 A
Zone 4 | Meth | Q321004361-1 | STANDARD | 2021-03-03 | AGX955AA | AGX955AA | 70097 | G09171051-017 | HARNESS, AFT FUSE, REAR LHS RAB | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Query 3942
Zone 4 | Meth | Q321004378-1 | STANDARD | 2021-03-03 | AGX985A | AGX985AA | 70094 | G05530150-001-90 | FAIRING INSTL, BULLET | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Bullet fairing flushness
Zone 4 | Meth | Q321004384-1 | STANDARD | 2021-03-04 | AGX985AA | AGX965AA | 70094 | G02123249-003 | DUCT ASSY, RIGID | No | Yes | UNDEFINED | UNDEFINED | 1 Problema detectado |  |  | ID under clamp. ECS
Zone 4 | Meth | Q321004534-1 | TECHNICAL | 2021-03-05 | AGX955AA | AGX955AA | 70097 | G09181002-003 | CABLE, COAX, NAV 1 VOR LOC VLB | Yes | Yes | RFC | RFC 61498 | 4 Solución en espera de ser aprobada |  | Effect 70120
Zone 4 | Meth | Q321004535-1 | TECHNICAL | 2021-03-05 | AGX955AA | AGX955AA | 70097 | G09172051-017 | HARNESS, AFT FUSE, REAR RHS RBB | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Query 4451 Clamps*
Zone 4 | Meth | Q321004542-1 | TECHNICAL | 2021-03-05 | AGX955A | AGX955AA | 70097 | G05363514-101 | FRAME, AFT ENG MOUNT, REAR FUSE | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | Query 3546 EWIS Standoff
Zone 4 | Meth | Q321004568-1 | TECHNICAL | 2021-03-05 | AGX975AA | AGX985AA | 70096 | G02691253-003 | TUBE ASSY, FIDEX, ENG LH | No | Yes | UNDEFINED | UNDEFINED | 1 Problema detectado |  |  | Low clearance Fidex pipe VS clamp
Zone 4 | Meth | Q321004570-1 | TECHNICAL | 2021-03-05 | AGX955AA |  | 70098 | G09181002-003 | CABLE, COAX, NAV 1 VOR LOC VLB | Yes | Yes | RFC | RFC 61498 | 4 Solución en espera de ser aprobada |  | Effect 70120
Zone 4 | Meth | Q321004571-1 | TECHNICAL | 2021-03-05 | AGX955AA |  | 70099 | G09181002-003 | CABLE, COAX, NAV 1 VOR LOC VLB | Yes | Yes | RFC | RFC 61498 | 4 Solución en espera de ser aprobada |  | Effect 70120
Zone 4 | Meth | Q321004572-1 | TECHNICAL | 2021-03-05 | AGX955AA |  | 70100 | G09181002-003 | CABLE, COAX, NAV 1 VOR LOC VLB | Yes | Yes | RFC | RFC 61498 | 4 Solución en espera de ser aprobada |  | Effect 70120
Zone 4 | Meth | Q321004573-1 | TECHNICAL | 2021-03-05 | AGX955AA |  | 70101 | G09181002-003 | CABLE, COAX, NAV 1 VOR LOC VLB | Yes | Yes | RFC | RFC 61498 | 4 Solución en espera de ser aprobada |  | Effect 70120
Zone 4 | Meth | Q321004574-1 | TECHNICAL | 2021-03-05 | AGX955AA |  | 70102 | G09181002-003 | CABLE, COAX, NAV 1 VOR LOC VLB | Yes | Yes | RFC | RFC 61498 | 4 Solución en espera de ser aprobada |  | Effect 70120
Zone 4 | Meth | Q321004575-1 | TECHNICAL | 2021-03-05 | AGX955AA |  | 70103 | G09181002-003 | CABLE, COAX, NAV 1 VOR LOC VLB | Yes | Yes | RFC | RFC 61498 | 4 Solución en espera de ser aprobada |  | Effect 70120
Zone 4 | Meth | Q321004576-1 | TECHNICAL | 2021-03-05 | AGX955AA |  | 70104 | G09181002-003 | CABLE, COAX, NAV 1 VOR LOC VLB | Yes | Yes | RFC | RFC 61498 | 4 Solución en espera de ser aprobada |  | Effect 70120
Zone 4 | Meth | Q321004577-1 | TECHNICAL | 2021-03-05 | AGX955AA |  | 70105 | G09181002-003 | CABLE, COAX, NAV 1 VOR LOC VLB | Yes | Yes | RFC | RFC 61498 | 4 Solución en espera de ser aprobada |  | Effect 70120
Zone 4 | Meth | Q321004578-1 | TECHNICAL | 2021-03-05 | AGX955AA |  | 70106 | G09181002-003 | CABLE, COAX, NAV 1 VOR LOC VLB | Yes | Yes | RFC | RFC 61498 | 4 Solución en espera de ser aprobada |  | Effect 70120
Zone 4 | Meth | Q321004579-1 | TECHNICAL | 2021-03-05 | AGX955AA |  | 70107 | G09181002-003 | CABLE, COAX, NAV 1 VOR LOC VLB | Yes | Yes | RFC | RFC 61498 | 4 Solución en espera de ser aprobada |  | Effect 70120
Zone 4 | Meth | Q321004580-1 | TECHNICAL | 2021-03-05 | AGX955AA |  | 70108 | G09181002-003 | CABLE, COAX, NAV 1 VOR LOC VLB | Yes | Yes | RFC | RFC 61498 | 4 Solución en espera de ser aprobada |  | Effect 70120
Zone 4 | Meth | Q321004581-1 | TECHNICAL | 2021-03-05 | AGX955AA |  | 70109 | G09181002-003 | CABLE, COAX, NAV 1 VOR LOC VLB | Yes | Yes | RFC | RFC 61498 | 4 Solución en espera de ser aprobada |  | Effect 70120
Zone 4 | Meth | Q321004646-1 | STANDARD | 2021-03-08 | AGX955AA | AGX955AA | 70097 | G09172051-017 | HARNESS, AFT FUSE, REAR RHS RBB | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Query 4451 Clamps*
Zone 4 | Meth | Q321004646-2 | STANDARD | 2021-03-08 | AGX955AA | AGX955AA | 70097 | G09172051-017 | HARNESS, AFT FUSE, REAR RHS RBB | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Query 4173 Clamps*
Zone 4 | Meth | Q321004671-1 | STANDARD | 2021-03-09 | AGX985A | AGX985AA | 70095 | G02691253-003 | TUBE ASSY, FIDEX, ENG LH | No | Yes | UNDEFINED | UNDEFINED | 1 Problema detectado |  |  | Low clearance Fidex pipe VS clamp
Zone 4 | Meth | Q321004725-1 | STANDARD | 2021-03-09 | AGX985AA | AGX985AA | 70095 | G05530175-001 | LE INST, VSTAB | No | Yes | UNDEFINED | UNDEFINED | 1 Problema detectado |  |  | Steps LE Vstab
Zone 4 | Meth | Q321004851-1 | STANDARD | 2021-03-10 | AGX985A | AGX985AA | 70095 | G05530150-001-90 | FAIRING INSTL, BULLET | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Bullet fairing flushness
Zone 4 | METH | Q321004875-1 | STANDARD | 2021-03-11 | AGX965AA | AGX965AA | 70096 | G02691203-005 | TUBE ASSY, FIDEX, APU | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Fidex fouling
Zone 4 | METH | Q321004876-1 | STANDARD | 2021-03-11 | AGX975A | AGX975AA | 70096 | G02197162-012-01 | INLET ASSY, MECH, PRECOOLER, PYLON | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | Query 3274 Pylons CSK. DDA 10881 A
Zone 4 | Meth | Q321004986-1 | STANDARD | 2021-03-12 | AGX964A | AGX964AA | 70097 | 627700-1002 | PTU - MOTOR/PUMP PACKAGE INTERFACE DEF | Yes | Yes | RFC | RFC 3000166121 | 4 Solución en espera de ser aprobada |  |  | RFC approved, waiting for ECD
Zone 4 | Meth | Q321005052-1 | STANDARD | 2021-03-12 | AGX965AA | AGX965AA | 70097 | G02691203-005 | TUBE ASSY, FIDEX, APU | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Fidex fouling
Zone 4 |  | Q321005176-1 | STANDARD | 2021-03-17 | AGX975AA | AGX975AA | 70096 | G02197162-011-01 | INLET ASSY, MECH, PRECOOLER, PYLON | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | Query 3274 Pylons CSK. DDA 10881 A
Zone 4 |  | Q321005268-1 | STANDARD | 2021-03-18 | AGX955AA | AGX955AA | 70098 | G09172051-017 | HARNESS, AFT FUSE, REAR RHS RBB | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Query 4451 Clamps*
Zone 4 |  | Q321005270-1 | STANDARD | 2021-03-18 | AGX955AA | AGX955AA | 70098 | G09172051-017 | HARNESS, AFT FUSE, REAR RHS RBB | No | UNDEFINED | UNDEFINED | UNDEFINED | 0 Unknown
Zone 4 |  | Q321005270-2 | STANDARD | 2021-03-18 | AGX955AA | AGX955AA | 70098 | G09172051-017 | HARNESS, AFT FUSE, REAR RHS RBB | No | UNDEFINED | UNDEFINED | UNDEFINED | 0 Unknown
Zone 4 | Meth | Q321005268-1 | STANDARD | 2021-03-18 | AGX955AA | AGX955AA | 70098 | G09172051-017 | HARNESS, AFT FUSE, REAR RHS RBB | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Query 4447 Clamps*
Zone 4 | Meth | Q321005270-1 | STANDARD | 2021-03-18 | AGX955AA | AGX955AA | 70098 | G09172051-017 | HARNESS, AFT FUSE, REAR RHS RBB | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Query 4451 Clamps*
Zone 4 | Meth | Q321005270-2 | STANDARD | 2021-03-18 | AGX955AA | AGX955AA | 70098 | G09172051-017 | HARNESS, AFT FUSE, REAR RHS RBB | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Query 4447 Clamps*
Zone 4 | Meth | Q321005407-1 | STANDARD | 2021-03-19 | AGX964A | AGX965AA | 70098 | 627700-1002 | PTU - MOTOR/PUMP PACKAGE INTERFACE DEF | Yes | Yes | RFC | RFC 3000166121 | 4 Solución en espera de ser aprobada |  |  | RFC approved, waiting for ECD
Zone 4 | Meth | Q321005497-1 | STANDARD | 2021-03-20 | AGX985AA | AGX985AA | 70096 | G05530150-001-90 | FAIRING INSTL, BULLET | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Bullet fairing flushness
Zone 4 | Meth | Q321005499-1 | STANDARD | 2021-03-20 | AGX985AA | AGX985AA | 70096 | G02123249-003 | DUCT ASSY, RIGID | No | Yes | UNDEFINED | UNDEFINED | 1 Problema detectado |  |  | ID under clamp. ECS
Zone 4 |  | Q321005676-1 | STANDARD | 2021-03-23 | AGX985A | AGX975AA | 70097 | G02197162-012-01 | INLET ASSY, MECH, PRECOOLER, PYLON | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | Query 3274 Pylons CSK. DDA 10881 A
Zone 4 | Meth | Q321005795-1 | STANDARD | 2021-03-25 | AGX985AA | AGX965AA | 70097 | G05375300-001 | DRAIN INSTL, REAR FUSE | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | Query 4515
Zone 4 | Meth | Q321005803-1 | STANDARD | 2021-03-25 | AGX955AA | AGX955AA | 70099 | G09172051-017 | HARNESS, AFT FUSE, REAR RHS RBB | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Query 4451 Clamps*
Zone 4 | Meth | Q321005803-2 | STANDARD | 2021-03-25 | AGX955AA | AGX955AA | 70099 | G09172051-017 | HARNESS, AFT FUSE, REAR RHS RBB | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Query 4447 Clamps*
Zone 5 | Meth | Q321004547-1 | TECHNICAL | 2021-03-05 | AGX276A | AGX276 | 70105 | G05311192-101/01 | ANGLE, MLG, DOOR | Yes | Yes | RFC | RFC 3000167102 | 5 Monitoreo y mejora |  | 70100 | Query 2934
Zone 5 | Meth | Q321004669-1 | STANDARD | 2021-03-09 | AGX290 | AGX290 | 70104 | G05310750-001-01 | COCKPIT NOSE ASSY | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | PSS WIP for analisys from disc 001 from Dimensional Capsule Nose
Zone 5 | Meth | Q321004669-2 | STANDARD | 2021-03-09 | AGX290 | AGX290 | 70104 | G05310750-001-01 | COCKPIT NOSE ASSY | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | PSS WIP for analisys from disc 002 from Dimensional Capsule Nose new Jig from Uplock fitting
Zone 5 | Meth | Q321004669-3 | STANDARD | 2021-03-09 | AGX290 | AGX290 | 70104 | G05310750-001-01 | COCKPIT NOSE ASSY | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | PSS WIP for analisys from disc 003 from Dimensional Capsule Nose some details parts seems to be out of tol contour analisys WIP.
Zone 5 |  | Q321005779-1 | STANDARD | 2021-03-24 | AGX290AA | AGX290AA | 70106 | G05310750-001-01 | COCKPIT NOSE ASSY | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | PSS WIP for analisys from disc 001 from Dimensional Capsule Nose
Zone 5 |  | Q321005779-2 | STANDARD | 2021-03-24 | AGX290AA | AGX290AA | 70106 | G05310750-001-01 | COCKPIT NOSE ASSY | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | PSS WIP for analisys from disc 002 from Dimensional Capsule Nose new Jig from Uplock fitting
Zone 5 |  | Q321005779-3 | STANDARD | 2021-03-24 | AGX290AA | AGX290AA | 70106 | G05310750-001-01 | COCKPIT NOSE ASSY | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | PSS WIP for analisys from disc 003 from Dimensional Capsule Nose some details parts seems to be out of tol contour analisys WIP.
Zone 3.4 | Meth | Q321004173-3 | STANDARD | 2021-03-01 | AGX952 | AGX952 | 70099 | G05450502-104 | SKIN, UPPER, CTR BOX, PYLON | Yes | Yes | COS | COS 2560 | 5 Monitoreo y mejora |  | 70108-X | New COS for drag angle G05450606-102-04
Zone 3.4 | Meth | Q321004173-4 | STANDARD | 2021-03-01 | AGX952 | AGX952 | 70099 | G05450503-104 | SKIN , LWR, CTR BOX, PYLON | No | UNDEFINED | UNDEFINED | UNDEFINED | 0 Unknown
Zone 3.4 | Meth | Q321004385-2 | STANDARD | 2021-03-04 | AGX952 | AGX952 | 70098 | G05450058-N0006 | PANEL ASSY, CTR BOX, PYLON | Yes | Yes | COS | COS G05450501-105-03 | 4 Solución en espera de ser aprobada |  | 70110-X
Zone 5 | Meth | Q321004389-1 | STANDARD | 2021-03-04 | AGX277 | AGX277 | 70106 | G05310962-107-02 | BEAM, NLG DOOR | Yes | NO | CN | CN 2329335 | 4 Solución en espera de ser aprobada |  | Not Define
Zone 5 | Meth | Q321004389-2 | STANDARD | 2021-03-04 | AGX277 | AGX277 | 70106 | G05310968-001/02 | FITTING ASSY, NLG DOOR, AFT | Yes | NO | CN | CN 2329335 | 4 Solución en espera de ser aprobada |  | Not Define
Zone 5 | Meth | Q321004389-3 | STANDARD | 2021-03-04 | AGX277 | AGX277 | 70106 | G05310990-003/01 | FITTING ASSY, NLG DOOR, FWD | Yes | NO | CN | CN 2329335 | 4 Solución en espera de ser aprobada |  | Not Define
Zone 4 | Meth | Q321004397-1 | STANDARD | 2021-03-04 | AGX965 | AGX955 | 70096 | 627700-1002 | PTU - MOTOR/PUMP PACKAGE INTERFACE DEF | No | UNDEFINED | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Quert #3387
Zone 4 | Meth | Q321004406-1 | STANDARD | 2021-03-04 | AGX955 | AGX955 | 70097 | G09171051-017 | HARNESS, AFT FUSE, REAR LHS RAB | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso
Zone 3.4 | Meth | Q321004408-1 | STANDARD | 2021-03-04 | AGX952 | AGX952 | 70100 | G05450171-004 | RIB ASSY, CTR BOX, PYLON | No | NO | UNDEFINED | UNDEFINED | 1 Problema detectado |  |  | Fouling Rib VS engine Mount fitting. AC 70101
Zone 2 | Meth | Q321004420-1 | STANDARD | 2021-03-04 | AGX880 | AGX880 | 70102 | G05530119-003 | SKIN INSTL, VSTAB, LH | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada
Zone 2 | Meth | Q321004422-1 | STANDARD | 2021-03-04 | AGX880 | AGX880 | 70100 | G05530119-003 | SKIN INSTL, VSTAB, LH | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada
Zone 5 | Meth | Q321004437-1 | STANDARD | 2021-03-04 | AGX277 | AGX277 | 70106 | G05310952-105/01 | SKIN, HYDRAULIC BAY | Yes | NO | CN | CN 2329335 | 4 Solución en espera de ser aprobada |  | Not Define
Zone 5 | Meth | Q321004437-2 | STANDARD | 2021-03-04 | AGX277 | AGX277 | 70106 | G05310958-103/03 | DOUBLER, NLG DOOR LANDING | Yes | NO | CN | CN 2329335 | 4 Solución en espera de ser aprobada |  | Not Define
Zone 5 | Meth | Q321004437-3 | STANDARD | 2021-03-04 | AGX277 | AGX277 | 70106 | G05310961-103-02 | CHANNEL, LATCH SUPPORT, FWD | Yes | NO | CN | CN 2329335 | 4 Solución en espera de ser aprobada |  | Not Define
Zone 5 | Meth | Q321004442-1 | STANDARD | 2021-03-04 | AGX277 | AGX277 | 70106 | G05311130-005-01 | DOOR ASSY, SERVICE PANEL | Yes | NO | CN | CN 2329335 | 4 Solución en espera de ser aprobada |  | Not Define
Zone 3.3 | Meth | Q321004446-1 | STANDARD | 2021-03-04 | AGX950 | AGX950 | 70100 | G05363921-003 | JOINT INSTL, STA 1016. REAR FUSE | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | JOINING, AGX810 JIG & PANELS INSTALLATION CONDITION
Zone 3.3 | Meth | Q321004446-2 | STANDARD | 2021-03-04 | AGX950 | AGX950 | 70100 | G05363921-003 | JOINT INSTL, STA 1016. REAR FUSE | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | JOINING, AGX810 JIG & PANELS INSTALLATION CONDITION
MTS | Meth | Q321004448-1 | STANDARD | 2021-03-04 | SGX949 | SGX949 |  | G05450432-001-04 | BRACKET ASSY, CTR BOX, PYLON | Yes | Yes | RFC | RFC 3000165719 | 4 Solución en espera de ser aprobada |  | 70110
Zone 3.4 | Meth | Q321004460-1 | STANDARD | 2021-03-04 | AGX952 | AGX952 | 70099 | G05450605-102-01 | ANGLE, DRAG, CTR BOX, PYLON | No | UNDEFINED | UNDEFINED | UNDEFINED | 0 Unknown
Zone 3.4 | Meth | Q321004463-1 | STANDARD | 2021-03-04 | AGX946 | AGX946 | 70101 | G05450062-010-01 | SKIN ASSY, LWR, CTR BOX, PYLON | No | UNDEFINED | UNDEFINED | UNDEFINED | 0 Unknown
Zone 3.4 | Meth | Q321004482-1 | STANDARD | 2021-03-04 | AGX952 | AGX952 | 70099 | G05450484-102 | FITTING, CTR BOX, PYLON | Yes | Yes | COS | COS 4470 | 4 Solución en espera de ser aprobada |  | April 30th
MTS | Meth | Q321004492-1 | STANDARD | 2021-03-04 | SGX975 | SGX975 |  | G02197168-105-01 | PANEL, DOOR, PRECOOLER INLET, PYLON | Yes | Yes | RFC | RFC 3000163508 | 5 Monitoreo y mejora |  | 70100
Zone 3.4 | Meth | Q321004511-2 | STANDARD | 2021-03-05 | AGX952 | AGX952 | 70100 | G05450680-101 | FITTING, CTR BOX, PYLON | Yes | Yes | COS | COS 4470 | 4 Solución en espera de ser aprobada |  | April 30th
Zone 3.4 | Meth | Q321004511-3 | STANDARD | 2021-03-05 | AGX952 | AGX952 | 70100 | G05363449-101 | DOUBLER SIDE PANEL AFT BARREL | No | UNDEFINED | UNDEFINED | UNDEFINED | 0 Unknown
Zone 3.3 | Meth | Q321004523-3 | STANDARD | 2021-03-05 | AGX950 | AGX950 | 70101 | G05363602-109 | SKIN, LOWER PANEL, AFT BARREL | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | STGR 24 OVER SIZE BY JOINING
Zone 3.4 | Meth | Q321004689-9 | STANDARD | 2021-03-09 | AGX952 | AGX952 | 70100 | G05450062-010 | SKIN ASSY, LWR, CTR BOX, PYLON | No | UNDEFINED | UNDEFINED | UNDEFINED | 0 Unknown
Zone 3.4 | Meth | Q321004733-2 | STANDARD | 2021-03-09 | AGX952 | AGX952 | 70100 | G05450628-102-02 | FITTING, CTR BOX, PYLON | Yes | Yes | COS | COS 4470 | 4 Solución en espera de ser aprobada |  | April 30th
Zone 3.4 | Meth | Q321004733-4 | STANDARD | 2021-03-09 | AGX952 | AGX952 | 70100 | G05450605-101-04 | ANGLE, DRAG, CTR BOX, PYLON | No | UNDEFINED | UNDEFINED | UNDEFINED | 0 Unknown
Zone 3.4 | Meth | Q321004759-1 | STANDARD | 2021-03-10 | AGX952 | AGX952 | 70099 | G05450059-007 | PANEL ASSY, CTR BOX, PYLON | Yes | Yes | COS | COS G05450501-105-03 | 4 Solución en espera de ser aprobada |  | 70110-X
Zone 3.4 | Meth | Q321004759-2 | STANDARD | 2021-03-10 | AGX952 | AGX952 | 70099 | G05450058-N0005 | PANEL ASSY, CTR BOX, PYLON | Yes | Yes | COS | COS G05450501-105-03 | 4 Solución en espera de ser aprobada |  | 70110-X
Zone 3.4 | Meth | Q321004760-1 | STANDARD | 2021-03-10 | AGX952 | AGX952 | 70100 | G05362000-003 | PANEL ASSY, LH, AFT FUSE | No | UNDEFINED | UNDEFINED | UNDEFINED | 0 Unknown
Zone 3.4 | Meth | Q321004762-2 | STANDARD | 2021-03-10 | AGX952 | AGX952 | 70099 | G05450058-N0006 | PANEL ASSY, CTR BOX, PYLON | Yes | Yes | COS | COS G05450501-105-03 | 4 Solución en espera de ser aprobada |  | 70110-X
Zone 3.3 | Meth | Q321004990-3 | STANDARD | 2021-03-12 | AGX950 | AGX950 | 70101 | G05363926-102 | INTERCOSTAL, MOORING, FTG AFT BARREL | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | RFC SOLICITADO PARA AGREGAR UNA NOTA ESP. QUE NOS PERMITA USAR SHIM PARA ELIMINAR GAPS GENERADOS.
Zone 3.1 | Meth | Q321005062-2 | STANDARD | 2021-03-13 | AGX810 | AGX810 | 70104 | G05360040-001 | FLOOR INSTLALLATION, REAR FUSE | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso | 34 |  | under investigation PSS 034
Zone 3.4 | Meth | Q321005077-1 | STANDARD | 2021-03-15 | AGX952 | AGX952 | 70099 | G05450055-N0003 | PANEL ASSY, CTR BOX, PYLON | Yes | Yes | COS | COS G05450501-105-03 | 4 Solución en espera de ser aprobada |  | 70110-X
Zone 3.4 | Meth | Q321005484-1 | STANDARD | 2021-03-19 | AGX952 | AGX952 | 70099 | G05450054-N0003 | PANEL ASSY, CTR BOX, PYLON | Yes | Yes | COS | COS G05450501-105-03 | 4 Solución en espera de ser aprobada |  | 70110-X | NCR MAL LEVANTADO NO ES DE METODOS
Zone 3.3 | Meth | Q321005663-3 | STANDARD | 2021-03-23 | AGX950 | AGX950 | 70102 | G05363921-003 | JOINT INSTL, STA 1016, REAR FUSE | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | JOINING, AGX810 JIG & PANELS INSTALLATION CONDITION
Zone 3.3 | Meth | Q321005663-2 | STANDARD | 2021-03-23 | AGX950 | AGX950 | 70102 | G05363921-003 | JOINT INSTL, STA 1016, REAR FUSE | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | JOINING, AGX810 JIG & PANELS INSTALLATION CONDITION
Zone 5 | Meth | Q321005681-1 | STANDARD | 2021-03-23 | AGX276 | AGX276 | 70106 | G05311192-101/01 | ANGLE, MLG, DOOR | Yes | Yes | RFC | RFC 3000167102 | 5 Monitoreo y mejora |  | 70100 | Query 2934
Zone 3.4 | Meth | Q321005796-4 | STANDARD | 2021-03-25 | AGX952 | AGX952 | 70100 | G05450055-N0003 | PANEL ASSY, CTR BOX, PYLON | Yes | Yes | COS | COS G05450501-105-03 | 4 Solución en espera de ser aprobada |  | 70110-X
Zone 3.4 | Meth | Q321005796-3 | STANDARD | 2021-03-25 | AGX952 | AGX952 | 70100 | G05450054-N0003 | PANEL ASSY, CTR BOX, PYLON | Yes | Yes | COS | COS G05450501-105-03 | 4 Solución en espera de ser aprobada |  | 70110-X
Zone 3.4 | Meth | Q321005796-2 | STANDARD | 2021-03-25 | AGX952 | AGX952 | 70100 | G05450058-N0005 | PANEL ASSY, CTR BOX, PYLON | Yes | Yes | COS | COS G05450501-105-03 | 4 Solución en espera de ser aprobada |  | 70110-X
Zone 3.4 | Meth | Q321005796-1 | STANDARD | 2021-03-25 | AGX952 | AGX952 | 70100 | G05450059-007 | PANEL ASSY, CTR BOX, PYLON | Yes | Yes | COS | COS G05450501-105-03 | 4 Solución en espera de ser aprobada |  | 70110-X
Zone 3.4 | Meth | Q321005798-3 | STANDARD | 2021-03-25 | AGX952 | AGX952 | 70100 | G05450055-N0004 | PANEL ASSY, CTR BOX, PYLON | Yes | Yes | COS | COS G05450501-105-03 | 4 Solución en espera de ser aprobada |  | 70110-X
Zone 3.4 | Meth | Q321005798-1 | STANDARD | 2021-03-25 | AGX952 | AGX952 | 70100 | G05450058-N0006 | PANEL ASSY, CTR BOX, PYLON | Yes | Yes | COS | COS G05450501-105-03 | 4 Solución en espera de ser aprobada |  | 70110-X
Zone 3.4 | Meth | Q321005798-2 | STANDARD | 2021-03-25 | AGX952 | AGX952 | 70100 | G05450054-N0004 | PANEL ASSY, CTR BOX, PYLON | Yes | Yes | COS | COS G05450501-105-03 | 4 Solución en espera de ser aprobada |  | 70110-X
Zone 3.4 | Meth | Q321005857-2 | STANDARD | 2021-03-25 | AGX952 | AGX952 | 70102 | G05363449-101 | DOUBLER SIDE PANEL AFT BARREL | No | UNDEFINED | UNDEFINED | UNDEFINED | 0 Unknown
Zone 3.1 | Meth | Q321005922-1 | STANDARD | 2021-03-26 | AGX802 | AGX802 | 70105 | G05372102-003 | ECS INSTL TRIM AIR PROVISIONS | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | UNDER INVESTIGATION; REWORK NOT DONE AS PER DISPO
Zone 3.4 | Meth | Q321005936-1 | STANDARD | 2021-03-26 | AGX952 | AGX952 | 70102 | G05450476-103-02 | ANGLE, CTR BOX, PYLON | No | UNDEFINED | UNDEFINED | UNDEFINED | 0 Unknown
Zone 3.3 | Meth | Q321005964-1 | STANDARD | 2021-03-26 | AGX950 | AGX950 | 70101 | G05530170-001 | FAIRING INSTL, DORSAL | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | TRIM DE LOS ANGULOS PARA EL DORSAL FAIRING
Zone 4 | Meth | Q321005966-1 | STANDARD | 2021-03-26 | AGX955 | AGX874 | 70099 | G02691203-005 | TUBE ASSY, FIDEX, APU | No | NO | UNDEFINED | UNDEFINED | 0 Unknown
Zone 3.2 | Meth | Q321005979-1 | STANDARD | 2021-03-26 | AGX830 | AGX830 | 70100 | G05364510-001 | CELL INSTL, FLEXIBLE, AFT FUEL TANK | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  | 30/4/21 | QUERY 4397
Zone 3.1 | Meth | Q321005981-1 | STANDARD | 2021-03-26 | AGX808 | AGX808 | 70104 | G05379403-101 | BRACKET, GROUND | Yes | Yes | RFC | RFC 3000167678 | 4 Solución en espera de ser aprobada |  | 2021-04-28
Zone 3.4 | Meth | Q321005982-1 | STANDARD | 2021-03-27 | AGX952 | AGX952 | 70101 | G05372651-005 | TRAY ASSY, FIDEX ENGINE , AFT FUSE | No | UNDEFINED | UNDEFINED | UNDEFINED | 0 Unknown
MTS | Meth | Q321005986-1 | STANDARD | 2021-03-27 | SGX965 | SGX965 |  | G02490961-103 | SUPPORT, PANEL SERVICE LIGHTS, AFT FUSE | Yes | Yes | RFC | RFC 3000165719 | 4 Solución en espera de ser aprobada |  | 70110 | 4/30/2021/EN ESPERA DE APROBACION POR PARTE DE STELIA
Zone 4 | Meth | Q321005988-1 | STANDARD | 2021-03-27 | AGX985 | AGX985 | 70097 | G05530150-001-90 | FAIRING INSTL, BULLET | No | Yes | UNDEFINED | UNDEFINED | 0 Unknown |  |  | Bullet fairing flushness
Zone 4 | Meth | Q321006001-1 | STANDARD | 2021-03-27 | AGX975 | AGX985 | 70097 | G02691253-003 | TUBE ASSY, FIDEX, ENG LH | No | Yes | UNDEFINED | UNDEFINED | 0 Unknown |  |  | Low clearance entre perma y clamp
Zone 4 | Meth | Q321006013-1 | STANDARD | 2021-03-27 | AGX985 | AGX965 | 70098 | G02691253-003 | TUBE ASSY, FIDEX, ENG LH | No | Yes | UNDEFINED | UNDEFINED | 0 Unknown |  |  | Low clearance entre perma y clamp
Zone 3.4 | Meth | Q321006015-6 | STANDARD | 2021-03-27 | AGX952 | AGX952 | 70102 | G05450485-102 | ANGLE. CTR BOX, PYLON | No | UNDEFINED | UNDEFINED | UNDEFINED | 0 Unknown
Zone 3.4 | Meth | Q321006015-4 | STANDARD | 2021-03-27 | AGX952 | AGX952 | 70102 | G05450503-104 | SKIN, LWR, CTR BOX, PYLON | No | UNDEFINED | UNDEFINED | UNDEFINED | 0 Unknown
Zone 3.4 | Meth | Q321006015-5 | STANDARD | 2021-03-27 | AGX952 | AGX952 | 70102 | G05450502-104 | SKIN, UPPER, CTR BOX, PYLON | No | Yes | UNDEFINED | UNDEFINED | 0 Unknown |  | 70102-X | Q. 2560 New COS for drag angle G05450606-102-04
Zone 3.4 | Meth | Q321006015-7 | STANDARD | 2021-03-27 | AGX952 | AGX952 | 70102 | G05450503-104 | SKIN, LWR, CTR BOX, PYLON | No | UNDEFINED | UNDEFINED | UNDEFINED | 0 Unknown
Zone 3.4 | Meth | Q321006015-8 | STANDARD | 2021-03-27 | AGX952 | AGX952 | 70102 | G05450606-102 | ANGLE, DRAG, CTR BOX, PYLON | No | UNDEFINED | UNDEFINED | UNDEFINED | 0 Unknown
Zone 3.4 | Meth | Q321006015-10 | STANDARD | 2021-03-27 | AGX952 | AGX952 | 70102 | G05450410-102 | STIFFENER, CTR BOX, PYLON | No | UNDEFINED | UNDEFINED | UNDEFINED | 0 Unknown
Zone 3.4 | Meth | Q321006015-9 | STANDARD | 2021-03-27 | AGX952 | AGX952 | 70102 | G05450439-102 | STIFFENER, CTR BOX, PYLON | No | UNDEFINED | UNDEFINED | UNDEFINED | 0 Unknown
Zone 1 | Meth | Q321006033-1 | STANDARD | 2021-03-29 | AGX744 | AGX744 | 70107 | G05372390-001 | ECS INSTL CPCS PROVISION REAR FUSE | Yes | Yes | RFC | RFC PCR 61582 | 4 Solución en espera de ser aprobada |  | Not Define | Query Generado solicitando el RFC #3356
Zone 3.4 | Meth | Q321006035-1 | STANDARD | 2021-03-29 | AGX944 | AGX944 | R0099 | G05450500-104-03 | SKIN, FIXED LE, PYLON | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  | TBD
Zone 2 | Meth | Q321006038-1 | STANDARD | 2021-03-29 | AGX870 | AGX890 | 70104 | G05363136-007-01 | FRAME ASSY, AFT ENG MOUNT | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada
MTS | Meth | Q321006039-1 | STANDARD | 2021-03-29 | SGX900 | SGX900 |  | G05211418-101 | PLATE, HINGE STEP, PASS ACS DR | No | Yes | UNDEFINED | UNDEFINED | 0 Unknown |  |  | Query 4502/4/30/2021 EN ESPERA DE 5 NCR'S
Zone 3.4 | Meth | Q321006063-1 | STANDARD | 2021-03-29 | AGX952 | AGX952 | 70101 | G05370031-001-01 | BATT RACK PREFIT, OPEN FINAL & DEBURR | No | UNDEFINED | UNDEFINED | UNDEFINED | 0 Unknown
Zone 3.4 | Meth | Q321006075-2 | STANDARD | 2021-03-29 | AGX952 | AGX952 | 70102 | G05450606-101 | ANGLE, DRAG, CTR BOX, PYLON | No | UNDEFINED | UNDEFINED | UNDEFINED | 0 Unknown
MTS | Meth | Q321006086-1 | STANDARD | 2021-03-29 | SGX948 | SGX948 |  | G05450432-002-04 | BRACKET ASSY, CTR BOX, PYLON | Yes | Yes | RFC | RFC 3000165719 | 4 Solución en espera de ser aprobada |  | 70110
Zone 1 | Meth | Q321006089-1 | STANDARD | 2021-03-29 | AGX738 | AGX738 | 70100 | G05291600-001 | ELECTRICAL INSTL, CARGO ACCESS DR | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | Query Generado solicitando el RFC despues de 4 RNC's seguidos como es solicitado #4450 & #4411 (23-Apr)
Zone 3.3 | Meth | Q321006097-1 | STANDARD | 2021-03-29 | AGX950 | AGX950 | 70103 | G05530215-101-03 | ANGLE, FRONT SPAR, VSTAB | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | RFC SOLICITADO PARA AGREGAR UNA NOTA ESP. QUE NOS PERMITA USAR SHIM PARA ELIMINAR GAPS GENERADOS.
Zone 3.4 | Meth | Q321006133-1 | STANDARD | 2021-03-30 | AGX952 | AGX808 | 70102 | G05379403-101 | BRACKET, GROUND | No | UNDEFINED | UNDEFINED | UNDEFINED | 0 Unknown
MTS | Meth | Q321006151-1 | STANDARD | 2021-03-30 | SGX965 | SGX965 |  | G02490961-103 | SUPPORT, PANEL SERVICE LIGHTS, AFT FUSE | Yes | Yes | RFC | RFC 61563 | 3 Causa Raiz detectada |  | April 30th | 4/30/2021/EN ESPERA DE APROBACION POR PARTE DE STELIA
Zone 3.4 | Meth | Q321006168-1 | STANDARD | 2021-03-31 | AGX952 | AGX952 | 70102 | G05450614-101-02 | PLATE, AFT ENG FTG, CTR BOX | No | UNDEFINED | UNDEFINED | UNDEFINED | 0 Unknown
Zone 3.2 | Meth | Q321006217-1 | STANDARD | 2021-03-31 | AGX830 | AGX830 | 70102 | G05364500-001-01 | STRUCTURE ASSY, FUEL TANK, REAR FUSE | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso |  |  | Under investigation
Zone 4 | Meth | Q321006218-1 | STANDARD | 2021-03-31 | AGX985 | AGX952 | 70098 | GD425-1001-19 | FITTING ASSY, BULKHEAD, ENGINE FEED (LH) | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | NCRs para crear registro de doble torque en fitting
MTS | Meth | Q321006224-1 | STANDARD | 2021-03-31 | SGX948 | SGX948 |  | G05450432-002-04 | BRACKET ASSY, CTR BOX, PYLON | Yes | Yes | RFC | RFC 3000165719 | 5 Monitoreo y mejora |  | 70110
MTS | Meth | Q321006225-1 | STANDARD | 2021-03-31 | SGX949 | SGX949 |  | G05450432-001-04 | BRACKET ASSY, CTR BOX, PYLON | Yes | Yes | RFC | RFC 3000165719 | 5 Monitoreo y mejora |  | 70110
MTS | Meth | Q321006229-1 | STANDARD | 2021-03-31 | SGX730 | SGX730 |  | G05293053-101 | RETAINER, BEARING | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | QUERY 4320/ ECD APRIL. 30TH
Zone 4 | Meth | Q321006249-1 | STANDARD | 2021-03-31 | AGX955 | AGX955 | 70100 | G09171051-019 | HARNESS, AFT FUSE, REAR LHS RAB | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | Query #3942
Zone 4 | Meth | Q321006251-1 | STANDARD | 2021-03-31 | AGX955 | AGX955 | 70100 | G09171051-019 | HARNESS, AFT FUSE, REAR LHS RAB | No | Yes | UNDEFINED | UNDEFINED | 2 Análisis en Proceso
Zone 4 | Meth | Q321006254-1 | STANDARD | 2021-03-31 | AGX955 | AGX955 | 70100 | G09172051-019 | HARNESS, AFT FUSE, REAR RHS RBB | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | Query #4451 clamps
Zone 4 | Meth | Q321006260-1 | STANDARD | 2021-03-31 | AGX955 | AGX955 | 70100 | G09172051-019 | HARNESS, AFT FUSE, REAR RHS RBB | No | Yes | UNDEFINED | UNDEFINED | 3 Causa Raiz detectada |  |  | Query #4447 clamps

## Sheet1
UNDEFINED
RFC 3000163508
RFC 3000165719
RFC 3000165719
RFC 3000165719
RFC 61563
RFC 3000163508
UNDEFINED
UNDEFINED
RFC 3000163508
UNDEFINED
RFC 3000163508
UNDEFINED
RFC 3000165719
RFC 61563
RFC 61563
UNDEFINED
UNDEFINED
RFC PCR 61582
RFC PCR 61582
UNDEFINED
RFC PCR 61582
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
RFC PCR 61582
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
COS G05363136-009-01
UNDEFINED
COS G05363136-009-01
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED no
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED N/A
UNDEFINED
UNDEFINED -
UNDEFINED -
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
COS 4470
UNDEFINED
COS 4470
COS 2560
UNDEFINED
COS 2560
COS 4402
COS 2756
COS 2560
COS 2560
COS 2560
COS 2560
COS 4183
COS 3274
COS 3274
COS 3274
COS 3274
COS 3274
COS
UNDEFINED
UNDEFINED
COS 2560
COS 4470
COS 4470
UNDEFINED
UNDEFINED
COS 4470
COS 2560
COS 2560
COS 4145
COS 2560
COS 2756
COS 4203
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
COS 4183
COS FAI snag
COS 2560 4470
COS 4470
COS 2560
COS 4503
COS 2560
COS 4470
UNDEFINED
COS 2560
COS 4183
UNDEFINED
COS 4503
UNDEFINED
COS 4183
COS 2756
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
COS 3116
UNDEFINED
UNDEFINED
RFC 61498
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
RFC 61498
UNDEFINED
UNDEFINED
UNDEFINED
RFC 61498
RFC 61498
RFC 61498
RFC 61498
RFC 61498
RFC 61498
RFC 61498
RFC 61498
RFC 61498
RFC 61498
RFC 61498
RFC 61498
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
RFC 3000166121
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
RFC 3000166121
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
RFC 3000167102
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
COS 2560
UNDEFINED
COS 3274
CN 2329335
CN 2329335
CN 2329335
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
CN 2329335
CN 2329335
CN 2329335
CN 2329335
UNDEFINED
UNDEFINED
RFC 3000165719
UNDEFINED
UNDEFINED
COS 4470
RFC 3000163508
COS 4470
UNDEFINED
UNDEFINED
UNDEFINED
COS 4470
UNDEFINED
COS 3274
COS 3274
UNDEFINED
COS 3274
UNDEFINED
UNDEFINED
COS 3274
COS 3274
UNDEFINED
UNDEFINED
RFC 3000167102
UNDEFINED 3274
UNDEFINED 3274
UNDEFINED 3274
UNDEFINED 3274
UNDEFINED 3274
UNDEFINED 3274
UNDEFINED 3274
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
RFC 3000167678
UNDEFINED
RFC 3000165719
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
RFC PCR 61582
UNDEFINED 4183
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED
RFC 3000165719
UNDEFINED
UNDEFINED
UNDEFINED
RFC 61563
UNDEFINED
UNDEFINED
UNDEFINED
RFC 3000165719
RFC 3000165719
RFC
UNDEFINED
UNDEFINED
UNDEFINED
UNDEFINED

## Today
ZONE | BADGE | NCR # | NCR Type | Disc. Create Date | Work Centre | Norm. Line Position | Tail # | Part # | Part Desc | Action | RFC/Query | ECD or A/C | Comments
3.3 |  | Q321005663-1 | STANDARD | 2021-03-23 | AGX950 | AGX950 | 70102 | G05363921-003 | JOINT INSTL, STA 1016, REAR FUSE | N/A | N/A | N/A | N/A
3.3 |  | Q321005707-1 | STANDARD | 2021-03-23 | AGX950 | AGX950 | 70102 | G02100001-001 | DUCT, RAM AIR | YES | CIN | 70106-70116 | OMIT INSTALL IN 1001 PLANT
4 |  | Q321005676-1 | STANDARD | 2021-03-23 | AGX985A | AGX975AA | 70097 | G02197162-012-01 | INLET ASSY, MECH, PRECOOLER, PYLON
MTS |  | Q321005654-1 | STANDARD | 2021-03-23 | SGX965A | SGX965A |  | G02490961-103 | SUPPORT, PANEL SERVICE LIGHTS, AFT FUSE
MTS |  | Q321005710-1 | STANDARD | 2021-03-23 | SGX900A | SGX900A |  | G05211418-101 | PLATE, HINGE STEP, PASS ACS DR

## Today Chart
2021-04-20
Row Labels | Count of RFC/Query
MTS
(blank)
ZONE 2 | 3
r | 3
ZONE 3.1
(blank)
ZONE 3.2
(blank)
ZONE 3.4 | 7
g | 3
v | 4
(blank)
ZONE 3.4B | 1
v | 1
ZONE 4
(blank)
ZONE 5 | 3
v | 3
(blank)
(blank)
(blank)
Grand Total | 14

## Full chart
Disc. Create Date | (All)
Row Labels | Count of RFC/Query | Count of NCR #
0 |  | 10
2 |  | 1
3 |  | 16
3.1 |  | 2
3.4 | 5 | 25
4 |  | 2
1502 |  | 1
4
AGX226AA |  | 1
AGX277 |  | 1
AGX290 |  | 5
AGX710 |  | 1
AGX740 |  | 1
AGX740AA |  | 1
AGX742AA |  | 2
AGX744 |  | 3
AGX744AA |  | 1
AGX760AA |  | 2
AGX770 |  | 1
AGX770AA |  | 1
AGX784 |  | 3
AGX802 |  | 1
AGX802AA |  | 1
AGX806 |  | 1
AGX806AA |  | 2
AGX807 |  | 1
AGX810 |  | 6
AGX810AA |  | 18
AGX818 |  | 1
AGX830 |  | 1
AGX830AA |  | 14
AGX872AA |  | 2
AGX874AA |  | 1
AGX879 |  | 1
AGX880AA |  | 8
AGX882AA |  | 3
AGX888AA |  | 1
AGX890AA |  | 2
AGX942AA |  | 1
AGX944 |  | 1
AGX944AA |  | 1
AGX945 |  | 1
AGX946 |  | 1
AGX949 |  | 1
AGX950AA |  | 27
AGX952 |  | 4
AGX952AA |  | 96
AGX955AA |  | 15
AGX964AA |  | 4
AGX965AA |  | 2
AGX985AA |  | 9
AGX999AA |  | 4
C1 |  | 1
EXTENSION |  | 10
Fase 5 |  | 3
MTS |  | 6
SNC |  | 3
STANDARD |  | 17
ZONE 1 |  | 12
ZONE 2 | 6 | 10
ZONE 3 | 52 | 121
Zone 3.1 |  | 9
Zone 3.2 | 1 | 2
Zone 3.3 |  | 5
Zone 3.4 | 14 | 23
ZONE 4 | 2 | 60
ZONE 5 |  | 8
(blank)
Grand Total | 80 | 605