## Old Data
Zone | BADGE | NCR # | NCR Type | Disc. Create Date | Work Centre | Norm. Line Position | Tail # | Part # | Part Desc | Action | ¿Repetitivo? | RFC/CN/COS | # | Phase | PSS # | ECD or A/C | Comments | Query
MTS | Meth | Q321004221-1 | STANDARD | 2021-03-02 | SGX730A | SGX730A |  | G05293050-001-06 | PLATE ASSY, INBD HDL, CARGO ACCESS DR | SI | SI | RFC |  | 3 Causa Raiz detectada |  |  | QUERY 4320/ ECD APRIL. 30TH
MTS | Meth | Q321004300-1 | STANDARD | 2021-03-03 | SGX975A | SGX975A | 70070 | G02197162-012-01 | INLET ASSY, MECH, PRECOOLER, PYLON | yes | SI | RFC | 3000163508 | 5 Monitoreo y mejora |  | 70100 | query 2757
MTS | Meth | Q321004356-1 | STANDARD | 2021-03-03 | SGX948A | SGX948A |  | G05450432-002-04 | BRACKET ASSY, CTR BOX, PYLON | yes | SI | RFC | 3000165719 | 5 Monitoreo y mejora |  | 70110 | Query 2682
MTS | Meth | Q321004707-1 | STANDARD | 2021-03-09 | SGX948A | SGX948A |  | G05450432-002-04 | BRACKET ASSY, CTR BOX, PYLON | yes | SI | RFC | 3000165719 | 5 Monitoreo y mejora |  | 70110 | Query 2682
MTS | Meth | Q321004709-1 | STANDARD | 2021-03-09 | SGX949A | SGX949A |  | G05450432-001-04 | BRACKET ASSY, CTR BOX, PYLON | yes | SI | RFC | 3000165719 | 5 Monitoreo y mejora |  | 70110 | Query 2682
MTS | Meth | Q321004792-1 | STANDARD | 2021-03-10 | SGX965A | SGX965A |  | G02490961-103 | SUPPORT, PANEL SERVICE LIGHTS, AFT FUSE |  | SI | RFC | 61563 | 4 Solución en espera de ser aprobada |  | 2022-03-15
MTS | Meth | Q321004834-1 | STANDARD | 2021-03-10 | SGX975A | SGX975A | 70070 | G02197168-105-01 | PANEL, DOOR, PRECOOLER INLET, PYLON | yes | SI | RFC | 3000163508 | 5 Monitoreo y mejora |  | 70100 | query 2757
MTS | METH | Q321004959-1 | STANDARD | 2021-03-11 | SGX730A | SGX730A |  | G05293050-001-06 | PLATE ASSY, INBD HDL, CARGO ACCESS DR | SI | SI | RFC |  | 3 Causa Raiz detectada |  |  | QUERY 4320/ ECD APRIL. 30TH
MTS | Meth | Q321004994-1 | STANDARD | 2021-03-12 | SGX900A | SGX900A |  | G05211418-101 | PLATE, HINGE STEP, PASS ACS DR | SI | SI | RFC |  | 3 Causa Raiz detectada |  |  | QUERY 4502/VALIDACION DE DATOS EN NCR CON QC POR 4 A/C
MTS | Meth | Q321005038-1 | STANDARD | 2021-03-12 | SGX975A | SGX975A | 70070 | G02197162-012-01 | INLET ASSY, MECH, PRECOOLER, PYLON | yes | SI | RFC | 3000163508 | 5 Monitoreo y mejora |  | 70100 | query 2757
MTS |  | Q321005177-1 | STANDARD | 2021-03-17 | SGX900 | SGX900 | 70070 | G05211418-101 | PLATE, HINGE STEP, PASS ACS DR | SI | SI | RFC |  | 3 Causa Raiz detectada |  |  | QUERY 4502/VALIDACION DE DATOS EN NCR CON QC POR 4 A/C
MTS | Meth | Q321005286-1 | STANDARD | 2021-03-18 | SGX975 | SGX975 | 70070 | G02197168-105-01 | PANEL, DOOR, PRECOOLER INLET, PYLON | yes | SI | RFC | 3000163508 | 5 Monitoreo y mejora |  | 70100 | query 2757
MTS | Meth | Q321005304-1 | STANDARD | 2021-03-18 | SGX730 | SGX730 |  | G05293053-101 | RETAINER, BEARING | SI | SI | RFC |  | 3 Causa Raiz detectada |  |  | QUERY 4320/ ECD APRIL. 30TH
MTS |  | Q321005626-1 | STANDARD | 2021-03-22 | SGX949A | SGX949A |  | G05450432-001-05 | BRACKET ASSY, CTR BOX, PYLON | yes | SI | RFC | 3000165719 | 5 Monitoreo y mejora |  | 70110 | Query 2682
MTS | Meth | Q321005654-1 | STANDARD | 2021-03-23 | SGX965A | SGX965A |  | G02490961-103 | SUPPORT, PANEL SERVICE LIGHTS, AFT FUSE |  | SI | RFC | 61563 | 4 Solución en espera de ser aprobada |  | 2022-03-15
MTS | Meth | Q321005654-1 | STANDARD | 2021-03-23 | SGX965A | SGX965A |  | G02490961-103 | SUPPORT, PANEL SERVICE LIGHTS, AFT FUSE |  | SI | RFC | 61563 | 4 Solución en espera de ser aprobada |  | 2022-03-15
MTS |  | Q321005710-1 | STANDARD | 2021-03-23 | SGX900A | SGX900A |  | G05211418-101 | PLATE, HINGE STEP, PASS ACS DR | SI | SI | RFC |  | 3 Causa Raiz detectada
Zone 1 | Meth | Q321004298-1 | STANDARD | 2021-03-03 | AGX738 | AGX738 | 70096 | G05291600-001 | ELECTRICAL INSTL, CARGO ACCESS DR |  | SI |  |  | 3 Causa Raiz detectada |  |  | Query Generado solicitando el RFC despues de 4 RNC's seguidos como es solicitado #4450 & #4411 (23-Apr)
Zone 1 | Meth | Q321004546-1 | TECHNICAL | 2021-03-05 | AGX744 | AGX744 | 70104 | G05372390-001 | ECS INSTL CPCS PROVISION REAR FUSE | Yes | SI | RFC | PCR 61582 | 4 Solución en espera de ser aprobada |  |  | Query Generado solicitando el RFC #3356
Zone 1 | Meth | Q321004552-1 | TECHNICAL | 2021-03-05 | AGX744AA | AGX744AA | 70104 | G05372390-001 | ECS INSTL CPCS PROVISION REAR FUSE | Yes | SI | RFC | PCR 61582 | 4 Solución en espera de ser aprobada |  |  | Query Generado solicitando el RFC #3356
Zone 1 | Meth | Q321004779-1 | STANDARD | 2021-03-10 | AGX738 | AGX738 | 70097 | G05291600-001 | ELECTRICAL INSTL, CARGO ACCESS DR |  | SI |  |  | 3 Causa Raiz detectada |  |  | Query Generado solicitando el RFC despues de 4 RNC's seguidos como es solicitado #4450 & #4411 (23-Apr)
Zone 1 | METH | Q321004925-1 | STANDARD | 2021-03-11 | AGX744AA | AGX744AA | 70105 | G05372390-001 | ECS INSTL CPCS PROVISION REAR FUSE | Yes | SI | RFC | PCR 61582 | 4 Solución en espera de ser aprobada |  |  | Query Generado solicitando el RFC #3356
Zone 1 |  | Q321005236-1 | STANDARD | 2021-03-17 | AGX290 | AGX290 | 70105 | G05310750-001-01 | COCKPIT NOSE ASSY
Zone 1 |  | Q321005236-2 | STANDARD | 2021-03-17 | AGX290 | AGX290 | 70105 | G05310750-001-01 | COCKPIT NOSE ASSY | [8 empty] | 3508
Zone 1 |  | Q321005236-3 | STANDARD | 2021-03-17 | AGX290 | AGX290 | 70105 | G05310750-001-01 | COCKPIT NOSE ASSY | [8 empty] | 2560
Zone 1 |  | Q321005236-4 | STANDARD | 2021-03-17 | AGX290 | AGX290 | 70105 | G05310750-001-01 | COCKPIT NOSE ASSY | [8 empty] | 2560
Zone 1 | Meth | Q321005418-1 | STANDARD | 2021-03-19 | AGX738 | AGX738 | 70098 | G05291600-001 | ELECTRICAL INSTL, CARGO ACCESS DR |  | SI |  |  | 3 Causa Raiz detectada |  |  | Query Generado solicitando el RFC despues de 4 RNC's seguidos como es solicitado #4450 & #4411 (23-Apr) | 2756
Zone 1 |  | Q321005551-1 | STANDARD | 2021-03-22 | AGX744AA | AGX744AA | 70106 | G05372390-001 | ECS INSTL CPCS PROVISION REAR FUSE | yes | SI | RFC | PCR 61582 | 4 Solución en espera de ser aprobada |  |  | Query Generado solicitando el RFC #3356 | 2560
Zone 1 | Meth | Q321005858-1 | STANDARD | 2021-03-25 | AGX738 | AGX738 | 70099 | G05291600-001 | ELECTRICAL INSTL, CARGO ACCESS DR |  | SI |  |  | 3 Causa Raiz detectada |  |  | Query Generado solicitando el RFC despues de 4 RNC's seguidos como es solicitado #4450 & #4411 (23-Apr) | 2560
Zone 2 | Meth | Q321004197-1 | STANDARD | 2021-03-02 | AGX890AA | AGX890AA | 70101 | G05530400-007-01 | STRAP ASSY, FRONT SPAR, VSTAB | No | SI |  |  | 3 Causa Raiz detectada |  |  | QUERY 4126/ Waiting RFC 26 May
Zone 2 | Meth | Q321004197-2 | STANDARD | 2021-03-02 | AGX890AA | AGX890AA | 70101 | G05530400-008-01 | STRAP ASSY, FRONT SPAR, VSTAB | No | SI |  |  | 3 Causa Raiz detectada |  |  | QUERY 4126/ Waiting RFC 26 May
Zone 2 | Meth | Q321004653-1 | STANDARD | 2021-03-08 | AGX880AA | AGX880AA | 70103 | G05530119-003 | SKIN INSTL, VSTAB, LH | No | SI |  |  | 3 Causa Raiz detectada |  |  | QUERY 4218/ Waiting RFC 28 May
Zone 2 | Meth | Q321004660-1 | STANDARD | 2021-03-09 | AGX890AA | AGX890AA | 70102 | G05530400-007-01 | STRAP ASSY, FRONT SPAR, VSTAB | No | SI |  |  | 3 Causa Raiz detectada |  |  | QUERY 4126/ Waiting RFC 26 May
Zone 2 | Meth | Q321004660-2 | STANDARD | 2021-03-09 | AGX890AA | AGX890AA | 70102 | G05530400-008-01 | STRAP ASSY, FRONT SPAR, VSTAB | No | SI |  |  | 3 Causa Raiz detectada |  |  | QUERY 4126/ Waiting RFC 26 May
Zone 2 | Meth | Q321004660-1 | STANDARD | 2021-03-09 | AGX890AA | AGX890AA | 70102 | G05530400-009-01 | STRAP ASSY, FRONT SPAR, VSTAB | No | SI |  |  | 3 Causa Raiz detectada |  |  | QUERY 4126/ Waiting RFC 26 May
Zone 2 | Meth | Q321004660-2 | STANDARD | 2021-03-09 | AGX890AA | AGX890AA | 70102 | G05530400-008-01 | STRAP ASSY, FRONT SPAR, VSTAB | No | SI |  |  | 3 Causa Raiz detectada |  |  | QUERY 4126/ Waiting RFC 26 May
Zone 2 | Meth | Q321004681-1 | STANDARD | 2021-03-09 | AGX890AA | AGX890AA | 70102 | G05530400-010-01 | STRAP ASSY, FRONT SPAR, VSTAB | No | SI |  |  | 3 Causa Raiz detectada |  |  | QUERY 4126/ Waiting RFC 26 May
Zone 2 | Meth | Q321005128-1 | STANDARD | 2021-03-16 | AGX890AA | AGX890AA | 70103 | G05530400-010-01 | STRAP ASSY, FRONT SPAR, VSTAB | No | SI |  |  | 3 Causa Raiz detectada |  |  | QUERY 4126/ Waiting RFC 26 May
Zone 2 | Meth | Q321005130-1 | STANDARD | 2021-03-16 | AGX890AA | AGX890AA | 70103 | G05530400-009-01 | STRAP ASSY, FRONT SPAR, VSTAB | No | SI |  |  | 3 Causa Raiz detectada |  |  | QUERY 4126/ Waiting RFC 26 May
Zone 2 | Meth | Q321005147-1 | STANDARD | 2021-03-16 | AGX880AA | AGX880AA | 70103 | G05363136-007-01 | FRAME ASSY, AFT ENG MOUNT | Yes | SI | COS | G05363136-009-01 | 4 Solución en espera de ser aprobada |  | 70120
Zone 2 |  | Q321005169-1 | EXTENSION | 2021-03-17 | AGX890AA |  | 70104 | G05530400-009-01 | STRAP ASSY, FRONT SPAR, VSTAB | No | SI |  |  | 3 Causa Raiz detectada |  |  | QUERY 4126/ Waiting RFC 26 May
Zone 2 |  | Q321005170-1 | EXTENSION | 2021-03-17 | AGX890AA |  | 70105 | G05530400-009-01 | STRAP ASSY, FRONT SPAR, VSTAB | No | SI |  |  | 3 Causa Raiz detectada |  |  | QUERY 4126/ Waiting RFC 26 May
Zone 2 |  | Q321005171-1 | EXTENSION | 2021-03-17 | AGX890AA |  | 70106 | G05530400-009-01 | STRAP ASSY, FRONT SPAR, VSTAB | No | SI |  |  | 3 Causa Raiz detectada |  |  | QUERY 4126/ Waiting RFC 26 May
Zone 2 |  | Q321005172-1 | EXTENSION | 2021-03-17 | AGX890AA |  | 70107 | G05530400-009-01 | STRAP ASSY, FRONT SPAR, VSTAB | No | SI |  |  | 3 Causa Raiz detectada |  |  | QUERY 4126/ Waiting RFC 26 May
Zone 2 |  | Q321005173-1 | EXTENSION | 2021-03-17 | AGX890AA |  | 70108 | G05530400-009-01 | STRAP ASSY, FRONT SPAR, VSTAB | No | SI |  |  | 3 Causa Raiz detectada |  |  | QUERY 4126/ Waiting RFC 26 May
Zone 2 |  | Q321005209-1 | STANDARD | 2021-03-17 | AGX880AA | AGX880AA | 70104 | G05530119-003 | SKIN INSTL, VSTAB, LH | No | SI |  |  | 3 Causa Raiz detectada |  |  | QUERY 4126/ Waiting RFC 26 May
Zone 2 |  | Q321005210-1 | EXTENSION | 2021-03-17 | AGX890AA |  | 70104 | G05530400-010-01 | STRAP ASSY, FRONT SPAR, VSTAB | No | SI |  |  | 3 Causa Raiz detectada |  |  | QUERY 4126/ Waiting RFC 26 May
Zone 2 |  | Q321005211-1 | EXTENSION | 2021-03-17 | AGX890AA |  | 70105 | G05530400-010-01 | STRAP ASSY, FRONT SPAR, VSTAB | No | SI |  |  | 3 Causa Raiz detectada |  |  | QUERY 4126/ Waiting RFC 26 May
Zone 2 |  | Q321005212-1 | EXTENSION | 2021-03-17 | AGX890AA |  | 70106 | G05530400-010-01 | STRAP ASSY, FRONT SPAR, VSTAB | No | SI |  |  | 3 Causa Raiz detectada |  |  | QUERY 4126/ Waiting RFC 26 May
Zone 2 |  | Q321005213-1 | EXTENSION | 2021-03-17 | AGX890AA |  | 70107 | G05530400-010-01 | STRAP ASSY, FRONT SPAR, VSTAB | No | SI |  |  | 3 Causa Raiz detectada |  |  | QUERY 4126/ Waiting RFC 26 May
Zone 2 |  | Q321005214-1 | EXTENSION | 2021-03-17 | AGX890AA |  | 70108 | G05530400-010-01 | STRAP ASSY, FRONT SPAR, VSTAB | No | SI |  |  | 3 Causa Raiz detectada |  |  | QUERY 4126/ Waiting RFC 26 May
Zone 2 |  | Q321005220-1 | STANDARD | 2021-03-17 | AGX870AA | AGX890AA | 70103 | G05363136-007-01 | FRAME ASSY, AFT ENG MOUNT | Yes | SI | COS | G05363136-009-01 | 4 Solución en espera de ser aprobada |  | 70120
Zone 3.1 | Meth | Q321004139-1 | STANDARD | 2021-03-01 | AGX810 | AGX810 | 70102 | G05362822-101-01 | SPLICE, FRAME, AFT FUSE | NO
Zone 3.1 | Meth | Q321004294-1 | STANDARD | 2021-03-03 | AGX810AA | AGX810AA | 70103 | G05360040-001 | FLOOR INSTL | No | [6 empty] | Under investigation PSS 034
Zone 3.1 | Meth | Q321004294-2 | STANDARD | 2021-03-03 | AGX810AA | AGX810AA | 70103 | G05360040-001 | FLOOR INSTL | No | [6 empty] | under investigation PSS 034
Zone 3.1 | Meth | Q321004303-1 | STANDARD | 2021-03-03 | AGX810 | AGX810AA | 70102 | G05360010-003 | BARREL ASSY, FWD, AFT FUSE | No | [6 empty] | Should be supplier
Zone 3.1 | Meth | Q321004308-1 | STANDARD | 2021-03-03 | AGX810 | AGX810AA | 70102 | G05360010-003 | BARREL ASSY, FWD, AFT FUSE | NO | [6 empty] | Should be supplier
Zone 3.1 | Meth | Q321004308-2 | STANDARD | 2021-03-03 | AGX810 | AGX810AA | 70102 | G05360010-003 | BARREL ASSY, FWD, AFT FUSE | NO | [6 empty] | Should be supplier
Zone 3.1 | Meth | Q321004567-1 | TECHNICAL | 2021-03-05 | AGX810AA | AGX810AA | 70103 | G05362084-101 | CLEAT, AFT FUSE | NO | SI | COS | QUERY 4416 | 3 Causa Raiz detectada |  | 2021-04-14
Zone 3.1 | Meth | Q321004716-1 | STANDARD | 2021-03-09 | AGX802AA | AGX802AA | 70103 | G05372102-003 | ECS INSTL TRIM AIR PROVISIONS | No | [6 empty] | Under investigation
Zone 3.1 | Meth | Q321004980-1 | STANDARD | 2021-03-12 | AGX804AA | AGX804AA | 70105 | G05363534-113 | FRAME, FRONT SPAR, REAR FUSE | yes |  |  | Visual AID | 1 Problema detectado
Zone 3.1 | Meth | Q321004984-1 | STANDARD | 2021-03-12 | AGX806AA | AGX806AA | 70104 | G05372140-005 | BRACKET ASSY APS REAR FUSE | NO | NO | RFC | Query 4442 | 1 Problema detectado
Zone 3.1 | Meth | Q321004999-1 | STANDARD | 2021-03-12 | AGX810 | AGX810AA | 70103 | G05360010-003 | BARREL ASSY, FWD, AFT FUSE | no |  |  | S/be Supplier
Zone 3.1 | Meth | Q321005062-1 | STANDARD | 2021-03-13 | AGX810 | AGX810 | 70104 | G05360040-001 | FLOOR INSTLALLATION, REAR FUSE | no |  |  | Supplier
Zone 3.1 | Meth | Q321005331-1 | STANDARD | 2021-03-18 | AGX802AA | AGX802AA | 70104 | G05372102-003 | ECS INSTL TRIM AIR PROVISIONS | No | [5 empty] | Under investigation
Zone 3.1 | Meth | Q321005382-1 | STANDARD | 2021-03-19 | AGX810 | AGX810AA | 70104 | G05366015-101 | FITTING, FWD ENGINE FRAME | no |  |  | no |  |  |  | Under investigation (location of cleat need to be validate)
Zone 3.1 | Meth | Q321005387-1 | STANDARD | 2021-03-19 | AGX810 | AGX810AA | 70104 | G05360010-003 | BARREL ASSY, FWD, AFT FUSE | no |  |  | no |  |  |  | Should be supplier
Zone 3.1 |  | Q321005509-1 | STANDARD | 2021-03-22 | AGX810 | AGX810AA | 70104 | G05360010-003 | BARREL ASSY, FWD, AFT FUSE | NO | NO | [5 empty] | Should be supplier
Zone 3.1 |  | Q321005509-2 | STANDARD | 2021-03-22 | AGX810 | AGX810AA | 70104 | G05360010-003 | BARREL ASSY, FWD, AFT FUSE | NO | NO | [5 empty] | Should be supplier
Zone 3.1 |  | Q321005509-3 | STANDARD | 2021-03-22 | AGX810 | AGX810AA | 70104 | G05360010-003 | BARREL ASSY, FWD, AFT FUSE | NO | NO | [5 empty] | Should be supplier
Zone 3.1 |  | Q321005573-1 | STANDARD | 2021-03-22 | AGX810AA | AGX810AA | 70105 | G05360040-001 | FLOOR INSTL | NO | NO | [5 empty] | Should be supplier
Zone 3.1 |  | Q321005573-2 | STANDARD | 2021-03-22 | AGX810AA | AGX810AA | 70105 | G05360040-001 | FLOOR INSTL | NO | SI |  |  | 3 Causa Raiz detectada | 34 |  | under investigation PSS 034
Zone 3.1 | Meth | Q321005831-1 | STANDARD | 2021-03-25 | AGX810AA | AGX810AA | 70105 | G05360010-003 | BARREL ASSY, FWD, AFT FUSE | NO | NO |  |  | 1 Problema detectado |  |  | Should be supplier
Zone 3.1 | Meth | Q321005831-2 | STANDARD | 2021-03-25 | AGX810AA | AGX810AA | 70105 | G05360010-003 | BARREL ASSY, FWD, AFT FUSE | NO | NO |  |  | 1 Problema detectado |  |  | Should be supplier
Zone 3.2 | Meth | Q321004358-1 | STANDARD | 2021-03-03 | AGX830AA | AGX830AA | 70102 | G05360045-001 | TANK INSTL, FUEL, REAR FUSE
Zone 3.2 | Meth | Q321004631-1 | STANDARD | 2021-03-08 | AGX830AA | AGX830AA | 70101 | G05364600-001 | FLOOR INSTL, FUEL TANK, REAR FUSE |  |  |  | COS
Zone 3.2 | Meth | Q321004730-1 | STANDARD | 2021-03-09 | AGX830AA | AGX830AA | 70098 | G05364500-001-01 | STRUCTURE ASSY, FUEL TANK, REAR FUSE
Zone 3.2 | Meth | Q321004839-1 | STANDARD | 2021-03-10 | AGX830AA | AGX830AA | 70101 | G02193000-001 | CPCS TUBE UNDER FUEL TANK INSTLN
Zone 3.2 | METH | Q321004916-1 | SNC | 2021-03-11 | AGX830AA | AGX830AA | 70102 | G05372801-001 | FUEL INSTL, PROV, FWD FS897 | YES |  |  | Query 4340 |  |  | FAI | Missing operations
Zone 3.2 | METH | Q321004918-1 | EXTENSION | 2021-03-11 | AGX830AA | AGX830AA | 70103 | G05372801-001 | FUEL INSTL, PROV, FWD FS897 | YES |  |  | Query 4340 |  |  | FAI | Missing operations
Zone 3.2 | METH | Q321004919-1 | EXTENSION | 2021-03-11 | AGX830AA | AGX830AA | 70104 | G05372801-001 | FUEL INSTL, PROV, FWD FS897 | YES |  |  | Query 4340 |  |  | FAI | Missing operations
Zone 3.2 | METH | Q321004920-1 | EXTENSION | 2021-03-11 | AGX830AA | AGX830AA | 70105 | G05372801-001 | FUEL INSTL, PROV, FWD FS897 | YES |  |  | Query 4340 |  |  | FAI | Missing operations
Zone 3.2 | METH | Q321004921-1 | SNC | 2021-03-11 | AGX830AA | AGX830AA | 70101 | G05372801-001 | FUEL INSTL, PROV, FWD FS897 | YES |  |  | Query 4340 |  |  | FAI | Missing operations
Zone 3.2 | Meth | Q321004970-1 | EXTENSION | 2021-03-12 | AGX830AA |  | 70101 | G02193000-001 | CPCS TUBE UNDER FUEL TANK INSTLN
Zone 3.2 | Meth | Q321004971-1 | EXTENSION | 2021-03-12 | AGX830AA |  | 70102 | G02193000-001 | CPCS TUBE UNDER FUEL TANK INSTLN
Zone 3.2 | Meth | Q321004972-1 | EXTENSION | 2021-03-12 | AGX830AA |  | 70103 | G02193000-001 | CPCS TUBE UNDER FUEL TANK INSTLN
Zone 3.2 | Meth | Q321004973-1 | EXTENSION | 2021-03-12 | AGX830AA |  | 70104 | G02193000-001 | CPCS TUBE UNDER FUEL TANK INSTLN
Zone 3.2 | Meth | Q321004974-1 | EXTENSION | 2021-03-12 | AGX830AA |  | 70105 | G02193000-001 | CPCS TUBE UNDER FUEL TANK INSTLN
Zone 3.2 | Meth | Q321004975-1 | EXTENSION | 2021-03-12 | AGX830AA |  | 70106 | G02193000-001 | CPCS TUBE UNDER FUEL TANK INSTLN
Zone 3.2 | Meth | Q321004976-1 | EXTENSION | 2021-03-12 | AGX830AA |  | 70107 | G02193000-001 | CPCS TUBE UNDER FUEL TANK INSTLN
Zone 3.2 | Meth | Q321004977-1 | EXTENSION | 2021-03-12 | AGX830AA |  | 70108 | G02193000-001 | CPCS TUBE UNDER FUEL TANK INSTLN
Zone 3.2 | Meth | Q321004978-1 | EXTENSION | 2021-03-12 | AGX830AA |  | 70109 | G02193000-001 | CPCS TUBE UNDER FUEL TANK INSTLN
Zone 3.2 | Meth | Q321004979-1 | EXTENSION | 2021-03-12 | AGX830AA |  | 70110 | G02193000-001 | CPCS TUBE UNDER FUEL TANK INSTLN
Zone 3.2 | Meth | Q321005154-1 | STANDARD | 2021-03-16 | AGX820AA | AGX820AA | 70103 | G05364510-001 | CELL INSTL, FLEXIBLE, AFT FUEL TANK
Zone 3.2 | Meth | Q321005374-1 | STANDARD | 2021-03-19 | AGX830AA | AGX830AA | 70099 | G05364500-001-01 | STRUCTURE ASSY, FUEL TANK, REAR FUSE
Zone 3.2 | Meth | Q321005374-1 | STANDARD | 2021-03-19 | AGX830AA | AGX830AA | 70099 | G05364500-001-01 | STRUCTURE ASSY, FUEL TANK, REAR FUSE
Zone 3.2 | Meth | Q321005374-1 | STANDARD | 2021-03-19 | AGX830AA | AGX830AA | 70099 | G05364500-001-01 | STRUCTURE ASSY, FUEL TANK, REAR FUSE
Zone 3.2 | Meth | Q321005486-1 | SNC | 2021-03-19 | AGX830AA | AGX830AA | 70100 | G05372104-001 | ECS INSTL, PACK PROVISION, REAR FUSE
Zone 3.2 | Meth | Q321005488-1 | SNC | 2021-03-20 | AGX830AA | AGX830AA | 70101 | G05372104-001 | ECS INSTL, PACK PROVISION, REAR FUSE
Zone 3.2 | Meth | Q321005489-1 | SNC | 2021-03-20 | AGX830AA | AGX830AA | 70102 | G05372104-001 | ECS INSTL, PACK PROVISION, REAR FUSE
Zone 3.2 | Meth | Q321005490-1 | SNC | 2021-03-20 | AGX830AA | AGX830AA | 70103 | G05372104-001 | ECS INSTL, PACK PROVISION, REAR FUSE
Zone 3.2 |  | Q321005639-1 | STANDARD | 2021-03-22 | AGX830AA | AGX830AA | 70099 | G05364510-001 | CELL INSTL, FLEXIBLE, AFT FUEL TANK
Zone 3.2 |  | Q321005759-1 | STANDARD | 2021-03-24 | AGX830 | AGX830 | 70103 | G05372226-001 | BRACKET ASSY, LP SYSTEM
Zone 3.2 | Meth | Q321005860-1 | STANDARD | 2021-03-25 | AGX830AA | AGX830AA | 70102 | G02193000-001 | CPCS TUBE UNDER FUEL TANK INSTLN
Zone 3.3 | Meth | Q321004198-1 | STANDARD | 2021-03-02 | AGX950AA | AGX950AA | 70098 | G05379184-101 | BRACKET, GROUND
Zone 3.3 | Meth | Q321004247-1 | STANDARD | 2021-03-02 | AGX950 | AGX950 | 70100 | G05363447-106 | SPLICE, REAR SPAR, AFT BARREL | NO |  |  | - |  |  | - | BARRENOS OLONGADOS/CAUSA: ACCESO/SE REVISARA EL EN EL SIGUEINTE AVION 102 OTRA ESTRATEGIA DE PASAR ESOS BARRENOS PARA EVITAR QUE SALGAN HOLONGADOS
Zone 3.3 | Meth | Q321004279-1 | STANDARD | 2021-03-02 | AGX950 | AGX950 | 70098 | G02100001-001 | DUCT, RAM AIR | SI | [5 empty] | 70106 | CSD-G05361000-003-0019 CREATED (CSD PARA MOVER EL FITTING DE PLANTA 1001 A 1503 AL WBK GX830110045)
Zone 3.3 | Meth | Q321004523-1 | TECHNICAL | 2021-03-05 | AGX950 | AGX950 | 70101 | G05363921-003 | JOINT INSTL, STA 1016, REAR FUSE | NO |  |  | - |  |  | - | GAP EXCESIVO/CAUSA:UNION Y ALINEACION JOINING AGX950) "CRUCI FORM"
Zone 3.3 | Meth | Q321004523-2 | TECHNICAL | 2021-03-05 | AGX950 | AGX950 | 70101 | G05530215-101 | ANGLE, FRONT SPAR, VSTAB | NO |  |  | - |  |  | - | GAP EXCESIVO/CAUSA:UNION Y ALINEACION JOINING AGX950) "ANGLE, FRONT SPAR"
Zone 3.3 | Meth | Q321004818-1 | STANDARD | 2021-03-10 | AGX950 | AGX950 | 70101 | G05530213-106-01 | FITTING, INTERFACE, FRONT SPAR, VS
Zone 3.3 | METH | Q321004862-1 | STANDARD | 2021-03-11 | AGX950 | AGX950 | 70096 | G05530170-001 | FAIRING INSTL, DORSAL
Zone 3.3 | METH | Q321004883-1 | STANDARD | 2021-03-11 | AGX950 | AGX950 | 70098 | G05530170-001 | FAIRING INSTL, DORSAL
Zone 3.3 | METH | Q321004887-1 | STANDARD | 2021-03-11 | AGX950 | AGX950 | 70097 | G05530170-001 | FAIRING INSTL, DORSAL
Zone 3.3 | METH | Q321004934-1 | STANDARD | 2021-03-11 | AGX950AA | AGX950AA | 70101 | G02100001-001 | DUCT, RAM AIR
Zone 3.3 | METH | Q321004941-1 | STANDARD | 2021-03-11 | AGX950 | AGX950 | 70101 | G05363133-003 | PANEL ASSY, SIDE LH, BARREL, REAR FUSE
Zone 3.3 | METH | Q321004941-2 | STANDARD | 2021-03-11 | AGX950 | AGX950 | 70101 | G05363142-003 | PANEL ASSY, SIDE RH, BARREL, REAR FUSE
Zone 3.3 | Meth | Q321004990-1 | STANDARD | 2021-03-12 | AGX950AA | AGX950AA | 70101 | G05363921-001 | JOINT INSTL, STA 1016, REAR FUSE | YES | [6 empty] | MANUFACTURE FITTING BY JOINING
Zone 3.3 | Meth | Q321004990-2 | STANDARD | 2021-03-12 | AGX950AA | AGX950AA | 70101 | G05363921-001 | JOINT INSTL, STA 1016, REAR FUSE | YES | [6 empty] | MANUFACTURE FITTING BY JOINING
Zone 3.3 | Meth | Q321005029-1 | STANDARD | 2021-03-12 | AGX950 | AGX950 | 70101 | G05363500-101 | STRAP, REAR SPAR, AFT BARREL, TOP
Zone 3.3 | Meth | Q321005088-1 | STANDARD | 2021-03-16 | AGX950 | AGX950 | 70099 | G05530170-001 | FAIRING INSTL, DORSAL | NO | [6 empty] | BY POSITION
Zone 3.3 |  | Q321005184-1 | STANDARD | 2021-03-17 | AGX950AA | AGX950AA | 70102 | G05530213-106 | FITTING, INTERFACE, FRONT SPAR, VS | YES |  |  | QUERY 4475 (RFC) |  |  | TBD
Zone 3.3 | Meth | Q321005298-1 | STANDARD | 2021-03-18 | AGX950 | AGX950 | 70100 | G05530170-001 | FAIRING INSTL, DORSAL
Zone 3.3 |  | Q321005663-1 | STANDARD | 2021-03-23 | AGX950 | AGX950 | 70102 | G05363921-003 | JOINT INSTL, STA 1016, REAR FUSE
Zone 3.3 |  | Q321005707-1 | STANDARD | 2021-03-23 | AGX950 | AGX950 | 70102 | G02100001-001 | DUCT, RAM AIR
Zone 3.4 | Meth | Q321004173-1 | STANDARD | 2021-03-01 | AGX952 | AGX952 | 70099 | G05450410-102 | STIFFENER, CTR BOX, PYLON | YES | SI | COS | 4470 | 4 Solución en espera de ser aprobada |  | 2021-04-30 | New COS for skin G05450061-004-04
Zone 3.3 | Meth | Q321005854-1 | STANDARD | 2021-03-25 | AGX950 | AGX950 | 70102 | G05530170-001 | FAIRING INSTL, DORSAL | NO
Zone 3.4 | Meth | Q321004173-2 | STANDARD | 2021-03-01 | AGX952 | AGX952 | 70099 | G05450439-102 | STIFFENER, CTR BOX, PYLON | YES | SI | COS | 4470 | 4 Solución en espera de ser aprobada |  | 2021-04-30 | New COS for skin G05450062-010-02
Zone 3.4 | Meth | Q321004126-1 | EXTENSION | 2021-03-01 | AGX952 |  | 70098 | G05379403-101 | BRACKET, GROUND
Zone 3.4 | Meth | Q321004127-1 | EXTENSION | 2021-03-01 | AGX952 |  | 70099 | G05379403-101 | BRACKET, GROUND
Zone 3.4 | Meth | Q321004128-1 | EXTENSION | 2021-03-01 | AGX952 |  | 70100 | G05379403-101 | BRACKET, GROUND
Zone 3.4 | Meth | Q321004129-1 | EXTENSION | 2021-03-01 | AGX952 |  | 70101 | G05379403-101 | BRACKET, GROUND
Zone 3.4 | TOOL CRIB | Q321004173-3 | STANDARD | 2021-03-01 | AGX952 | AGX952 | 70099 | G05450502-104 | SKIN, UPPER, CTR BOX, PYLON
Zone 3.4 | TOOL CRIB | Q321004173-4 | STANDARD | 2021-03-01 | AGX952 | AGX952 | 70099 | G05450503-104 | SKIN , LWR, CTR BOX, PYLON
Zone 3.4 | Meth | Q321004204-1 | STANDARD | 2021-03-02 | AGX952 | AGX952 | 70099 | G05450502-104 | SKIN, UPPER, CTR BOX, PYLON | Yes | SI | COS | 2560 | 5 Monitoreo y mejora |  | 70102-X | New COS for drag angle G05450606-102-04
Zone 3.4 | Meth | Q321004204-2 | STANDARD | 2021-03-02 | AGX952 | AGX952 | 70099 | G05450605-102-03 | ANGLE, DRAG, CTR BOX, PYLON | Yes | SI | COS | 4402 | 4 Solución en espera de ser aprobada |  | TBD | New COS for drag angle G05450605-102
Zone 3.4 | Meth | Q321004233-1 | STANDARD | 2021-03-02 | AGX952 | AGX952 | 70098 | G05450073-002-01 | TE INSTL, PYLON | Yes | SI | COS | 2756 | 4 Solución en espera de ser aprobada |  | 70105-X | New COS for rib G05450363-104-06
Zone 3.4 | Meth | Q321004289-1 | STANDARD | 2021-03-02 | AGX952 | AGX952 | 70099 | G05450620-104 | FITTING, TENSION, FIXED LE, PYLON | Yes | SI | COS | 2560 | 4 Solución en espera de ser aprobada |  | 70105-X | New COS for fitting G05450379-102-03
Zone 3.4 | Meth | Q321004289-2 | STANDARD | 2021-03-02 | AGX952 | AGX952 | 70099 | G05450621-104 | FITTING, TENSION, FIXED LE, PYLON | Yes | SI | COS | 2560 | 5 Monitoreo y mejora |  | 70101-X | New COS for fitting G05450376-102-03
Zone 3.4 | Meth | Q321004204-3 | STANDARD | 2021-03-03 | AGX952 | AGX952 | 70099 | G05450605-102 | ANGLE, DRAG, CTR BOX, PYLON | Yes | SI | COS | 2560 | 4 Solución en espera de ser aprobada |  | 70109-X | New COS for drag angle G05450605-102-05
Zone 3.4 | Meth | Q321004302-3 | STANDARD | 2021-03-03 | AGX952 | AGX952 | 70099 | G05450606-101 | ANGLE, DRAG, CTR BOX, PYLON | Yes | SI | COS | 2560 | 4 Solución en espera de ser aprobada |  | 70108-X | New COS for drag angle G05450606-101-04
Zone 3.4 | Meth | Q321004545-1 | TECHNICAL | 2021-03-05 | AGX945 | AGX945 | 70102 | G05450051-007 | LE ASSY FIXED PYLON | YES | SI | COS | 4183 | 4 Solución en espera de ser aprobada |  | TBD | Double hole due to workaround to fix problem with new COS for LE
Zone 3.4 | meth | Q321004553-1 | TECHNICAL | 2021-03-05 | AGX952AA | AGX952AA | 70098 | G05450057-N0013 | TE ASSY, REMOVABLE, PYLON | YES | SI | COS | 3274 | 4 Solución en espera de ser aprobada |  | 70112-X | New COS for G05450508-107-02 70112-X & G05450509-107-02 70130-X
Zone 3.4 | Meth | Q321004583-1 | TECHNICAL | 2021-03-05 | AGX952AA | AGX952AA | 70098 | G05450059-007 | PANEL ASSY, CTR BOX, PYLON | YES | SI | COS | 3274 | 4 Solución en espera de ser aprobada |  | 70150-X | New COS G05450511-105-02
Zone 3.4 | Meth | Q321004583-2 | TECHNICAL | 2021-03-05 | AGX952AA | AGX952AA | 70098 | G05450058-N0005 | PANEL ASSY, CTR BOX, PYLON | YES | SI | COS | 3274 | 4 Solución en espera de ser aprobada |  | 70108-X | New COS G05450510-105-02
Zone 3.4 | Meth | Q321004583-4 | TECHNICAL | 2021-03-05 | AGX952AA | AGX952AA | 70098 | G05450055-N0003 | PANEL ASSY, CTR BOX, PYLON | YES | SI | COS | 3274 | 4 Solución en espera de ser aprobada |  | 70110-X | New COS G05450505-105-02
Zone 3.4 | meth | Q321004586-1 | TECHNICAL | 2021-03-05 | AGX952AA | AGX952AA | 70098 | G05450052-005 | LE ASSY , REMOVABLE, PYLON | YES | SI | COS | 3274 | 4 Solución en espera de ser aprobada |  | 70109-X | New COS G05450501-105-03
Zone 3.4 | Meth | Q321004609-1 | STANDARD | 2021-03-08 | AGX952 | AGX952 | 70100 | G05450225-101-02 | ANGLE, FIXED LE, PYLON | NO | SI | COS |  | 3 Causa Raiz detectada
Zone 3.4 | Meth | Q321004609-2 | STANDARD | 2021-03-08 | AGX952 | AGX952 | 70100 | G05450606-101-03 | ANGLE, DRAG, CTR BOX, PYLON | NO | SI |  |  | 2 Análisis en Proceso
Zone 3.4 | Meth | Q321004673-1 | STANDARD | 2021-03-09 | AGX948 | AGX948 | 70101 | G05450056-010-01 | TE ASSY, FIXED, PYLON
Zone 3.4 | Meth | Q321004689-1 | STANDARD | 2021-03-09 | AGX952 | AGX952 | 70100 | G05450502-104 | SKIN, UPPER, CTR BOX, PYLON
Zone 3.4 | Meth | Q321004689-5 | STANDARD | 2021-03-09 | AGX952 | AGX952 | 70100 | G05450439-102 | STIFFENER, CTR BOX, PYLON
Zone 3.4 | Meth | Q321004689-6 | STANDARD | 2021-03-09 | AGX952 | AGX952 | 70100 | G05450410-102 | STIFFENER, CTR BOX, PYLON
Zone 3.4 | Meth | Q321004689-8 | STANDARD | 2021-03-09 | AGX952 | AGX952 | 70100 | G05450075-002 | BOX INSTL, CENTER PYLON
Zone 3.4 | Meth | Q321004689-9 | STANDARD | 2021-03-09 | AGX952 | AGX952 | 70100 | G05450062-010 | SKIN ASSY, LWR, CTR BOX, PYLON
Zone 3.4 | Meth | Q321004733-1 | STANDARD | 2021-03-09 | AGX952 | AGX952 | 70100 | G05450484-102-02 | FITTING, CTR BOX, PYLON
Zone 3.4 | Meth | Q321004744-1 | STANDARD | 2021-03-09 | AGX952 | AGX952 | 70100 | G05450620-104 | FITTING, TENSION, FIXED LE, PYLON
Zone 3.4 | Meth | Q321004744-2 | STANDARD | 2021-03-09 | AGX952 | AGX952 | 70100 | G05450621-104 | FITTING, TENSION, FIXED LE, PYLON
Zone 3.4B | Meth | Q321004748-1 | STANDARD | 2021-03-09 | AGX952 | AGX952B | 70099 | G05370026-001-01 | FIDEX INSTL, PROVISIONS, REAR FUSE
Zone 3.4 | Meth | Q321004760-1 | STANDARD | 2021-03-10 | AGX952AA | AGX952AA | 70100 | G05362000-003 | PANEL ASSY, LH, AFT FUSE
Zone 3.4 | Meth | Q321004760-1 | STANDARD | 2021-03-10 | AGX952AA | AGX952AA | 70100 | G05362000-003 | PANEL ASSY, LH, AFT FUSE
Zone 3.4 | Meth | Q321004777-1 | STANDARD | 2021-03-10 | AGX952 | AGX952 | 70100 | G05450606-101-02 | ANGLE, DRAG, CTR BOX, PYLON
Zone 3.4 | Meth | Q321004807-1 | STANDARD | 2021-03-10 | AGX952 | AGX952 | 70099 | G05450073-001-01 | TE INSTL, PYLON
Zone 3.4 | Meth | Q321004826-1 | STANDARD | 2021-03-10 | AGX944 | AGX944 | RR096 | G05450204-102-03 | STIFFENER, FIXED LE, PYLON
Zone 3.4 | Meth | Q321004850-1 | STANDARD | 2021-03-10 | AGX952AA | AGX952AA | 70099 | G05450612-103-02 | ANGLE, DRAG, FIXED TE, PYLON
Zone 3.4 | Meth | Q321004852-1 | STANDARD | 2021-03-10 | AGX952AA | AGX952AA | 70098 | G05363449-101 | DOUBLER SIDE PANEL AFT BARREL
Zone 3.4 | Meth | Q321004852-2 | STANDARD | 2021-03-10 | AGX952AA | AGX952AA | 70098 | G05450606-101-03 | ANGLE, DRAG, CTR BOX, PYLON
Zone 3.4 | Meth | Q321004852-3 | STANDARD | 2021-03-10 | AGX952AA | AGX952AA | 70098 | G05450606-101-03 | ANGLE, DRAG, CTR BOX, PYLON
Zone 3.4 | Meth | Q321004852-4 | STANDARD | 2021-03-10 | AGX952AA | AGX952AA | 70098 | G05450605-101 | ANGLE, DRAG, CTR BOX, PYLON
Zone 3.4 | Meth | Q321004852-6 | STANDARD | 2021-03-10 | AGX952AA | AGX952AA | 70098 | G05366010-103 | FITTING, FWD ENG MOUNT
Zone 3.4 | Meth | Q321004852-7 | STANDARD | 2021-03-10 | AGX952AA | AGX952AA | 70098 | G05450606-101 | ANGLE, DRAG, CTR BOX, PYLON
Zone 3.4 | Meth | Q321004853-1 | STANDARD | 2021-03-10 | AGX952AA | AGX952AA | 70099 | G05363449-101 | DOUBLER SIDE PANEL AFT BARREL
Zone 3.4B | Meth | Q321004810-1 | STANDARD | 2021-03-10 | AGX952AA | AGX952B | 70099 | G00653060-003 | FLOOR BEAM EOP/WL/BL
Zone 3.4B | Meth | Q321004810-2 | STANDARD | 2021-03-10 | AGX952AA | AGX952B | 70099 | G00653060-003 | STRINGER RADIAL POSITIONS (SECT BR-BR)
Zone 3.4B | Meth | Q321004810-3 | STANDARD | 2021-03-10 | AGX952AA | AGX952B | 70099 | G00653060-003 | BUTT STRAP OML
Zone 3.4 | Meth | Q321005102-1 | STANDARD | 2021-03-16 | AGX952 | AGX830 | 70102 | G05364600-001 | POST, FUEL TANK FLOOR
Zone 3.4B | Meth | Q321004810-4 | STANDARD | 2021-03-10 | AGX952AA | AGX952B | 70099 | G00653060-003 | SKIN EOP
Zone 3.4B | Meth | Q321004810-5 | STANDARD | 2021-03-10 | AGX952AA | AGX952B | 70099 | G00606104-001 | SYM POINTS
Zone 3.4B | Meth | Q321004810-6 | STANDARD | 2021-03-10 | AGX952AA | AGX952B | 70099 | G00606104-001 | HSTAB PIVOT FITTINGS
Zone 3.4B | Meth | Q321004810-7 | STANDARD | 2021-03-10 | AGX952AA | AGX952B | 70099 | G00654510-001 | ENGINE MOUNTS
Zone 3.4 | Meth | Q321005016-1 | STANDARD | 2021-03-12 | AGX952 | AGX952 | 70101 | G05450171-004 | RIB ASSY, CTR BOX, PYLON | NO | [6 empty] | Fouling Rib VS engine Mount fitting. AC 70101
Zone 3.4 | Meth | Q321005099-1 | STANDARD | 2021-03-16 | AGX944 | AGX944 | RR096 | G05450500-104-03 | SKIN, FIXED LE, PYLON
Zone 3.4 |  | Q321005227-1 | STANDARD | 2021-03-17 | AGX948 | AGX948 | 70102 | G05450056-010-01 | TE ASSY, FIXED, PYLON
Zone 3.4 | Meth | Q321005292-1 | STANDARD | 2021-03-18 | AGX952AA | AGX952AA | 70101 | G05450502-104 | SKIN, UPPER, CTR BOX, PYLON | Yes |  | COS | 2560 4470 |  |  | 70102-X | For query 2560 70102-X For query 4470, no effy yet
Zone 3.4 | Meth | Q321005292-2 | STANDARD | 2021-03-18 | AGX952AA | AGX952AA | 70101 | G05450410-102 | STIFFENER, CTR BOX, PYLON | Yes |  | COS | 4470 |  |  | TBD | No effy yet
Zone 3.4 | TOOL CRIB | Q321005292-3 | STANDARD | 2021-03-18 | AGX952AA | AGX952AA | 70101 | G05450503-104 | SKIN , LWR, CTR BOX, PYLON | [7 empty] | TOOL CRIB
Zone 3.4 | Meth | Q321005292-5 | STANDARD | 2021-03-18 | AGX952AA | AGX952AA | 70101 | G05450075-002 | BOX INSTL, CENTER, PYLON | Yes |  | COS | 2560 |  |  | 70109-X | New COS for drag angle
Zone 3.4 | Meth | Q321005295-2 | STANDARD | 2021-03-18 | AGX952 | AGX952 | 70101 | G05450485-101-02 | ANGLE, CTR BOX, PYLON | No |  | COS | 3500 |  |  |  | 3500 rejected. New query pending ECD 26 MAR
Zone 3.4 | Meth | Q321005295-3 | STANDARD | 2021-03-18 | AGX952 | AGX952 | 70101 | G05450606-101-03 | ANGLE, DRAG, CTR BOX, PYLON | Yes |  | COS | 2560 |  |  | 70108-X | New COS for drag angle
Zone 3.4 | Meth | Q321005295-4 | STANDARD | 2021-03-18 | AGX952 | AGX952 | 70101 | G05450410-101-03 | STIFFENER, CTR BOX, PYLON | Yes |  | COS | 4470 |  |  | TBD | No effy yet
Zone 3.4 | Meth | Q321005327-1 | STANDARD | 2021-03-18 | AGX952 | AGX952 | 70101 | G05450611-103-02 | ANGLE, DRAG, FIXED TE, PYLON | No | [6 empty] | Hole close to radius due to accumulation of tolerances in WL.
Zone 3.4 | Meth | Q321005367-1 | STANDARD | 2021-03-18 | AGX952 | AGX952 | 70101 | G05450620-104 | FITTING, TENSION, FIXED LE, PYLON | Yes |  | COS | 2560 |  |  | 70105-X | New COS for tension fitting
Zone 3.4 | Meth | Q321005395-1 | STANDARD | 2021-03-19 | AGX945 | AGX945 | 70103 | G05450500-103-03 | SKIN, FIXED LE, PYLON | Yes |  |  | 4183 |  |  |  | DDA 12219A. No effy yet
Zone 3.4 | Meth | Q321005404-1 | STANDARD | 2021-03-19 | AGX952 | AGX952 | 70101 | G05450612-103-02 | ANGLE, DRAG, FIXED TE, PYLON | No | [6 empty] | Low ED en angle por desv/acumulacion tol en WL
Zone 3.4 | Meth | Q321005419-1 | STANDARD | 2021-03-19 | AGX952 | AGX952 | 70101 | G05450628-102-02 | FITTING, CTR BOX, PYLON | No |  |  | 3500 |  |  |  | Query rechazado. Nuevo query pendiente ECD 26 MAR
Zone 3.4 | Meth | Q321005455-1 | SNC | 2021-03-19 | AGX952 | AGX952B | 70099 | G05372301-004 | FITTING ASSY, ECS PACK, REAR FUSE
Zone 3.4 | Meth | Q321005292-6 | STANDARD | 2021-03-20 | AGX952 | AGX952B | 70101 | G05450606-102 | ANGLE, DRAG, CTR BOX, PYLON | No | [6 empty] | Hole clse to radius due to accumulation of tolerances/dev in WL
Zone 3.4 |  | Q321005534-1 | STANDARD | 2021-03-22 | AGX944 | AGX944 | 70104 | G05450500-104-03 | SKIN, FIXED LE, PYLON
Zone 3.4 |  | Q321005619-1 | STANDARD | 2021-03-22 | AGX952 | AGX952 | 70101 | G05450073-002-01 | TE INSTL, PYLON
Zone 3.4 |  | Q321005793-1 | STANDARD | 2021-03-24 | AGX952AA | AGX952B | 70100 | G00653060-003 | FLOOR BEAM EOP/WL/BL
Zone 3.4 |  | Q321005793-2 | STANDARD | 2021-03-24 | AGX952AA | AGX952B | 70100 | G00653060-003 | BUTT STRAP OML
Zone 3.4 |  | Q321005793-3 | STANDARD | 2021-03-24 | AGX952AA | AGX952B | 70100 | G00653060-003 | SKIN EOP
Zone 3.4 |  | Q321005793-4 | STANDARD | 2021-03-24 | AGX952AA | AGX952B | 70100 | G00606104-001 | SYM POINTS
Zone 3.4 |  | Q321005793-5 | STANDARD | 2021-03-24 | AGX952AA | AGX952B | 70100 | G00606104-001 | HSTAB PIVOT FITTINGS
Zone 3.4 |  | Q321005793-6 | STANDARD | 2021-03-24 | AGX952AA | AGX952B | 70100 | G00654510-001 | ENGINE MOUNTS
Zone 3.3 | Meth | Q321005839-1 | STANDARD | 2021-03-25 | AGX952AA | AGX952AA | 70100 | G05360001-003 | STRINGER RADIAL
Zone 3.3 | Meth | Q321005857-1 | STANDARD | 2021-03-25 | AGX952 | AGX952 | 70102 | G05450606-101 | ANGLE, DRAG, CTR BOX, PYLON
Zone 4 | Meth | Q321004114-1 | STANDARD | 2021-03-01 | AGX955AA | AGX955AA | 70096 | G09171051-017 | HARNESS, AFT FUSE, REAR LHS RAB |  | SI |  |  | 2 Análisis en Proceso |  |  | Query 3942
Zone 4 | Meth | Q321004123-1 | STANDARD | 2021-03-01 | AGX955AA | AGX955AA | 70096 | G09171051-017 | HARNESS, AFT FUSE, REAR LHS RAB |  | SI |  |  | 2 Análisis en Proceso |  |  | Query 4173 Clamps*
Zone 4 | Meth | Q321004125-1 | STANDARD | 2021-03-01 | AGX955AA | AGX955AA | 70096 | G09181002-003 | CABLE, COAX, NAV 1 VOR LOC VLB |  | SI | RFC | 61498 | 4 Solución en espera de ser aprobada |  | Effect 70120
Zone 4 | Meth | Q321004130-1 | STANDARD | 2021-03-01 | AGX955AA | AGX955AA | 70096 | G09172051-017 | HARNESS, AFT FUSE, REAR RHS RBB |  | SI |  |  | 2 Análisis en Proceso |  |  | Query 4173 Clamps*
Zone 4 | Meth | Q321004131-1 | STANDARD | 2021-03-01 | AGX955AA | AGX955AA | 70096 | G09172051-017 | HARNESS, AFT FUSE, REAR RHS RBB | Yes | SI |  |  | 2 Análisis en Proceso |  |  | Query 4451 Clamps*
Zone 4 | Meth | Q321004131-2 | STANDARD | 2021-03-01 | AGX955AA | AGX955AA | 70096 | G09172051-017 | HARNESS, AFT FUSE, REAR RHS RBB |  | SI |  |  | 2 Análisis en Proceso |  |  | Query 4173 Clamps*
Zone 4 | Meth | Q321004155-1 | STANDARD | 2021-03-01 | AGX975A | AGX975AA | 70095 | G02197162-012-01 | INLET ASSY, MECH, PRECOOLER, PYLON |  | SI |  |  | 4 Solución en espera de ser aprobada |  |  | Query 3274 Pylons CSK. DDA 10881 A
Zone 4 | Meth | Q321004293-1 | STANDARD | 2021-03-03 | AGX975AA | AGX975AA | 70095 | G02197162-011-01 | INLET ASSY, MECH, PRECOOLER, PYLON |  | SI |  |  | 4 Solución en espera de ser aprobada |  |  | Query 3274 Pylons CSK. DDA 10881 A
Zone 4 | Meth | Q321004293-1 | STANDARD | 2021-03-03 | AGX975AA | AGX975AA | 70095 | G02197162-011-01 | INLET ASSY, MECH, PRECOOLER, PYLON |  | SI |  |  | 4 Solución en espera de ser aprobada |  |  | Query 3274 Pylons CSK. DDA 10881 A
Zone 4 | Meth | Q321004361-1 | STANDARD | 2021-03-03 | AGX955AA | AGX955AA | 70097 | G09171051-017 | HARNESS, AFT FUSE, REAR LHS RAB |  | SI |  |  | 2 Análisis en Proceso |  |  | Query 3942
Zone 4 | Meth | Q321004378-1 | STANDARD | 2021-03-03 | AGX985A | AGX985AA | 70094 | G05530150-001-90 | FAIRING INSTL, BULLET |  | SI |  |  | 2 Análisis en Proceso |  |  | Bullet fairing flushness
Zone 4 | Meth | Q321004384-1 | STANDARD | 2021-03-04 | AGX985AA | AGX965AA | 70094 | G02123249-003 | DUCT ASSY, RIGID |  | SI |  |  | 1 Problema detectado |  |  | ID under clamp. ECS
Zone 4 | Meth | Q321004534-1 | TECHNICAL | 2021-03-05 | AGX955AA | AGX955AA | 70097 | G09181002-003 | CABLE, COAX, NAV 1 VOR LOC VLB |  | SI | RFC | 61498 | 4 Solución en espera de ser aprobada |  | Effect 70120
Zone 4 | Meth | Q321004535-1 | TECHNICAL | 2021-03-05 | AGX955AA | AGX955AA | 70097 | G09172051-017 | HARNESS, AFT FUSE, REAR RHS RBB |  | SI |  |  | 2 Análisis en Proceso |  |  | Query 4451 Clamps*
Zone 4 | Meth | Q321004542-1 | TECHNICAL | 2021-03-05 | AGX955A | AGX955AA | 70097 | G05363514-101 | FRAME, AFT ENG MOUNT, REAR FUSE |  | SI |  |  | 3 Causa Raiz detectada |  |  | Query 3546 EWIS Standoff
Zone 4 | Meth | Q321004568-1 | TECHNICAL | 2021-03-05 | AGX975AA | AGX985AA | 70096 | G02691253-003 | TUBE ASSY, FIDEX, ENG LH |  | SI |  |  | 1 Problema detectado |  |  | Low clearance Fidex pipe VS clamp
Zone 4 | Meth | Q321004570-1 | TECHNICAL | 2021-03-05 | AGX955AA |  | 70098 | G09181002-003 | CABLE, COAX, NAV 1 VOR LOC VLB |  | SI | RFC | 61498 | 4 Solución en espera de ser aprobada |  | Effect 70120
Zone 4 | Meth | Q321004571-1 | TECHNICAL | 2021-03-05 | AGX955AA |  | 70099 | G09181002-003 | CABLE, COAX, NAV 1 VOR LOC VLB |  | SI | RFC | 61498 | 4 Solución en espera de ser aprobada |  | Effect 70120
Zone 4 | Meth | Q321004572-1 | TECHNICAL | 2021-03-05 | AGX955AA |  | 70100 | G09181002-003 | CABLE, COAX, NAV 1 VOR LOC VLB |  | SI | RFC | 61498 | 4 Solución en espera de ser aprobada |  | Effect 70120
Zone 4 | Meth | Q321004573-1 | TECHNICAL | 2021-03-05 | AGX955AA |  | 70101 | G09181002-003 | CABLE, COAX, NAV 1 VOR LOC VLB |  | SI | RFC | 61498 | 4 Solución en espera de ser aprobada |  | Effect 70120
Zone 4 | Meth | Q321004574-1 | TECHNICAL | 2021-03-05 | AGX955AA |  | 70102 | G09181002-003 | CABLE, COAX, NAV 1 VOR LOC VLB |  | SI | RFC | 61498 | 4 Solución en espera de ser aprobada |  | Effect 70120
Zone 4 | Meth | Q321004575-1 | TECHNICAL | 2021-03-05 | AGX955AA |  | 70103 | G09181002-003 | CABLE, COAX, NAV 1 VOR LOC VLB |  | SI | RFC | 61498 | 4 Solución en espera de ser aprobada |  | Effect 70120
Zone 4 | Meth | Q321004576-1 | TECHNICAL | 2021-03-05 | AGX955AA |  | 70104 | G09181002-003 | CABLE, COAX, NAV 1 VOR LOC VLB |  | SI | RFC | 61498 | 4 Solución en espera de ser aprobada |  | Effect 70120
Zone 4 | Meth | Q321004577-1 | TECHNICAL | 2021-03-05 | AGX955AA |  | 70105 | G09181002-003 | CABLE, COAX, NAV 1 VOR LOC VLB |  | SI | RFC | 61498 | 4 Solución en espera de ser aprobada |  | Effect 70120
Zone 4 | Meth | Q321004578-1 | TECHNICAL | 2021-03-05 | AGX955AA |  | 70106 | G09181002-003 | CABLE, COAX, NAV 1 VOR LOC VLB |  | SI | RFC | 61498 | 4 Solución en espera de ser aprobada |  | Effect 70120
Zone 4 | Meth | Q321004579-1 | TECHNICAL | 2021-03-05 | AGX955AA |  | 70107 | G09181002-003 | CABLE, COAX, NAV 1 VOR LOC VLB |  | SI | RFC | 61498 | 4 Solución en espera de ser aprobada |  | Effect 70120
Zone 4 | Meth | Q321004580-1 | TECHNICAL | 2021-03-05 | AGX955AA |  | 70108 | G09181002-003 | CABLE, COAX, NAV 1 VOR LOC VLB |  | SI | RFC | 61498 | 4 Solución en espera de ser aprobada |  | Effect 70120
Zone 4 | Meth | Q321004581-1 | TECHNICAL | 2021-03-05 | AGX955AA |  | 70109 | G09181002-003 | CABLE, COAX, NAV 1 VOR LOC VLB |  | SI | RFC | 61498 | 4 Solución en espera de ser aprobada |  | Effect 70120
Zone 4 | Meth | Q321004646-1 | STANDARD | 2021-03-08 | AGX955AA | AGX955AA | 70097 | G09172051-017 | HARNESS, AFT FUSE, REAR RHS RBB |  | SI |  |  | 2 Análisis en Proceso |  |  | Query 4451 Clamps*
Zone 4 | Meth | Q321004646-2 | STANDARD | 2021-03-08 | AGX955AA | AGX955AA | 70097 | G09172051-017 | HARNESS, AFT FUSE, REAR RHS RBB |  | SI |  |  | 2 Análisis en Proceso |  |  | Query 4173 Clamps*
Zone 4 | Meth | Q321004671-1 | STANDARD | 2021-03-09 | AGX985A | AGX985AA | 70095 | G02691253-003 | TUBE ASSY, FIDEX, ENG LH |  | SI |  |  | 1 Problema detectado |  |  | Low clearance Fidex pipe VS clamp
Zone 4 | Meth | Q321004725-1 | STANDARD | 2021-03-09 | AGX985AA | AGX985AA | 70095 | G05530175-001 | LE INST, VSTAB |  | SI |  |  | 1 Problema detectado |  |  | Steps LE Vstab
Zone 4 | Meth | Q321004851-1 | STANDARD | 2021-03-10 | AGX985A | AGX985AA | 70095 | G05530150-001-90 | FAIRING INSTL, BULLET | wip | SI |  |  | 2 Análisis en Proceso |  |  | Bullet fairing flushness
Zone 4 | METH | Q321004875-1 | STANDARD | 2021-03-11 | AGX965AA | AGX965AA | 70096 | G02691203-005 | TUBE ASSY, FIDEX, APU |  | SI |  |  | 2 Análisis en Proceso |  |  | Fidex fouling
Zone 4 | METH | Q321004876-1 | STANDARD | 2021-03-11 | AGX975A | AGX975AA | 70096 | G02197162-012-01 | INLET ASSY, MECH, PRECOOLER, PYLON |  | SI |  |  | 4 Solución en espera de ser aprobada |  |  | Query 3274 Pylons CSK. DDA 10881 A
Zone 4 | Meth | Q321004986-1 | STANDARD | 2021-03-12 | AGX964A | AGX964AA | 70097 | 627700-1002 | PTU - MOTOR/PUMP PACKAGE INTERFACE DEF |  | SI | RFC | 3000166121 | 4 Solución en espera de ser aprobada |  |  | RFC approved, waiting for ECD
Zone 4 | Meth | Q321005052-1 | STANDARD | 2021-03-12 | AGX965AA | AGX965AA | 70097 | G02691203-005 | TUBE ASSY, FIDEX, APU |  | SI |  |  | 2 Análisis en Proceso |  |  | Fidex fouling
Zone 4 |  | Q321005176-1 | STANDARD | 2021-03-17 | AGX975AA | AGX975AA | 70096 | G02197162-011-01 | INLET ASSY, MECH, PRECOOLER, PYLON |  | SI |  |  | 4 Solución en espera de ser aprobada |  |  | Query 3274 Pylons CSK. DDA 10881 A
Zone 4 |  | Q321005268-1 | STANDARD | 2021-03-18 | AGX955AA | AGX955AA | 70098 | G09172051-017 | HARNESS, AFT FUSE, REAR RHS RBB |  | SI |  |  | 2 Análisis en Proceso |  |  | Query 4451 Clamps*
Zone 4 |  | Q321005270-1 | STANDARD | 2021-03-18 | AGX955AA | AGX955AA | 70098 | G09172051-017 | HARNESS, AFT FUSE, REAR RHS RBB
Zone 4 |  | Q321005270-2 | STANDARD | 2021-03-18 | AGX955AA | AGX955AA | 70098 | G09172051-017 | HARNESS, AFT FUSE, REAR RHS RBB
Zone 4 | Meth | Q321005268-1 | STANDARD | 2021-03-18 | AGX955AA | AGX955AA | 70098 | G09172051-017 | HARNESS, AFT FUSE, REAR RHS RBB | Yes | SI |  |  | 2 Análisis en Proceso |  |  | Query 4447 Clamps*
Zone 4 | Meth | Q321005270-1 | STANDARD | 2021-03-18 | AGX955AA | AGX955AA | 70098 | G09172051-017 | HARNESS, AFT FUSE, REAR RHS RBB | Yes | SI |  |  | 2 Análisis en Proceso |  |  | Query 4451 Clamps*
Zone 4 | Meth | Q321005270-2 | STANDARD | 2021-03-18 | AGX955AA | AGX955AA | 70098 | G09172051-017 | HARNESS, AFT FUSE, REAR RHS RBB | Yes | SI |  |  | 2 Análisis en Proceso |  |  | Query 4447 Clamps*
Zone 4 | Meth | Q321005356-1 | EXTENSION | 2021-03-18 | AGX955AA |  | 70099 | G09172051-017 | HARNESS, AFT FUSE, REAR RHS RBB | Yes | SI |  |  | 2 Análisis en Proceso |  |  | Query 4447 Clamps*
Zone 4 | Meth | Q321005403-1 | SR | 2021-03-19 | AGX955AA | AGX955AA | 70098 | G05363514-101 | FRAME, AFT ENG MOUNT, REAR FUSE |  | SI |  |  | 3 Causa Raiz detectada |  |  | Query 3546 EWIS Standoff
Zone 4 | Meth | Q321005407-1 | STANDARD | 2021-03-19 | AGX964A | AGX965AA | 70098 | 627700-1002 | PTU - MOTOR/PUMP PACKAGE INTERFACE DEF |  | SI | RFC | 3000166121 | 4 Solución en espera de ser aprobada |  |  | RFC approved, waiting for ECD
Zone 4 | Meth | Q321005497-1 | STANDARD | 2021-03-20 | AGX985AA | AGX985AA | 70096 | G05530150-001-90 | FAIRING INSTL, BULLET |  | SI |  |  | 2 Análisis en Proceso |  |  | Bullet fairing flushness
Zone 4 | Meth | Q321005499-1 | STANDARD | 2021-03-20 | AGX985AA | AGX985AA | 70096 | G02123249-003 | DUCT ASSY, RIGID |  | SI |  |  | 1 Problema detectado |  |  | ID under clamp. ECS
Zone 4 |  | Q321005676-1 | STANDARD | 2021-03-23 | AGX985A | AGX975AA | 70097 | G02197162-012-01 | INLET ASSY, MECH, PRECOOLER, PYLON |  | SI |  |  | 4 Solución en espera de ser aprobada |  |  | Query 3274 Pylons CSK. DDA 10881 A
Zone 4 | Meth | Q321005795-1 | STANDARD | 2021-03-25 | AGX985AA | AGX965AA | 70097 | G05375300-001 | DRAIN INSTL, REAR FUSE |  | SI |  |  | 3 Causa Raiz detectada |  |  | Query 4515
Zone 4 | Meth | Q321005803-1 | STANDARD | 2021-03-25 | AGX955AA | AGX955AA | 70099 | G09172051-017 | HARNESS, AFT FUSE, REAR RHS RBB |  | SI |  |  | 2 Análisis en Proceso |  |  | Query 4451 Clamps*
Zone 4 | Meth | Q321005803-2 | STANDARD | 2021-03-25 | AGX955AA | AGX955AA | 70099 | G09172051-017 | HARNESS, AFT FUSE, REAR RHS RBB |  | SI |  |  | 2 Análisis en Proceso |  |  | Query 4447 Clamps*
Zone 5 | Meth | Q321004547-1 | TECHNICAL | 2021-03-05 | AGX276A | AGX276 | 70105 | G05311192-101/01 | ANGLE, MLG, DOOR
Zone 5 | Meth | Q321004669-1 | STANDARD | 2021-03-09 | AGX290 | AGX290 | 70104 | G05310750-001-01 | COCKPIT NOSE ASSY
Zone 5 | Meth | Q321004669-2 | STANDARD | 2021-03-09 | AGX290 | AGX290 | 70104 | G05310750-001-01 | COCKPIT NOSE ASSY
Zone 5 | Meth | Q321004669-3 | STANDARD | 2021-03-09 | AGX290 | AGX290 | 70104 | G05310750-001-01 | COCKPIT NOSE ASSY
Zone 5 | Meth | Q321004669-4 | STANDARD | 2021-03-09 | AGX290 | AGX290 | 70104 | G05310750-001-01 | COCKPIT NOSE ASSY
Zone 5 |  | Q321005756-1 | STANDARD | 2021-03-24 | AGX280 | AGX280 | 70106 | G05310851-111-01 | BULKHEAD, FR3
Zone 5 |  | Q321005779-1 | STANDARD | 2021-03-24 | AGX290AA | AGX290AA | 70106 | G05310750-001-01 | COCKPIT NOSE ASSY
Zone 5 |  | Q321005779-2 | STANDARD | 2021-03-24 | AGX290AA | AGX290AA | 70106 | G05310750-001-01 | COCKPIT NOSE ASSY
Zone 5 |  | Q321005779-3 | STANDARD | 2021-03-24 | AGX290AA | AGX290AA | 70106 | G05310750-001-01 | COCKPIT NOSE ASSY

## Today
ZONE | BADGE | NCR # | NCR Type | Disc. Create Date | Work Centre | Norm. Line Position | Tail # | Part # | Part Desc | Action | RFC/Query | ECD or A/C | Comments
3.3 |  | Q321005663-1 | STANDARD | 2021-03-23 | AGX950 | AGX950 | 70102 | G05363921-003 | JOINT INSTL, STA 1016, REAR FUSE
3.3 |  | Q321005707-1 | STANDARD | 2021-03-23 | AGX950 | AGX950 | 70102 | G02100001-001 | DUCT, RAM AIR
4 |  | Q321005676-1 | STANDARD | 2021-03-23 | AGX985A | AGX975AA | 70097 | G02197162-012-01 | INLET ASSY, MECH, PRECOOLER, PYLON
MTS |  | Q321005654-1 | STANDARD | 2021-03-23 | SGX965A | SGX965A |  | G02490961-103 | SUPPORT, PANEL SERVICE LIGHTS, AFT FUSE
MTS |  | Q321005710-1 | STANDARD | 2021-03-23 | SGX900A | SGX900A |  | G05211418-101 | PLATE, HINGE STEP, PASS ACS DR

## Today Chart
2021-04-05
Row Labels | Count of RFC/Query
MTS
(blank)
ZONE 2 | 3
r | 3
ZONE 3.1
(blank)
ZONE 3.2
(blank)
ZONE 3.4 | 7
g | 3
v | 4
(blank)
ZONE 3.4B | 1
v | 1
ZONE 4
(blank)
ZONE 5 | 3
v | 3
(blank)
(blank)
(blank)
Grand Total | 14

## Full chart
Disc. Create Date | (All)
Row Labels | Count of RFC/Query | Count of NCR #
0 |  | 10
2 |  | 1
3 |  | 16
3.1 |  | 2
3.4 | 5 | 25
4 |  | 2
1502 |  | 1
4
AGX226AA |  | 1
AGX277 |  | 1
AGX290 |  | 5
AGX710 |  | 1
AGX740 |  | 1
AGX740AA |  | 1
AGX742AA |  | 2
AGX744 |  | 3
AGX744AA |  | 1
AGX760AA |  | 2
AGX770 |  | 1
AGX770AA |  | 1
AGX784 |  | 3
AGX802 |  | 1
AGX802AA |  | 1
AGX806 |  | 1
AGX806AA |  | 2
AGX807 |  | 1
AGX810 |  | 6
AGX810AA |  | 18
AGX818 |  | 1
AGX830 |  | 1
AGX830AA |  | 14
AGX872AA |  | 2
AGX874AA |  | 1
AGX879 |  | 1
AGX880AA |  | 8
AGX882AA |  | 3
AGX888AA |  | 1
AGX890AA |  | 2
AGX942AA |  | 1
AGX944 |  | 1
AGX944AA |  | 1
AGX945 |  | 1
AGX946 |  | 1
AGX949 |  | 1
AGX950AA |  | 27
AGX952 |  | 4
AGX952AA |  | 96
AGX955AA |  | 15
AGX964AA |  | 4
AGX965AA |  | 2
AGX985AA |  | 9
AGX999AA |  | 4
C1 |  | 1
EXTENSION |  | 10
Fase 5 |  | 3
MTS |  | 6
SNC |  | 3
STANDARD |  | 17
ZONE 1 |  | 12
ZONE 2 | 6 | 10
ZONE 3 | 52 | 121
Zone 3.1 |  | 9
Zone 3.2 | 1 | 2
Zone 3.3 |  | 5
Zone 3.4 | 14 | 23
ZONE 4 | 2 | 60
ZONE 5 |  | 8
(blank)
Grand Total | 80 | 605